## Resume
PROJECT |  | NEW CONSTRUCTION OF LIBRARY IN TIMOR-LESTE
ORGANIZATION |  | MANY HANDS ONE NATION (MAHON)
DIRECTOR |  | ANGELO FERNANDO XIMENES
No | Items | Amount of Grant |  | Details | Breack Down | Percentages
1 | Materials for the New Construction of LIBRARY | 22095.55 | 1.1 | PRELIMINARIES / SERVISU PRELIMINARIO | 1530 | 73.65%
|  |  | 1.2 | GROUND, CONCRETE, MASSONRY AND BLOCK WORKS | 9596.5
|  |  | 1.3 | WINDOWS & DOORS HARDWARES / JANELA NO ODOMATAN | 1958
|  |  | 1.4 | STEEL ROOF STRUCTURES / ESTRUTURA KAKULUK HO BAJA | 7760.05
|  |  | 1.5 | ELECTRICAL MATERIALS / MATERIAL ELETRISIDADE | 1063.5
|  |  | 1.6 | PLUMBING MATERIALS / MATERIAL BE-MOS | 187.5
2 | LIBRARY MATERIALS | 4928.45 | 1 | LIBRARY MATERIALS | 4928.45 | 16.43%
3 | Labor for construction | 2976 | 2.1. | Construction Supervisor ($12/day *40days * 1 person) | 480 | 9.92%
|  |  | 2.2. | Civil Engineer ($12/day * 40 days * 1 person) | 480
|  |  | 2.3. | Laborer / Badaen ($10/day * 40 days * 2 persons) | 800
|  |  | 2.4. | Assistants ($7/day * 40 days * 4 persons) | 1120
|  |  | 2.5. | Electrician ($12/day * 6 days * 1 person) | 72
|  |  | 2.6. | Plumbing Installations ($12/day * 2 days * 1 person) | 24
AUTO - TOTAL |  | 30000 |  | - |  | 100%

## Materials Calculations
PROJECT |  | NEW CONSTRUCTION OF LIBRARY IN TIMOR-LESTE
ORGANIZATION |  | MANY HANDS ONE NATION (MAHON)
DIRECTOR |  | ANGELO FERNANDO XIMENES
No | Items | Amount of Grant |  | Details | Qty | Unit | U$/Unit | Total Unit ($) | Remarks / Local Suppliers
1 | Materials for the New Construction of EBF Taimea, Bobonaro | 22095.55 | A | PRELIMINARIES / SERVISU PRELIMINARIO |  |  |  | 1530
|  |  | 1 | Temporary site buildings (temporary warehouse for drooping the construction materials) | Ls |  | 0 | 300 | MAHON
|  |  | 2 | Water for the work | Ls |  | 0 | 200
|  |  | 3 | Notice Board + Placa ($200 + 100) | Ls |  | 0 | 200 | Local supplier
|  |  | 4 | Power and lighting | Ls |  | 0 | 150 | Loja Vitoria
|  |  | 5 | Temporary hoardings / Pagar | Ls |  | 0 | 100 | Loja Minuvarto
|  |  | 6 | Samples of materials | Ls |  | 0 | 100 | Order husi Dili
|  |  | 7 | Cleaning site during construction | Ls |  | 0 | 100 | MAHON
|  |  | 8 | Cleaning site and the work at completion | Ls |  | 0 | 70 | MAHON
|  |  | 9 | Temporary toilet facilities
|  |  | 10 | The contractor shall provide approval temporary toilet facilities at a location to be approved on site by the client supervisor | Ls | 0 | 0 | 150 | MAHON
|  |  | 11 | Safety clothing
|  |  | 12 | The contractor is to provide the safety clothing to the site employees while working on the project | Note
|  |  | 13 | Leather Boots with metalic protective devices for toes | 4 | Pcs | 15 | 60 | Loja Vitoria
|  |  | 14 | Hard hats of approved colour rated for normal construction | 4 | Pcs | 10 | 40 | Loja Vitoria
|  |  | 15 | Protective Hand Gloves | 3 | Sets | 12 | 36 | Loja Vitoria
|  |  | 16 | Vest for Labour | 2 | Ls | 12 | 24 | Loja Vitoria
|  |  | B | GROUND, CONCRETE, MASSONRY AND BLOCK WORKS |  |  |  | 9596.5
|  |  | 1 | Stone + Transport (Fatuk + transporte) | 12 | Trucks | 80 | 960 | Loja Alexandro
|  |  | 2 | Sands + Transport (Rai henek + transporte) | 15 | Trucks | 80 | 1200 | Loja Alexandro
|  |  | 3 | Gravel / Fatuk kerikil | 10 | Trucks | 80 | 800 | Loja Alexandro
|  |  | 4 | Cement (Sementi) | 125 | Sacks | 5 | 625 | Loja Alexandro
|  |  | 5 | Steel bar 12mm (Besi) | 40 | Ls | 7 | 280 | Loja Minuvarto
|  |  | 6 | Steel bar 10mm (Besi) | 40 | Ls | 6.75 | 270 | Loja Minuvarto
|  |  | 7 | Steel bar 8mm (Besi) | 45 | Ls | 4.5 | 202.5 | Loja Minuvarto
|  |  | 8 | Steel bar 6mm (Besi) | 50 | Ls | 3.75 | 187.5 | Loja Minuvarto
|  |  | 9 | Steel wire (Arame kesi besi) | 7 | Rolls | 3.5 | 24.5 | Loja Minuvarto
|  |  | 10 | Strong wood 3 x10 cm (Ai) | 35 | Ls | 7 | 245 | Loja Alexandro
|  |  | 11 | Strong wood 4 x 6 cm (Ai) | 1 | Kb | 375 | 375 | Loja Alexandro
|  |  | 12 | Strong wood 5 x 7 cm (Ai) | 1 | Kb | 395 | 395 | Loja Alexandro
|  |  | 13 | Blocks 20 x 40 cm for all constructions need (Batako) | 3500 | Pcs | 1 | 3500 | Loja Alexandro
|  |  | 14 | Clossed for toilet | 4 | Pcs | 35 | 140 | Loja Alexandro
|  |  | 15 | Water clossed for handwash (Fase liman fatin) | 4 | Pcs | 43 | 172 | Loja Alexandro
|  |  | 16 | Water flush for men's toilet (Soe be fatin ba mane) | 4 | Pcs | 55 | 220 | Loja Alexandro
|  |  | C | WINDOWS & DOORS HARDWARES / JANELA NO ODOMATAN |  |  |  | 1958
|  |  | 1 | Aluminium window frames 2.28m x x 1.22mm (kosen Janela alm.) | 10 | Pcs | 85 | 850 | Loja Minuvarto
|  |  | 2 | Window glasses 6mm x 0.70m x 152mm | 70 | Pcs | 1 | 70 | Loja Minuvarto
|  |  | 3 | Door frames (Pa) 0.935 x 2.11m (Kosen odomatan aula) | 2 | Pcs | 125 | 250 | Loja Alexandro
|  |  | 4 | Door frames (Pc) 0.70 x 2.11m (Kosen odomatan toilet) | 2 | Pcs | 85 | 170 | Loja Alexandro
|  |  | 5 | Doors (Pa) 0.935 x 2.11m (Folha odomatan aula) | 2 | Pcs | 125 | 250 | Loja Alexandro
|  |  | 6 | Doors (Pc) 0.86 x 2.07m (Folha odomatan toilet) | 2 | Pcs | 110 | 220 | Loja Alexandro
|  |  | 7 | Doors hangings (Engsel odomatan) | 12 | Pcs | 5 | 60 | Loja Vitoria
|  |  | 8 | Door Keys (Savi odomatan) | 4 | Pcs | 12 | 48 | Loja Vitoria
|  |  | 9 | Plate screwed to door (Plat prevensaun be ba odomatan) | 2 | Pcs | 20 | 40 | Loja Vitoria
|  |  | D | STEEL ROOF STRUCTURES / ESTRUTURA KAKULUK HO BAJA |  |  |  | 7760.05
|  |  | 1 | C75 x 40 x 1mm cold formed lipped channel bottom chord (1/7.70m and 1/4.80 long per truss) (Baja balok kuda-kuda medida diferente) | 75 | Pcs | 5 | 375 | Loja Alexandro
|  |  | 2 | C75 x 40 x 1mm cold formed lipped channel bottom chord (1/7.24m long per truss) (Baja balok kuda-kuda medida diferente) | 75 | Pcs | 5 | 375 | Loja Alexandro
|  |  | 3 | C75 x 40 x 1mm cold formed lipped channel ties and struts - 2/0.70m, 2/1.23m, 2/1.32 and 2/1.67m long per truss (Baja balok kuda-kuda medida diferente) | 70 | Pcs | 5 | 350 | Loja Alexandro
|  |  | 4 | C75 x 40 x 1mm cold formed open channel back-to-back web stiffeners (C75 x 40 x 1mm 2/0.20m and 1/0.20m long per truss) (Baja plat aperta kuda-kuda medida diferente) | 12 | Pcs | 5.5 | 66 | Loja Alexandro
|  |  | 5 | 12-14 x 25 self drilling metal tek screws for jointing truss at the workshop (72 per truss) (Parfuzu ba kuda-kuda) | 175 | No | 0.15 | 26.25 | Loja Vitoria
|  |  | 6 | C75 X 40 X 1mm cold formed lipped channel rafter 4.80mm long (Baja kuda-kuda la-ho-rangka) | 15 | Pcs | 5 | 75 | Loja Vitoria
|  |  | 7 | C75 X 40 X 1mm cold formed lipped channel rafter 6.70mm long (Baja kuda-kuda la-ho-rangka) | 21 | Pcs | 5 | 105 | Loja Vitoria
|  |  | 8 | C75 X 40 X 1mm cold formed lipped channel back-to-back web stiffeners (C75 x 40 x 1mm 2/0.20mm long per rafter) (Istikador) | 0.6 | Pcs | 5 | 3 | Loja Vitoria
|  |  | 9 | 12-14 x 25 self drilling metal tek screws for jointing truss at the workshop (6 per rafter) (Parfuzu) | 18 | No | 0.15 | 2.7 | Loja Alexandro
|  |  | 10 | 100 x 50 x 3mm RHS beams along verendah (Besi kotak) | 23.4 | Pcs | 12 | 280.8 | Loja Alexandro
|  |  | 11 | C45 x 35 1mm "Topspan" or approved equivalent steel channel purlins (14/3.30m, 56/5.20m, 14/5.90m long) (Gordin) | 150 | Pcs | 5 | 750 | Loja Alexandro
|  |  | 12 | 12-14 x 25 self drilling metal tek screws forfixing purlin on site (Parfuzu) | 1302 | No | 0.15 | 195.3 | Loja Alexandro
|  |  | 13 | 12-14 x 25 self drilling metal tek screwsfor jointing of top span on site (4 screws per joint) (Parfuzu) | 280 | No | 0.15 | 42 | Loja Alexandro
|  |  | 14 | Bent plate 230mm girth colorbond fascia (Seng plat) | 70 | m | 8 | 560 | Loja Alexandro
|  |  | 15 | 12-14 x 25 self drilling metal tek screws for fixing fascia to end of top chord on site (Parfuzu) | 500 | No | 0.15 | 75 | Loja Alexandro
|  |  | 16 | C45 x 35 x 1mm "topspan" or approved equivalent steel channels purlins (14/3.30m, 56/5.20m and 14/5.90m long) (Gordin Baja) | 250 | Pcs | 0.5 | 125 | Loja Alexandro
|  |  | 17 | 035mm Zinc x 5m x 100mm (Kalen) | 50 | Pcs | 19 | 950 | Loja Minuvarto
CEILING / PLAFON
|  |  | 18 | 6mm Plywood (Triplex 6mm) | 40 | Pcs | 6 | 240 | Loja Minuvarto
|  |  | 19 | Screws 6 - 18 x 25mm (Parfuzu) | 200 | Pcs | 0.25 | 50 | Loja Alexandro
|  |  | 20 | Stell ceiling battens 13mm x 0.35 x 0.42mm (Rangka baja plafon) | 22 | Pcs | 7.5 | 165 | Loja Minuvarto
|  |  | 21 | Joint ceiling 25 x 25mm (Ai lis junta plafon) | 20 | Pcs | 6 | 120 | Loja Alexandro
FINISHES
|  |  | 22 | Ceramic 200 x 200mm tiling for toilet areas (Keramik ba area sintina) | 36 | Boxes | 7.5 | 270 | Loja Alexandro
|  |  | 23 | Ceramic 300 x 300mm tiling to floors (Keramik Aula) | 112 | Boxes | 9.5 | 1064 | Loja Vitoria
|  |  | 24 | Ceramic 300 x 100mm tiling to toilet floors (Keramik sintina laran) | 64 | Boxes | 12 | 768 | Loja Vitoria
PAINTING
|  |  | 25 | Tint for external and internal painting (Tinta pinta liur no laran) | 4 | Pcs | 45 | 180 | Loja Minuvarto
|  |  | 26 | Tint for doors and windows (Tinta odomatan no janela) | 2 | Pcs | 16 | 32 | Loja Alexandro
|  |  | 27 | Painting rools (Rol tinta) | 3 | Pcs | 5 | 15 | Loja Alexandro
TRANSPORTATIONS / TRANSPORTE
|  |  | 28 | Transportation from Supplier to Project location | 4 | Trucks | 125 | 500 | Local supplier
|  |  | E | ELECTRICAL MATERIALS / MATERIAL ELETRISIDADE |  |  |  | 1063.5
|  |  | 1 | Main Switch Board (MSB) | 1 | Pc | 150 | 150 | Loja Vitoria
|  |  | 2 | Cable 3 x 2.5mm (Fiu Listrik 3x2.5mm) | 1 | Roll | 150 | 150 | Loja Alexandro
|  |  | 3 | Single light points + sockets | 4 | Sets | 35 | 140 | Loja Minuvarto
|  |  | 4 | Double light points sockets | 2 | Pcs | 43 | 86 | Loja Minuvarto
|  |  | 5 | Single Switch + Sockets | 1 | Pc | 7 | 7 | Loja Alexandro
|  |  | 6 | Double Switch + Sockets | 2 | Pcs | 8 | 16 | Loja Alexandro
|  |  | 7 | Taps / Isolasi | 2 | pcs | 3 | 6 | Loja Alexandro
|  |  | 8 | MCB 25A | 2 | Pcs | 6 | 12 | Loja Alexandro
|  |  | 9 | Metering Panel 63 Ampere (PLN control) | 1 | Pc | 150 | 150 | PLN
|  |  | 10 | 25mm uPVC earth cables | 30 | Pcs | 3.5 | 105 | Loja Alexandro
|  |  | 11 | Installation materials | 1 | Set | 100 | 100 | Loja Vitoria
|  |  | 12 | Black cables | 50 | Meters | 1.5 | 75 | Loja Alexandro
|  |  | 13 | Connectors | 4 | Pcs | 5 | 20 | Loja Alexandro
|  |  | 14 | Stronger ties (Istikador) | 4 | Pcs | 5.5 | 22 | Loja Alexandro
|  |  | 15 | Cable clips 12mm | 7 | Boxes | 3.5 | 24.5 | Loja Alexandro
|  |  | F | PLUMBING MATERIALS / MATERIAL BE-MOS |  |  |  | 187.5
|  |  | 1 | 20mm or 1/2 long pipe | 12 | pcs | 4 | 48 | Loja Alexandro
|  |  | 2 | 40mm or 1.1/4 long pipe | 12 | pcs | 4.5 | 54 | Loja Alexandro
|  |  | 3 | 40mm or 1.1/4 (L) pipe | 6 | pcs | 2.5 | 15 | Loja Minuvarto
|  |  | 4 | 40mm or 1.1/4 (T) pipe | 5 | pcs | 2.5 | 12.5 | Loja Minuvarto
|  |  | 9 | Tape / Lem Pipa | 2 | pcs | 5 | 10 | Loja Minuvarto
|  |  | 10 | Junction 20mm / Sambungan | 8 | pcs | 0.5 | 4 | Loja Minuvarto
|  |  | 11 | Junction 40mm / Sambungan | 12 | pcs | 2.5 | 30 | Loja Minuvarto
|  |  | 13 | Water Crams / Kram air | 4 | pcs | 3.5 | 14 | Loja Minuvarto
2 | Library Materials | 4928.45 |  | LIBRARY MATERIALS |  |  |  | 4928.45
|  |  | 1 | Books for children and youth |  | Ls |  | 1475
|  |  | 2 | Computers |  | Ls |  | 1475
|  |  | 3 | ICT Equipment |  | Ls |  | 478.45
|  |  | 4 | Chairs |  | Ls |  | 500
|  |  | 5 | Book's cases |  | Ls |  | 500
|  |  | 6 | Desks |  | Ls |  | 500
3 | Labor costs for construction | 2976 | 2.1. | Construction Supervisor ($12/day *40days * 1 person) | 40 | Days | 12 | 480
|  |  | 2.2. | Civil Engineer ($12/day * 40 days * 1 person) | 40 | Days | 12 | 480
|  |  | 2.3. | Laborer / Badaen ($10/day * 40 days * 2 persons) | 40 | Days | 10 | 800
|  |  | 2.4. | Assistants ($7/day * 40 days * 4 persons) | 40 | Days | 7 | 1120
|  |  | 2.5 | Electrician ($12/day * 6 days * 1 person) | 6 | Days | 12 | 72
|  |  | 2.6 | Plumbing Installations ($12/day * 2 days * 1 person) | 2 | Days | 12 | 24
| TOTAL (decimal point omitted) | 30000 |  | -