## En version
ESTIMATED BUDGET FOR THE PROJECT OF "HEALTH CARE FOR 3,000 LOW-INCOME WORKERS IN VIETNAM" - PHASE 2 (2018)
Enhance knowledge and skills in reproductive-sexual health, practice of proper nutrition and raising children for reproductive age women in Thang Long Industrial Park, Dong Anh District, Hanoi
No. | Activities | Cost (USD) |  | Notes
|  | Direct cost | Reciprocation of partners/sponsors from businesses
1 | Activity 1: Organized 03 training courses with 3 topics for Trade Union officials and health workers of enterprises in Thang Long Industrial Zone. Provision: 1 day/session. Particitpants: 50 (including 40 workers and 10 others from Thang Long Industrial Zone's Trade Union, For Vietnamese Stature Foundation and some international organizations). Expected time of deployment: March 2018. | 4290
2 | Activity 2: Establishing an online forum for employees to share and exchange information and advice from reputable experts. Estimated time: April 2018 | 660
3 | Activity 3: Organizing 25 communications sessions with different themes on a) "proper nutrition for female workers during pregnancy and infant raising period, and their children" b) "mental health care for female workers who are pregnant and nursing children"; and c) "reproductive and sexual health for women of reproductive age" for 3,000 workers. Estimated time: From May to October, 2018 | 11650 | 10265 | A dairy company will provide free fresh milk for workers drinking during communication sessions
4 | Activity 4: Compiling 3,000 leaflets providing information on reproductive - sexual health, mental health care and proper nutritional practice for women in reproductive age. Expected time: June 2018 | 665
5 | Activity 5: Organize a two-days reproductive-sexual health check-up for about 800 female workers (during the examination will provide contraceptive solutions to those in need). Expected time: June 2018 | 1950 | 500 | Companies that have workers participating in reproductive/sexual health check-up will pay for some medical supplies during the examination
6 | Activity 6: Organize a writing, drawing and photography contest on the theme "Family monents". Expected time: June 2018 | 200 | 665 | A company will sponsor gifts for the contest
7 | Activity 7: Organize "Nutrition Day" and exhibition on the theme "Family moments". Expected time: June 2018 | 9850
8 | Activity 8: Organize a workshop to summarize the project to share results and lessons learned for those interested, especially business leaders, Trade Union leaders at all levels, government agencies, national and international development organizations, researchers and journalists. Estimated time: December 2018 | 760
| Total cost | 30025 | 11430
41455
| The total cost need to be raised from Global Giving | 30025