Program strategy 2016-2018

| - Africhild Initiative(ACI) Program Strategic objective: All Children in the program to lead a dignified life,where the community will take a leading role in their care, support and protection. |  |
| --- | --- |
| Strategies | Activities |
| - Enhance community child protection mechanisms | - sensitization meetings with community, local administration and religious leaders |
|  | - Mobilize communities to form child protection committees at sub location Level and, formation of inter-denominational forum. |
|  | - set up help desk services for child abuse cases |
| - Promote care and support to orphans and vulnerable children. | - refresher training for child home monitors to enhance their skills on PSS to children |
|  | - facilitate PSS services at house hold level by Community Home Monitors |
|  | - identify and support needy children with scholastic materials (uniforms, books, pens, geometric sets) |
|  | - identify and support needy girls with dignity kits (soap, sanitary pads) |
|  | - Train mothers and careers on nutritional needs of children, lactating and expectant mothers |
|  | - Identify and provide nutritional supplements to malnourished children and expectant women. |
| - Improve learning environment at Community Early Childhood Development, and Education (ECDE)centers | - Create Child friendly learning spaces in 9 community ECDE centers - Support the centers with teaching and learning materials - Promote out door learning and gaming in identified centers, - Establish one model digital learning and gaming center at Buongo Community ECDE center. |
| - Environment and Climate change Strategic objective: to promote environmental conservation activities and enhance community capacity for climate change mitigation and adaptation. |  |
| strategies | Activities |
| - mobilize communities to plant trees in public areas and on farms | - Train 9farmer groups on tree nursery establishments and management. |
|  | - support planting of 15,000 indigenous treesalong riparian of River nzoia, sio and hill tops within Busia and Bungoma counties |
|  | - Promote tree planting in schools through tree per child project targeting 9 schools to plant 2,700 trees |
|  | - support planting of 5,000 agro forestry trees on farms |
| - Enhance community resilience to effects of climate change | - Conduct 8 community awareness workshops on climate change |
|  | - promote use of energy saving cooking devices (jikos, fireless cookers, briquettes) in 500 Households |
|  | - promote use of clean energy ( solar devices for lighting) in 500 households |
|  | - Support 4 youth groups with fireless brick making machines. |
| - Food security and livelihood Strategic objective: To improve food security and livelihood support systems at household level |  |
| - Build capacity of target households to enable them produce enough food | - Train 500 households on innovative farming techniques (organic farming, floating gardens etc) |
|  | - support 500 needy households with simple farm tools and planting materials |
| - Improve household income for target communities | - train 500 households on basic entrepreneurial skills |
|  | - organize the trained household members in common interest groups (CIGs) for village saving and loaning scheme (VSL) |
|  | - Support 120 needy older ovc to undergo short vocational training and support them with basic business start up kits. |