WOMEN ECONOMIC EMPOWERMENT FOR JUSTICE

Executive summary

Umoja wa wawezeshaji KIOO is a voluntary non-political, non-religious, and non-profit sharing organization registered under the Societies Ordinance of 1954 with certificate of registration number SO. 12793. KIOO is envisioning in having a Tanzanian society where every individual is free from poverty, injustice and lives indignity.

The objectives to which our organization is established are to raise awareness on HIV/AIDS, malaria and other pandemic disease; to promote and defend women rights; to raise public awareness on the hazards of drug abuse and life skills; to develop and support programs that create awareness and induce people to develop the culture of self-employment as means of eradicating poverty; to raise awareness on human rights; good governance and accountability and provision of entrepreneurship and vocational training to mitigate the situation.

The main goal of this project is to ensure that Rural women marginalized by abuse of rights, absolute poverty and inequality from seven districts of Kigoma region in Tanzania are empowered to access their social economic rights and resources.

Different researches conducted by KIOO shows that poverty and gender inequality are inextricably linked. Unequal access and control over resources and services, and social discrimination which keeps this in place, present serious obstacles to women aiming to address their social and economic  deprivation.  Women, and more specifically widows, in Kigoma region are unable to claim inheritance of property or assets and resources which they have jointly acquired with their spouses.

Through our experience of helping marginalized people in Kigoma region especially women and children, KIOO discovered that most of women who come for legal counseling have a very poor economic situation. The situation renders it more difficult for them to access justice. Many women are coming from remote areas where they need transport to go to court. Their poor economic situation forces poor women to concentrate on struggling for what to feed their families.

The proposed project will solve the problem by forming women group for easy and sounding information sharing, community women's right  awareness meetings, social inclusion and capital mobilization trainings, financial and business management training, capacity building training on different laws that governing women rights in Tanzania, marketing training and provision of apprenticeship tools and women economic empowerment including education on entrepreneurship.

On a daily basis, project team is in the community will conduct follow-up meetings with the women groups and legal training with local leaders. They will work closely with women until the group has become successful enough to apply for regular micro-loans.

PROJECT GOAL

Rural women marginalized by abuse of rights, absolute poverty and inequality from seven districts of Kigoma region in Tanzania empowered to access their social economic rights and resources by 2020.

# Outcomes

Rural women marginalized by abuse of rights, absolute poverty and inequality from seven districts of Kigoma region in Tanzania empowered to access their social economic rights and resources by 2020.

## OUTCOME 1

Vulnerable women obtain increased, secure and sustainable sources of income through enterprise with which they can support their families and have equal access to, and control of, household resources.

## OUTCOME 2

Legal, paralegal and socio-economic services and support appropriate to the needs of vulnerable women to address rights abuse are available and in use.

## OUTCOME 3

Reduced vulnerability of 2,100 rural women as a result of their participation in peer support groups of vulnerable women with similar problems and interests

## OUTCOME 4

Increased community awareness of inequality and women’s rights will result to positive behavioral change that will enable women's participation in social and economic activities

# STRATEGIES

- Program orientation

- Group formation

- Community mobilization meetings

- Social inclusion training & Group constitution development

- Fund mobilization& Management

- Group leadership and management training

- Financial management training to group members

- Business Management training

- Marketing training

- Skills Training

- Business counseling

- Provision of loan and apprenticeship tools

| Cost item | Quantity and description of units | Unit cost | Total cost US$ |
| --- | --- | --- | --- |
|  | No. of units | Description |  |  |
| 1. Identify, train and orient enumerators to undertake baseline surveys, developing baseline questionnaire and report writing |  |  |  |  |
| 1.1 Training package for 30 days to enumerators and 4 KIOO staffs | 50 | People | 15 | $ 750.00 |
| 1.2 Baseline survey and program orientation |  |  |  |  |
| 1.2.1 Accommodation for 50 enumerators | 200 | People | 20 | $ 4,000.00 |
| 2.4.2 Hiring transport for enumerators for | 20 | Days | 100 | $ 2,000.00 |
| Training and baseline subtotal |  |  |  | $ 6,750.00 |
| 2.Community mobilization meetings and group formation |  |  |  |  |
| 2.1 Allowances to 4 KIOO officials | 2100 | People | 20 | $ 42,000.00 |
| 2.2. Fuel for KIOO vehicle during launching meeting | 480 | Liters | 1.045455 | $ 501.82 |
| 2.3 Public Addressing systems | 30 | Days | 25 | $ 750.00 |
| Mobilization subtotal |  |  |  | $ 43,251.82 |
| 3. Social inclusion training & Group constitution development |  |  |  |  |
| 3.1 Transport allowances to participants 1200 | 1200 | People | 20 | $ 24,000.00 |
| 3.2 Venue hiring | 8 | Venue | 40 | $ 320.00 |
| 3.3. Fuel for KIOO vehicle during training | 360 | Liters | 1.045455 | $ 376.36 |
| 3.4. Facilitators allowances | 16 | People | 50 | $ 800.00 |
| 3.5 Breakfast and lunch to 1200 participant | 1200 | People | 8 | $ 9,600.00 |
| Social inclusion Subtotal |  |  |  | $ 35,096.36 |
| 4.Group leadership and management training |  |  |  |  |
| 4.1 Transport allowances to 1200 participants | 1200 | People | 20 | $ 24,000.00 |
| 4.2 Venue hiring | 4 | Venue | 40 | $ 160.00 |
| 4.3. Fuel for KIOO vehicle during training | 360 | Liters | 1.045455 | $ 376.36 |
| 4.4. Facilitators allowances | 8 | People | 50 | $ 400.00 |
| 4.5 Breakfast and lunch to 1200 | 1200 | People | 8 | $ 9,600.00 |
| Leadership subtotal |  |  |  | $ 34,536.36 |
| 5. Financial management training to group members |  |  |  |  |
| 5.1 Transport allowances to 1200 participants | 1200 | People | 20 | $ 24,000.00 |
| 5.2 Venue hiring | 4 | Venue | 40 | $ 160.00 |
| 5.3. Fuel for KIOO vehicle during training | 360 | Liters | 1.045455 | $ 376.36 |
| 4.4. Facilitators allowances | 8 | People | 50 | $ 400.00 |
| 5.5 Breakfast and lunch to 1200 participants | 1200 | People | 8 | $ 9,600.00 |
| Financial Management, subtotal |  |  |  | $ 34,536.36 |
| 6. Business Management training and marketing training |  |  |  |  |
| 6.1 Transport allowances to participants | 1200 | People | 20 | $ 24,000.00 |
| 6.2 Venue hiring | 4 | Venue | 40 | $ 160.00 |
| 6.3. Fuel for KIOO vehicle during training | 360 | Liters | 1.045455 | $ 376.36 |
| 6.4. Facilitators allowances | 8 | People | 50 | $ 400.00 |
| 6.5 Breakfast and lunch to 1200 | 1200 | People | 8 | $ 9,600.00 |
| Business Management, subtotal |  |  |  | $ 34,536.36 |
| 7. Skills Training and business counseling |  |  |  |  |
| 7.1 Transport allowances to participants | 1200 | People | 20 | $ 24,000.00 |
| 7.2 Venue hiring for one day | 4 | Venue | 40 | $ 160.00 |
| 7.3. Fuel for KIOO vehicle during training 360 liters | 360 | Liters | 1.045455 | $ 376.36 |
| 7.4. Facilitators allowances | 8 | People | 50 | $ 400.00 |
| 7.5 Breakfast and lunch to 1200 participant x 5days | 1200 | People | 8 | $ 9,600.00 |
| Other costs, subtotal |  |  |  | $ 34,536.36 |
| 8. Monitoring, evaluation and information |  |  |  |  |
| Personnel costs and external services |  |  |  |  |
| Accommodation to 2 KIOO staffs during monitoring and evaluation for 120days | 120 | Days | 15.4 | $ 1,848.00 |
| Accommodation |  |  |  | $ 1,848.00 |
| Fuel for KIOO vehicle during roundtable meeting 120 liters | 540 | Liters | 1.045455 | $ 564.55 |
| Travel , subtotal |  |  |  | $ 564.55 |
| Other costs |  |  |  |  |
| Printing and photocopying of training materials | 5000 | pages | 0.12 | $ 600.00 |
| Administration costs | 12 | Months | 611.98 | $ 7,343.76 |
| Report writing and dissemination | 500 | Copies | 0.8 | $ 400.00 |
| Other costs, subtotal |  |  |  | $ 8,343.76 |
| Monitoring, evaluation and information, subtotal |  |  |  | $ 10,756.31 |
| Total implementation costs |  |  |  | $ 233,999.94 |