## Implementation of the project
Project implementation file
II. ACTIVITIES CARRIED OUT DURING THE MONTH
1 | Cultural work in the communal and family nursery gardens.
2 | Motivation in the care of plantations in communal and family fields.
3 | Audiovisual training course in the communities of the district of Pichigua.
4 | Inicio de viviendas saludables en las once unidades de atención y organización de las comunidades para el primer concurso.
5 | District-level meeting on chlorite ipo management training under coordination with the ATM office and Espinar health post
6 | Motivation in the breeding of guinea pigs, the construction of their sheds has already begun.
7 | Elaboration of improved stoves, cupboards, refrigerators and ovens in the 11 units.
8 | Meeting of juries and community presidents to discuss the key points of the contests.
9 | Participation in the community fairs in the communities of Chimpa Alccasana and Sillota.
IV. CONTRIBUTION OF THE MUNICIPALITY OF PICHIGUA
| Details |  | Quantity | Unit cost | Municipal contribution
1 | Forest expert |  | 1 | 1500 | 1500
2 | 90 octane gasoline fuel |  | 4 | 14 | 56
3 | Motorcycle and oil for motorcycle |  | 1 | 60 | 60
5 | Support staff |  | 1 | 1300 | 1300
| TOTAL |  |  |  | 2916
V. INTERINSTITUTIONAL RELATIONS
| Institución | Actividad
1 | M.D.PICHIGUA | Coordination of the protection of communal nurseries.
2 | Social management | Bio-gardens ¦ cookers
3 | Subprefecture | Support in community meetings on afforestation issues.
4 | ATM | Fairs and trainings with JASS committees
6 | Camelids Project | Implementation of records in camelid breeding.
7 | CFC | Forestation
VI. DIFFICULTIES
1 | Some juries show little interest in motivating the participants in their community.
2 | Rain affects communal nursery gardens with stagnant water.
3 | The lack of personnel in the communal nursery gardens to perform the work of recalse and weeding.
4 | Lack of contribution by the municipality of Pichigua to carry out activities.
VII. SOLUTIONS FOUND
1 | Audiovisual training to motivate families in the 11 care units.
2 | Planning team work in community nursery gardens.
VII. PERSONAL
| Nombre |  | Actividad
Pachamama | Benito Pucho |  | Coordinator
| Humberto Rodrigues |  | Communities in charge: chimpa alccasana, chani pichigua, moro alccasana.
| Walter Uscapi |  | Communities in charge: alccasana, ccahuya baja,nueva esperanza y sillota
Elias Becerra
Municipalidad | Semion Huaman |  | Forest nurseryman
VIII. ACTIVITIES FOR THE NEXT MONTH
What activities will be carried out next month?
1 | Audiovisual training in different topics in the communities of the Pichigua district.
2 | Give greater emphasis to the work of family and other community contests.
3 | Construction follow-up of guinea pig sheds in the communities.
4 | Participation in the national fair of pichigua.
5 | Technical assistance in the communities of the Pichigua district.
6 | Communally roofing of forest nursery gardens.
7 | Protection of communal and family forest plantations.

## Innovations
Innovation Adoption Card
Date: | 2018-04-30
No. of contest: | FIRST
District: | PICHIGUA
Coordinator: | BENITO PUCHO CHULLO
Communities | No. Communal Padron Families | Familias que no residen en la comunidad | Target families | How many families are registered for the contest? | How many families participate in the project? | Percentages according to the goal (do not write in this column)
chimpa alccasana | 210 | 110 | 100 | 62 | 60 | 60%
sillota | 30 | 3 | 30 | 24 | 27 | 90%
chani pichigua | 100 | 20 | 80 | 30 | 33 | 41.25%
moro alccasana | 120 | 30 | 90 | 53 | 56 | 62.22%
ccahuaya baja | 135 | 10 | 80 | 83 | 75 | 93.75%
nueva esperanza | 42 | 4 | 40 | 22 | 20 | 50%
alccasana | 240 | 120 | 100 | 133 | 95 | 95%
TOTAL | 877 | 297 | 520 | 407 | 366 | 70.38%
II- HEALTH AND HOUSING
A. Nutrition |  |  |  |  | B. Healthy homes
Communities | Target families | Families with a vegetable garden greater than 3 varieties of vegetables |  |  | Families with improved facade | Families with improved kitchen | Families with separate bedroom | Families that dispose of their waste in landfills
chimpa alccasa | 100 | 13 |  |  | 28 | 14 | 54 | 28
sillota | 27 | 9 |  |  | 7 | 3 | 8 | 13
chani pichigua | 80 | 6 |  |  | 11 | 14 | 26 | 24
moro alccasana | 90 | 23 |  |  | 39 | 25 | 28 | 51
ccahuaya baja | 80 | 33 |  |  | 29 | 15 | 65 | 30
nueva esperanza | 39 | 5 |  |  | 8 | 7 | 8 | 6
alccasana | 100 | 15 |  |  | 22 | 28 | 68 | 28
TOTAL | 516 | 104 |  |  | 144 | 106 | 257 | 180
III- AGRICULTURAL PRACTICES AND FORESTATION
Communities | Target families | Families with orderly shepherding | Families with cultivated pastures and irrigation for their animals
chimpa alccasa | 100 | 25 | 15
sillota | 27 | 11 | 8
chani pichigua | 80 | 25 | 12
moro alccasana | 90 | 35 | 10
ccahuaya baja | 80 | 56 | 25
nueva esperanza | 39 | 12 | 5
alccasana | 100 | 42 | 96
TOTAL | 516 | 206 | 171
IV- GENERATE A BUSINESS
|  |  |  | Guinea pigs |  |  | Sheeps |  | Dairy cattle |  | Llamas | Crafts
| Target families | Families with businesses | Families with production and sales records | Families with more than 30 guinea pigs | Families with more than 100 guinea pigs | Families that have sheds for guinea pigs | Families with more than 150 sheep | Families with shed for sheep | Families with dairy cow businesses | Families that have converted for their cows
100
27
80
90
80
39
100
| 516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0% | 0% | 0% | [7 empty] | 0%
IV- SELF-ESTEEM, IDENTITY AND COEXISTENCE
Target families | Families with future plans painted | Families with dreams and clear goals for their future | Families that participate actively in the communal agreements | Families in charge of the elderly | Families with disabled dependents
100
27
80
90
80
39
100
516 | 0 | 0 | 0 | 0 | 0
Note on A45: We still need to update this section with data from coordinators
Note on A59: It will be updated at the end of July and will be presented with the baseline so that the impact obtained can be observed.
Note on C9: Son familias que tienen sus casas o terrenos en la comunidad pero no residen ahí
Note on D9: Familias que viven en comunidad
Note on G17: 70% of the families of the district of Pichigua participate in the Project

## Forestation
Plants in nursery gardens - Campaign 2018 Pichigua
Community | Species | Goal | Current production of nursery garden 2018 | Production of family nursery gardens | Total
chañi pichigua | Pine Patula | 5000
| Radiata Pine | 45000 | 49180 | 1050 | 50230
| Native | 2000 | 1050 |  | 1050
moro alccasana | Pine Patula | 3000
| Radiata Pine | 45000 | 38500 | 21000 | 59500
| Native | 2000 | 1000 |  | 1000
ccahuaya baja | Pine Patula | 3000
| Radiata Pine | 40000 | 34500 | 3000 | 37500
| Native | 2000
vivero central | Pine Patula | 20000
| Radiata Pine | 280000 | 40220 |  | 40220
Native
chimpa alcasana | Pine Patula
| Radiata Pine |  |  | 6500 | 6500
Eucalyptus
alccasana | Radiata Pine | 15000 |  | 8000 | 8000
Pine Patula
nueva esperanza | Radiata Pine | 3000 |  | 1200 | 1200
Pine Patula
sillota | Radiata Pine | 4000 |  | 2000 | 2000
Total |  | 469000 | 164450 | 42750 | 207200

## Happiness for Everyone
"HAPPINESS FOR ALL" PROJECT
N° | NAMES AND SURNAMES | COMMUNITY | ITEMS WHERE THEY PARTICIPATE
1 | MELITON CLEMENTE RODRIGUEZ | CCAHUAYA | EMBROIDERY
2 | NICASIO CHOQUEMAQUE | CCAHUAYA | CRAFTS
3 | ISAAC PFOCCO CHICCA | CCAHUAYA | STORIES AND LEGENDS
4 | VALENTIN TARIFA FERATA | N. ESPERANZA | STORIES AND LEGENDS
5 | DANIEL JORDAN CACERES | SILLOTA | STORY OF THE VIRGIN SELLOTA
6 | FRANCISCA MAMANI SUCA | ALCCASANA | TISSUE TO STICKS
Note on A1: BOOST THE QUALITY OF LIFE OF THE ELDERLY AND DISABLED