Action Plan

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| NO | Activity | Responsible Person | Time frame | Means of verification |
| 1 | Conducting Baseline Survey and publicize issues to District Members and other stakeholders | Director  Accountant  M&E officer | 10th- 15th June 2018 | Survey reports  questionnaires |
| 2 | To conduct an advocacy meeting and train with 0 stakeholders and the 10 Traditional healers on the effects of FGM onto women | Director  Accountant  M&E officer | 20th June 2018 | Training reports  Payment voucher  Photo, attendance list |
| 3 | Select and training 30 community based surveillance Volunteers for 3days to conduct education of the effects of FGM on women | Director  Accountant  M&E officer | July 2018 | Training reports  Payment voucher  Photo, attendance list |
| 4 | Conduct community education on the effects of FGM on women through one-on-one, small groups, house to house focus group meetings | Director  Accountant  M&E officer | June 30, 2018- February 2020 | Data collection, photos, payment vouchers |
| 5 | Conduct 15 community sensitization durbar/drama on the rights of women | Director  Accountant  M&E officer | June 30, 2018- February 2020 | Durbar reports, photo, payment vouchers |
| 6 | Conduct monthly monitoring and supervision visit to support the work of the Volunteers | Accountant  M&E officer | Monthly | Reports photos payment vouchers |