## Feuil1
| PROJECT SUMMARY | INDICATORS | MEANS OF VERIFICATION | RISKS / ASSUMPTIONS
Goal | Internally Displaced Persons and Children found in Tole reduce their vulnerability and are more able to generate income, access basic healthcare and feed themselves. | household consumption, survival strategies identified, self-reported well-being, access to services | evaluation report, participant's testimonies, databases | Tole remains safe and relatively untouched by the crisis
Outcomes | A clear picture of the scope of the crisis within Tole, Buea informs further actions. | number of projects informed by data collected | project reports | community collaboration
| Impact of the program is captured and can be used to learn and mobilize more support | number of projects informed by outcome data | project reports | participant's collaboration
| Participants vulnerability reduces | household consumption, survival strategies identified, self-reported well-being, access to services | evaluation report, participant's testimonies | participants are protected from further economic shocks
Outputs | Internally Displaced Persons of Tole are identified, with vulnerability scores and tracking and updating mechanisms in place | exact number of IDP living in Tole community is determined and basic vulnerability scores are assigned | database of IDPs in Tole | updating mechanisms can be sustained
| 20 beneficiary households and Reach Out staff keep track of household consumption and income | Rich and truthful data on participants' consumption and productive assets is obtained | database | Risk: Household mobility
| 20 Participant households increase their purchasing power by 70,000 fr | household consumption increases, productive assets increase in size | monitoring visits, participants books | Participants are safe and able to use their grant on household expenditures and productive assets
Activities | Identification Meetings | number of IDPs identified | IDPs list | IDP community is receptive and not afraid
| Community Identification | number of IDPs identified | IDPs list | IDP leaders are willing to volunteer
| Participatory Targeting with IDPs and community | 20 Selected families | beneficiaries' list | IDP and Host community is receptive, fair and able to deflect conflict
| Training of 20 prospective beneficiaries on basic bookkeeping | number of beneficiaries trained | attendance sheets, training reports, pictures | Participant households are able and willing to practice bookkeeping
| Monitoring of household expenditure and productive activities | number of monitoring sessions and attendance | attendance records, consumption records, reports | Participants have stable locations and / or inform project team when moving. Participants are willing to come to follow-up meetings
| Disbursement of support grants of 70,000 per family | number of grants given | disbursement sheets, contracts | Security