## THE LITERACY GARDEN
THE LITERACY GARDEN PROJECT 2018
| INCOME | TYPE | AMOUNT USD | DATE
| Global Giving Org | GRANT | 1100 | FEBRUARY
| Ali Osborne, Volunteer, Canada | DONATION | 1000 | APRIL
| Tenteleni Org UK | GRANT | 3000 | JUNE
| Gates of Hope Org USA | GRANT | 5000 | JULY
| Kendra Nicolai , Volunteer, USA | DONATION | 1750 | JULY
| TOTAL |  | 11850
EXPENDITURE
Global Giving Org
| Item/Description | Quantity | Unit Cost Kes | Total Cost Kes | TOTAL COST USD | STATUS
Building Blocks and Fencing of literacy Garden
| Rolls of chain link for fencing | 25 rolls | 2400 | 60000 | 600 | COMPLETED
| Building blocks for construction of mini library | 500pcs | 65 | 32500 | 325
| Labor for fencing |  |  | 7000 | 70
| Transport |  |  | 2500 | 25
|  | Sub Total |  | 102000 | 1020
Ali Osborne, Volunteer, Canada
| Item/Description | Quantity | Unit Cost Kes | Total Cost Kes | USD
General Preparations and Excavation of Roller skating paths
| Labor for clearing rocks and ground leveling | 10 days | 2000 | 20000 | 200 | COMPLETED
| Labor to spatial Planner to provide architectural plan for roller skating paths | 1 | 25000 | 25000 | 250
| Labor for digging holes to plant trees | 1 | 5000 | 5000 | 50
| Labor for excavations of rollerskating paths | 3 men | 8000 | 24000 | 240
| Installation of Gate | 1pc | 25000 | 25000 | 250
| Slashers | 2pcs | 450 | 900 | 9
|  |  | Sub Total | 99900 | 999
Kendra Nicolai , Volunteer, USA
| Item/Description | Quantity | Unit Cost Kes | Total Cost Kes | USD
General Preparations and Excavation of Roller skating paths
| Kindles | 5pcs | 10000 | 50000 | 500
| Ipads | 5pcs | 25000 | 125000 | 1250 | COMPLETED
|  |  | Sub Total | 175000 | 1750
| Tenteleni Org UK, Grant | EXCHANGE RATE: KES 140= 1 GBP
No. | Item/Description | Quantity | Unit Cost Kes | Total Cost Kes | TOTAL COST GBP
1 | Construction Of Mini Library Room for storing of books and availing to readers
| Ballast 1” | 10 tonnes | 800 | 8000 | 57.1429 | IN PROGRESS
| Sand | 7 tonnes | 1000 | 7000 | 50
| Cement | 50 bags | 750 | 37500 | 267.8571
| Water for construction | 3 units | 3000 | 9000 | 64.2857
| Labor for construction | 1 unit | 30000 | 30000 | 214.2857
| Deformed bars – D12 | 45pcs | 1000 | 45000 | 321.4286
| Deformed bars D8 | 25pcs | 500 | 12500 | 89.2857
|  | Sub Total |  | 149000 | 1064.2857
2 | Writing and Storytelling
| Adventure story books by local authors | 300PCS | 350 | 105000 | 750 | TO BE DONE FIRST WEEK OF AUGUST
| Picture books to introduce storytelling | 50pcs | 400 | 20000 | 142.8571
| Costumes- Animal masks | 20pcs | 300 | 6000 | 42.8571
| Finger/Hand puppets | 10pcs | 500 | 5000 | 35.7143
| Painted wood spoon characters | assorted | 6000 | 6000 | 42.8571
| Pens & pencils | 100pcs | 20 | 2000 | 14.2857
| costumes- African dresses for oral narratives | 50pcs | 800 | 40000 | 285.7143
| Writing pads | 100pcs | 100 | 10000 | 71.4286
| E-Book Creation & publishing workshops – snacks/refreshments | 5 sessions | 4000 | 20000 | 142.8571
| Essay Writing Competition | 3 prizes | 2000 | 6000 | 42.8571
|  |  | Sub Total | 220000 | 1571.4286
|  |  | TOTAL | 369000 | 2635.7143
| Gates of Hope Org USA | EXCHANGE RATE: KES 100= 1 USD
Basketball & Roller Skating Program 2018
| Item/Description | Quantity | Unit Cost Kes | Total Cost Kes | USD
Construction of Basketball Court
| Excavations and ground leveling – 3 workers x 3 days @ Kes 1000 per day | 9 man hours | 1000 | 9000 | 90 | started on 10th July. Expected to be done by 20th August
| Ballast 1” | 10 tonnes | 800 | 8000 | 80
| Ballast 3/4” | 3 lorries | 5000 | 15000 | 150
| Sand | 2 tonnes | 18000 | 36000 | 360
| granite stones for edges | 3 lorries | 3000 | 9000 | 90
| Cement | 70 bags | 750 | 52500 | 525
| Water for construction | 3 units | 3000 | 9000 | 90
| Wire mesh | 30pcs | 750 | 22500 | 225
| Tar | 10 tonnes | 5000 | 50000 | 500
| Allow for transport of Materials |  | 10000 | 10000 | 100
| Allow for marking and painting |  | 10000 | 10000 | 100
| Labor- Masonry |  |  | 70000 | 700
| Side benches | 4pcs | 6000 | 24000 | 240
|  |  | Sub Total | 325000 | 3250
Basketball Board & Rims
| 2” square tubes | 4pcs | 800 | 3200 | 32
| 1” square tubes- roofing | 2pcs | 550 | 1100 | 11
| 6” Round Tube- heavy gauge -stand/base | 2pcs | 6000 | 12000 | 120
| Welding rods | 1 pkt | 1000 | 1000 | 10
| Cutting disc | 2pcs | 200 | 400 | 4
| Grinding disc | 2pcs | 250 | 500 | 5
| Timber 8 x 1 | 120ft | 80 | 9600 | 96
| Transport | 1 | 4000 | 4000 | 40
| Labor welding | 1 | 9000 | 9000 | 90
|  |  | Sub Total | 40800 | 408
Equipment/Supplies
| Basketballs | 4pcs | 4500 | 18000 | 180
| Kid Roller Skating shoes | 20 pairs | 4000 | 80000 | 800
| Helmets | 20pcs | 1700 | 34000 | 340
| Basketball hoop net | 4pcs | 200 | 800 | 8
|  |  | Sub total | 132800 | 1328
|  |  | TOTAL | 498600 | 4986
|  |  |  | TOTAL | 11755