ISMU Work Plan and Budget Summary

A) Executive Summary:

- Support impoverished children with scholarships so they can start or continue with their studies

- Strengthen the organizational capacity and self-management of impoverished communities that work with ISMU

B) Introduction and Background:

- When Guatemala City experienced a rapid population growth, impoverished settlements emerged- now these are the alternative housing for the poor who live in the city

- The inhabitants of the impoverished settlements have developed an effort to make their settlements sustainable and to have basic services like water, electricity, sewage system, access to education

- ISMU focuses its efforts on strengthening community organizations to cope with difficult problems that affect the impoverished areas of Guatemala City

- ISMU supports families through training as a way for them to acquire knowledge and strategies for survival

- ISMU contributes to the development of children, preventive health, education, and respectful relationships between human beings (especially towards women and children)

C) Goals and Objectives:

- Develop ISMU’s work in 7 communities: The municipalities of Chinautla, Guatemala, Palín, San Miguel Petapa, Unión Zacapa, Tejutla, and Cantón Luisiana

- Continue supporting the education of 185 children from different communities who are facing socio-economic problems so they can begin or continue with their studies, up to high school education

- Promote youth development that will contribute to the welfare of the community and family

- Promote scholarship recipients to participate in community service through cultural activities and environment preservation

- Support 120 families from different communities with improved housing

- Strengthen families’ economic capacity through microcredits so they can start or expand a small family business

- Strengthen administrative skills of small businesses

D) Challenges:

- There is an increasing demand for ISMU programs to support other communities, which ISMU cannot respond to due to limited resources

- The strategy to train community handicraft teachers has helped us overcome the challenge of ISMU staff having to develop continual training programs

- In addition, the community handicraft teachers know their communities best and are recognized by their work locally

E) Strategy and Actions:

- Education

- Enroll and give school supplies to 25 scholarship recipients for primary education

- Give guidance to parents and student who have educational challenges or family problems

- Facilitate 40 meetings throughout the year with the 4 scholarship groups (each group has an average of 35 students)- 10 meetings with each group

- Facilitate 30 community visits- this will help establish a connection with the scholarship recipients an learn about their educational and human development

- Grant scholarship funds to 30 students from the Tejutleco Institute

II.	Job Training

- Support 8 handicrafts teachers - who will provide a total of 40 community workshops (5 workshops per teacher) to community groups – with a toolkit on how to set up and carry out a workshop

- Conduct 10 workshops on handicrafts made out of recycled materials and non-recycled materials for 12 new handicraft teachers from different communities

- Organize 9 meetings to coordinate the marketing of handicrafts that are produced at home

- Hold 1 exhibition event for handicrafts made by the communities’ teachers

- Coordinate with 3 institutions to support the selling of handicrafts

- Coordinate with Landivar University to recommend a student to do a supervised internship with ISMU- the intern will monitor the different programs

F) Monitoring and Evaluation:

- Weekly check-in on progress work with each community

- Monthly meetings are carried out with different community groups

- Frequent community visits are done on a weekly basis

- Community tutors have supported ISMU’s education program by following-up with the students who receive scholarships

- Monthly reports are produced internally for ISMU

G) Appendices: Budgets, Annual Plans, etc.

| ISMU Budget |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ITEM | No. BENEF. | ACTIVITY | IN CHARGE | COST/UNIT | USD |
| EDUCATION |  |  |  |  |  |
| General Education Scholarships | 25 | Supplies, tuition | Education Program Coordinator | 20,000 | 2,500 |
| Scholarships for students of Tejutla School | 30 | Transfer | Coordinator | 15,000 | 1,875 |
| Meetings w/ scholarship recipient and parents | 215 | 40 Meeting | Education Program Coordinator | 12,000 | 1,500 |
| Community Visits | 150 | 30 Visits | Education Program Coordinator | 7,500 | 937.5 |
| Education Program Coordinator, Salary 50% |  |  |  | 24,000 | 3,000 |
| Total |  |  |  |  | $9,812.50 |
| Job Training |  |  |  |  |  |
| Community Meetings for planning and information sharing | 150 | 10 Meetings | Field Staff | 1,000 | 125 |
| Meetings with Youth to analyze environmental challenges | 20 | 4 Meetings | Field Staff | 400 | 50 |
| Workshops with Youth on affirmative action to address environmental challenges | 20 | 4 Workshops | Field Staff | 600 | 75 |
| Meetings of handicraft teachers | 10 | 9 Meetings | Field Staff | 2,500 | 312.5 |
| Training by handicraft teachers to community groups | 400 | 5 Workshops | Handicraft teachers | 2,400 | 300 |
| Trainings on materials based out of recycled materials | 12 | 10 Workshops | Second Group of Handicraft Teachers | 4,000 | 500 |
| Materials and office supplies |  |  |  | 5,150 | 643.75 |
| Coordination of Handicrafts Production and Marketing | 15 | 9 Meetings | First Group of Teachers | 900 | 112.5 |
| Handicraft Exhibition | 25 | 1 Exhibition | People | 1000 | 125 |
| Outside Trainers | 5 | Specific Project | Community Technician | 3000 | 375 |
| Total |  |  |  |  | 2,618.75 |
| OVERALL TOTAL: |  |  |  |  | $12,431.25 |
| GlobalGiving Administration @15% |  |  |  |  | $1,865 |
| IDEX Program Evaluation @ 10% |  |  |  |  | $1,243 |
| OVERALL TOTAL: |  |  |  |  | $15,539.25 |
| Exchange Rate: 1USD X 8Q |  |  |  |  |  |