PROJECT FOR

RURAL WOMEN ECONOMIC EMPOWERMENT

| General Information |  |
| --- | --- |
| Name of organization | Centre for Human Resource Development |
| Legal status | Non profit & non governmene organization |
| Postal Address | 01, Walakumbura watta, raitalawela, Ukuwela- Sri Lanka |
| Telephone Number | 94 (0) 71 548 9964 |
| Fax Number | 04 (0) 66 45101 |
| E-mail | hrdvisionjm@gmail.com |
| Contact person 1 | Jayathri Mihirani (Ms) |
| Contact person 2 | Renuka maliyagoda (Mrs) |
| website of the organisation | www.humanresourcedevelopment.org |
| Summary of the Proposed Project |  |
| Title of the Project | Rural Women Economic Development |
| Location | Rural Area of the Matale District |
| Duration of the Project | 12 months |
| Finance requested | 20,000 US$ |
| Objective of the Action | Overall Objective To contribute to sustainable livelihoods for the poor and marginalized in Matale District of the Central Province of Sri Lanka |
| Target groups | Poor and marginalized women |
| Final beneficiaries | - 1000 women and (70% women and 30% youth) benefit from pro-poor value chain development - 130 women benefit from Community Investment Funds (CIF Fund) - 1000 women (70% women and 30% youth receive employable skills Training |
| Project Components | Project Outcome 1 – Increased employment opportunities, market access and incomes for poor and marginalized groups particularly women; and have greater participation Project Outcome 2 – Women have greater participation in and benefit from economic activities |
| Main Activities | Identification and development of selected valued chains on target district; setting up of Community Investment, Trade Identification Funds (CIF) and delivery of Technical and Vocational skills; supporting small scale enterprenures. |

The proposed Project for Women’s Economic Empowerment and Market Development in three villages of Matale District of the Central Province of Sri Lanka will be implemented. The Project seeks sustained improvement in the quality of life of the rural population by strengthening low-income rural markets, stimulating local economic development and diversifying livelihood opportunities, which can also contribute towards the national development goals of inclusive economic growth, and poverty alleviation. Rural economy faces multiple challenges to its growth, which range from the lack of access to financial resources, inadequate managerial and technical skills, little access to market information, high levels of vulnerabilities to disasters and inhibitive regulatory environment. In these circumstances, the Project intends to create economic choices through a combination of efforts to build rural assets and skills for the poor rural women and help them to diversify their income generating activities by stimulating engagement not only in value addition to rural products but also in non-farm production and services that provide additional employment and income opportunities.

Project Introduction:

Matale District consists of 11Divisional Secretary’s Areas and 11 Pradeshiya Sabas (Divisional Councils) spread over an area of 74,521 Km2. It has a population of about 28 million (as per recent estimates), which accounts for 13 percent of Sri Lanka’s total population. 83 percent of the population lives in rural areas of the District. Matale is rich in natural growth drivers such as agriculture, livestock, fisheries, tourism, energy, hydro power, and mines and minerals. Its potential for hydroelectricity generation is estimated to be around 90 MW.  Despite past progress and the proven potential for development of a modern economy, the district’s ability has not been realized, which culminates into stagnant economy and poor human development indicators. Its economic growth, about 4.5 percent between 2005 and 2015, is lower than the national average. This means that per capita income has been increasing by about 1.5% per annum. According to the 2015/16 Household Income and Expenditure Survey, poverty with 37.2 percent of the population living below the poverty line in Matale, is higher than the national average. Rural poverty (41.1 percent) is higher than the urban poverty (28.1 percent) in the District. The poverty rate amongst women is higher in Matale than in other Districts. The Household Income and Expenditure Survey, Sri Lanka Demographic and Health Survey and Sri Lanka Social and Living Standards Measurement Survey suggest different data on income distribution in the district. Although, there is absence of reliable date, it reflects a more important fact and that is, the complex forces influencing the nature of poverty, associated with land ownership, economic trends, social conventions and natural resources in the district.

Matale District has a growing labour force with a high unemployment rate of above 10 percent. This is mostly because people have limited access to education and training opportunities. Employment rates for women are low and their representation in government and senior decision-making positions is very limited. Most women are subject to economic dependence and their traditional roles have changed little in the last decades.

The large majority of the population earns its livelihoods from farming or retailing activity, both of which are carried out on a small scale and generate low incomes. The Household Income and Expenditure Survey (2015/06) data shows the composition of employment in Matale District; 36 percent agriculture and fisheries, 30 percent services, shops and market sales, 3.5 percent professionals, and 3.3 percent technicians and associate.

Professionals. Agriculture contributes 21 percent to provincial GDP. About 75 percent of the population is, at least, dependent on agriculture, and this includes many of the poorest households. Crops account for about 70 percent of the value of agricultural production and livestock for about 30 percent. However, agricultural growth is constrained by fragile natural resources, fragmentation of land holdings, underfunded research and extension, and limited availability of financial services; all of which contribute to low levels of productivity.

Its literacy rate is 74 percent and completion rate is only 26 percent, which are lower than the national averages. The lack of adequate and appropriate education and training opportunities for its increasing youth population is yet another challenge for the district. As evident from the case of Swat crisis, the inability to provide youth with productive activities can lead to their engagement in militancy. Likewise, its health indicators are also low. The poor have few social safety nets to secure quality health services. Only 47 percent of the households have tap water and 61 percent have safe sanitation leading to a high prevalence of water-borne diseases.

Project Design:

The Overall Objectives ‘To contribute to sustainable livelihoods for the poor and women in Matale districts of the Central Province’.

The Project Outcomes and Outputs are grouped into three broader components as given below;

Project Outcome1:

Increased employment opportunities, market access and incomes for poor and marginalized groups, particularly women.

Output 1.1: Improved value chains to facilitate access of poor and women to viable markets with appropriate products and services,

Output 1.2: Improved value of labour by the poor

Project Outcome 2:

Women have greater participation in and benefit from economic activities

Output 2.1: Increased access of women to financial services and income generating activities

Output 2.2: Improved literacy and functional skills, and leadership opportunities for women

2.2) PROJECT OUTCOME 1: VALUE CHAINS AND MARKET ACCESS

Improved value chains to facilitate access of poor and women to viable markets with appropriate products and services

It is well known that poverty is multi-faceted and that raising incomes and increasing assets alone are often not adequate to sustainably reduce poverty. It is therefore, important to leverage markets to improve the economic wellbeing of the very poor as an essential facet of graduating people out of poverty. Although, labour and time intensive, the informal economic activities face multiple challenges to growth; i) low levels of skills and knowledge of modern technologies; ii) lack of access to financial assistance; iii) inaccessibility to services for quality inputs; iv) little access to information about market demands and trends; v) increased exploitation by middle men who decide business terms and siphon off the profits; vi) high levels of vulnerabilities to disasters and crisis; (vii) absence of organised collective efforts to meet market requirements; viii) low productivity; and ix) an inhibitive regulatory environment.

courses and capacity building initiatives can then be modified to include findings of the assessment. Following technical capacity building the evaluation suggests that the focus should be on establishing access and linkages with the market for the trained beneficiaries for improved economic gains. This will allow for the creation of marketable products (and individuals, based on their skillset), which will be more likely to generate improved incomes.Based on the experience and lessons learned around the economic component of Phase 1, the second phase intends to strengthen livelihoods of the poor and vulnerable groups, particularly women, by focusing on value chains and market linkages.

Description of Activities:

Increased employment opportunities, market access and incomes for poor and marginalised women

This outcome will achieve its objective through two outputs; i) improved value chains and market linkages for increased incomes of poor women; and ii) improved technical/vocational skills enhancing employment opportunities for poor community members.

Output 1.1: Improved value chains and market linkages for increased incomes of the poor

This output will identify important sub-sectors in the district and map their value chains. Based on this, the nature and scope of interventions will be defined for each selected sub-sector. The development of value chains will look at the complex range of activities implemented by various actors, such as primary producers, processors, traders, Business Development Providers Services. It will not only consider activities implemented by a single enterprise but move along all its backward and forward linkages with other enterprises engaged in trading, processing, assembling etc., to maximise the generation of value along the chain, and thus, promote and upscale small-scale microenterprises. These enterprises can become important source of primary or supplementary income for the rural poor.

Broadly speaking, the value chains will assist the target clients in three important ways. One, it will facilitate technical capacity building to improve production processes and, hence, the quantity and quality of the product. Two, it will facilitate the access of the poor and marginalised womento smart subsidies, financial services and private sector that can provide incentives for entrepreneurship and investment, increase productivity, improve access to markets, and reduce risk and vulnerability. Three, it will increase the commercial linkages between the businesses that the poor own and work in, and businesses that can offer them new and more profitable opportunities as suppliers or consumers.

Important areas can be, but are not limited to, (i) On-farm Agriculture, such as, fruit and vegetable production, off-season floriculture for example, Corn production and marketing, Nursery Promotion; (ii) Non-Timber Forest Production, that is, aromatic plants, and mushroom production; (iii) and (v) Off-Farm Production and Services such as, word decorative,  marble mosaics, leather goods, and hospitality etc.

Description of Activities

| No. | Indicative Activities | Planned Activities (indicative) |
| --- | --- | --- |
| 1.1.1 | Conduct Market Research to identify opportunities and constraints of selected sub-sector Value Chains | Market survey in Matale district |
| 1.1.2 | Prepare and deliver training to identified target women on modern techniques | 975 men and women trained |
| 1.1.3 | Facilitate market linkages for strengthening weak links in the selected value chains | 975 men and women benefit from strengthened market linkages |
| 1.1.4 | Extend smart subsidies to stimulate economic growth, especially, for the low-income target women | 975 men and women receive smart subsidies |
| 1.1.5 | Organise ‘Show and Tell’ events to showcase best practices of target women | 3 events organised |
| 1.1.6 | Conduct learning visits for the target women | 95 men and women attend the visits |

Internal Monitoring and Evaluation:

CHRD will undertake frequent project reviews. Support will be provided in reflecting on field experiences, achievements and lessons learnt, and ensuring submission of timely reports as per Grant requirements. This monitoring will be multi-faceted and include technical, financial, compliance, monitoring, etc. The Project Support Unit will also conduct regular and rigours progress reviews based on a detailed Implementation Plan. The internal M&E process will be responsible for identifying critical areas for improvement, for instance cross cutting issues, focus on poor and vulnerable, duplication of resources etc.

CHRD will also make efforts to build capacities of local staff in monitoring and evaluation. This is because it is difficult to locate professionals with adequate knowledge and experience of monitoring and evaluation of projects in the local market in Matale. In its existing program in the District, CHRD has invested considerable amounts of education and guidance to develop a good cadre of different professionals. This resource pool will be available to provide technical assistance to the project staff when and as required.

BUDGET

| No. | Description | Total cost in LKR | Total cost in US$ |
| --- | --- | --- | --- |
| 1. | Project Cost | 2,198,000.00 | 14,000 |
| 2. | Skill Training | 150,000.00 | 955 |
| 3. | Training Materials | 50,000.00 | 318 |
| 4. | Office Rent | 180,000.00 | 1,146 |
| 5. | Stationary and Postage | 100,000.00 | 845 |
| 6. | Administration | 280,000.00 | 1,783 |
| 7. | Travelling | 150,000.00 | 953 |
|  | Total Cost | 3,140,000.00 | 20,000 |

1 US$ equal to LKR 157.00