## Detailed Bgt
BOCADOS PROPOSED BUDGET FOR
EMPOWERING WIDOWS WITH LIVESTOCK FARMING SKILLS
Sno |  |  | FOR TWELVE MONTHS
1 | Basic Activity One -Senstisation of House holds
| Period | Direct Proj. Activities | Imputs | Qty | Unit cost | Total Proj. sum by | Amnt reqstd
| Y/E 2009/10 |  |  |  |  | (BOCADO)/comty | From Donor
[6 empty] | Shs | Shs
| Oct-Nov | Senstisation of | Venue & seats | 2 days | 100000 | 200000 | 0
|  | farming groups | Facilitors fee | 1 officers | 50000*2days | 100000
|  |  | Facilitors travels | 2 officers | 10000*2days | 40000
|  |  | Facilitator accomodation | 2 officers | 10000*2days | 40000
|  |  | Trainees food & drinks | 60 farmers | 2000*2days | 240000
|  |  | Trainees transport refund | 60 farmers | 2000*2days | 240000
|  |  | Community meeting events | 3 times | 250000 | 750000
|  |  | Stationery for workshops |  | 300000 | 300000
| Total for Activity One |  |  |  |  | 1910000 | 0
2 | Basic Activity Two-Support Programe For Widows.
| Nov-Dec | Construction of
|  | cattle shelters(kiraal) | Cattle shelters (kiraal) | 20 kiraals | 150000 | 3000000 | 3000000
|  | Procurement of cows & | Freesian Heifer-incalf ( 75%) | 20 cows | 1800000 | 36000000 | 36000000
|  | other imputs | Dewarmers-Sulherdemidin | 20 ltrs | 50000 | 1000000 | 1000000
|  |  | Dairy mineral leak (salt) | 648Pcs | 5000 | 3240000 | 3240000
|  |  | Acaricides/Spona | 100 ltrs | 40000 | 4000000 | 4000000
|  |  | Bucket/spray pumps | 20 pcs | 150000 | 3000000 | 3000000
|  | Transport &distributions | Transporting cows from | 20 cows |  | 1450000 | 1450000
supplier to farmers
| Total for Activity Two |  |  |  |  | 51690000 | 51690000
3 | Programe Management
| Dec-Sep | Monitoring & reporting | Vet. Doctor fee/consultancy | 20 cows | 120000 | 2160000 | 2160000
|  |  | Transport means for monitoring |  |  | 3500000 | 3500000
|  |  | Laptop computer | 1 | 1500000 | 1500000 | 1500000
|  | Evaluation & reporting | Project Audit fee. |  | 900000 | 900000 | 900000
|  |  | Communication |  |  | 480000 | 0
|  |  | Office Rent | 12 months | 100000 | 1200000 | 0
|  | Personel(allowances) | Project secretary | 12 months | 100000 | 1200000 | 1200000
|  |  | Project Field officer | 12 months | 100000 | 1200000 | 1200000
|  |  | Contingency Fund |  |  | 147500 | 147500
|  | Total for Prog.Mgt |  |  |  | 12287500 | 10607500
[6 empty] | 65887500 | 62297500
|  |  | Sub-Total requested |  |  |  | Us $, 31,149
|  |  | 12%Transaction fee for GGF |  |  |  | 3738
|  |  | Total project sum requested |  |  |  | 34887
Exchange rate is One Us $ = Ushs 2,000

## Bgt Summary
BOCADO'S BUDGET SUMMARY FOR
HEIFER PROJECT-2009/10
Breakdown
by Activities | Total project Cost | Contribution by BOCADO | Amnt reqstd from Donor
| UGX | UGX | UGX
Basic Activity One | 1910000 | 1910000 | 0
Basic Activity Two | 51690000 | 0 | 51690000
Programe Management | 12287500 | 1680000 | 10607500
Total Project Cost | 65887500 | 3590000 | 62297500
| Sub-total reqstd |  | Us$ 31,149
| 12% Transctn fee GGF |  | Us $ 3,738
| Total project sum |  | Us$ 34,887
NB: |  | Exchange rate is One Us $ = Ushs 2000