ADDITIONAL DOCUMENTATION

ANNUAL WORK PLAN FOR GLOBAL GIVING ACCELERATOR PROGRAMME FOR FY 2019/2020

Name of organization: Amoru AIDs Support Community Initiative (AASCI)                                  	                Financial year: 2019/2020

Prepared by: Project Coordinator                    						           Approved by: Executive Director

Name: Nicholas Engwau                      						                      Name: Florence Auma

Signature: Engwau Nicholas                                                                                                 Signature: Florence Auma

Date: 29.01.2019                                                                                                       Date: 29.01.2019

| Outcome area one. Demand creation for Strengthening Peer Education on AIDs and Reproductive Health (SPEARH) to end AIDs by 2030 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Main activity | Sub Activity | Annual target | Approved quarterly work plan |  |  |  | Detailed planned activities |  |  |
|  |  |  | Q1 | Q2 | Q3 | Q4 | Approved budget | Funding source | Comments |
| - Advocacy | 1.1 Conduct Sub County level Advocacy | 1 | 100 $ |  |  |  | 100 $ | GGA | Provide motorbike |
|  | 1.2 Conduct Parish Level Advocacy | 1 | 100$ |  |  |  | 1000$ | GGA |  |
|  | 1.3 Conduct Village Level Advocacy | 1 | 250$ |  |  |  | 250$ | GGA |  |
|  | Budget Sub Total |  |  |  |  |  | 500$ |  |  |

| Outcome area one. Demand creation for Strengthening Peer Education on AIDs and Reproductive Health (SPEARH)_ to end AIDs by 2030 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Main activity | Sub Activity | Annual target | Approved quarterly work plan |  |  |  | Detailed planned activities |  |  |
|  |  |  | Q1 | Q2 | Q3 | Q4 | Approved budget | Funding source | Comments |
| - Scale up SPEARH | 2.1 Triggering identified villages | 66 | 500$ | 500$ | 500$ | 500$ | 2000$ | GGA | Provide Venue |
|  | 2.2 Selection of members of ACYC | 7280 | 250$ | 250$ | 250$ | 250$ | 1000$ | GGA |  |
|  | 2.3 Holding engagement meetings with members | 42 | 500$ | 500$ | 500$ | 500$ | 2000$ | GGA |  |
|  | Budget Sub Total |  |  |  |  |  | 5000$ |  |  |

| Outcome area one. Demand creation for Strengthening Peer Education on AIDs and Reproductive Health (SPEARH ) to end AIDs by 2030 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Main activity | Sub Activity | Annual target | Approved quarterly work plan |  |  |  |  |  | Detailed planned activities |  |  |
|  |  |  | Q1 | Q2 |  | Q3 | Q4 | Approved budget |  | Funding source | Comments |
| - Use Media/Games | 3.1 Conduct radio talk shows on AIDs | 12 | 250$ | 250$ |  | 250$ | 250$ | 1000$ |  | GGA | Provide human resource |
|  | 3.2 Conduct music, dance and drama in schools | 98 | 250$ | 250$ |  | 250$ | 250$ | 1000$ |  | GGA |  |
|  | 3.3 Conduct educative school debates | 148 | 100$ | 100$ |  | 100$ | 100$ | 1000$ |  | GGA |  |
|  | 3.4 Conduct school health talks | 164 | 100$ | 100$ |  | 100$ | 100$ | 1000$ |  | GGA |  |
|  | Budget Sub total |  |  |  |  |  |  | 4000$ |  |  |  |
| Outcome area two: Strengthening Peer Education on AIDs and Reproductive Health (SPEARH ) supply chain to end AIDs by 2030 |  |  |  |  |  |  |  |  |  |  |  |
| Main activity | Sub Activity | Annual target | Approved quarterly work plan |  |  |  |  |  | Detailed planned activities |  |  |
|  |  |  | Q1 | Q2 | Q3 | Q4 |  | Approved budget |  | Funding source | Comments |
| - Capacity building of staff and club members | 4.1 Orient staff on SPEARH project | 2 | 50$ | 50$ | 50$ | 50$ |  | 200$ |  | GGA | Provide skilled human resource |
|  | 4.2 Identify youth/adolescents to join the clubs | 7280 | 500$ |  |  |  |  | 500$ |  | GGA |  |
|  | 4.3 Train Club Members on life saving skills | 7280 | 3070$ | 3070$ | 3070$ | 3070$ |  | 10283$ |  | GGA |  |
|  | 4.4 Support club members to mobilize and sensitize other youth | 40 | 250$ | 250$ | 250$ | 250$ |  | 1000$ |  | GGA |  |
|  | 4.5 Train condom distributors | 66 | 500$ |  |  |  |  | 500$ |  | GGA |  |
|  | 4.6 Procure and distribute condoms | 5000 | 250$ | 250$ | 250$ | 250$ |  | 1000$ |  | GGA |  |
|  | 4.7 Feeding Children with HIV/AIDS | 48 | 250$ | 250$ | 250$ | 250$ |  | 1000$ |  | GGA |  |
|  | Budget sub total |  |  |  |  |  |  | 15483$ |  |  |  |

| Outcome area three. Enabling environment for Strengthening Peer Education on AIDs and Reproductive Health (SPEARH ) to end AIDs by 2030 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Main activity | Sub Activity | Annual target | Approved quarterly work plan |  |  |  | Detailed planned activities |  |  |
|  |  |  | Q1 | Q2 | Q3 | Q4 | Approved budget | Funding source | Comments |
| - Enabling environment for SPEARH | 5.1 Educating Children Infected with HIV | 12 | 250$ | 250$ | 250$ | 250$ | 1000$ | GGA | Provide skilled human resource |
|  | 5.2 Orient Church leaders on the project | 120 | 150$ |  | 100$ |  | 250$ | GGA |  |
|  | 5.3 Orient local leaders on the project | 180 | 100$ |  | 100$ |  | 200$ | GGA |  |
|  | 5.4 Involve religious leaders in advocacy | 94 | 75$ | 75$ | 75$ | 75$ | 300$ | GGA |  |
|  | 5.5 Conduct group sessions with ACYC | 28 | 250$ | 250$ | 250$ | 250$ | 1000$ | GGA |  |
|  | 5.6 Follow up home visits to clients | 240 | 150$ | 150$ | 150$ | 150$ | 600$ | GGA |  |
|  | 5.7 Home based counselling to youth | 64 | 50$ | 50$ | 50$ | 50$ | 200$ | GGA |  |
|  | 5.8 Facilitate medical bills for children infected with HIV | 18 | 250$ | 250$ | 250$ | 250$ | 1000$ | GGA |  |
|  | Budget sub total |  |  |  |  |  | 2250$ |  |  |

| Outcome area Four. Coordinate activities for Strengthening Peer Education on AIDs and Reproductive Health (SPEARH ) to end AIDs by 2030 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Main activity | Sub Activity | Annual target | Approved quarterly work plan |  |  |  |  | Detailed planned activities |  |  |
|  |  |  | Q1 | Q2 | Q3 | Q4 | Approved budget |  | Funding source | Comments |
| - coordinate activities of SPEARH | 6.1 Secure office accommodation for the project | 2 | 54.3$ | 54.3$ | 54.3$ | 54.3$ | 217.2$ |  | GGA | Provide quality services to beneficiaries |
|  | 6.2 Procure project furniture and all the equipment | 3 sets | 2600$ | 50$ | 50$ | 50$ | 2750$ |  | GGA |  |
|  | 6.3 Pay salaries for staff and volunteers | 8 staff | 1000$ | 1000$ | 1000$ | 1000$ | 4000$ |  | GGA |  |
|  | 6.4 Hold planning and review meetings for Board of Directors | 12 | 100$ | 100$ | 100$ | 100$ | 400$ |  | GGA |  |
|  | 6.5 Hold planning and review meetings with club members | 6 | 500$ | 500$ | 500$ | 500$ | 200$ |  | GGA |  |
|  | 6.6 Documentation of best practices of the project | 4 | 25$ | 25$ | 25$ | 25$ | 100$ |  | GGA |  |
|  | 6.7 End of project evaluation | 1 |  |  |  |  | 100$ |  | GGA |  |
|  | Budget sub total |  |  |  |  |  | 7767$ |  | GGA |  |
|  | Grand Total For 12 Months |  |  |  |  |  | 35,000$ |  |  |  |

Acronyms.

- GGA: Global Giving Accelerator

- ACYC: AIDs Challenge Youth Clubs

- SPEARH: Strengthening Peer Education On AIDs and Reproductive Health

Equivalent amount of rate the rate of exchange (ROE); 1U$ = 3680UGX