FAMILY HARVEST FOUNDATION

Project proposal for Vocational training of 180 youth in Gulu district, northern Uganda

15.02.2019

Contents

Document Purpose	3

Project Context and Objectives	3

Development Objective	3

Purpose	4

Project activities	4

Needed Equipment	4

Framing the Program Goal and Beneficiary Outcomes	6

7

7

Appendix	8

Target Group – Key Terms	8

Problem introduction/Background	9

Non-profit Organization Details	10

Logical framework for the project	12

# Document Purpose

Family Harvest Foundation is pleased to submit this proposal with GlobalGiving in response to the Request for Proposal (“RFP”) published on GG websitein December, 2018.

The following document sets out our proposed approach to deliver based on this engagement. If you have any questions about this proposal or would like additional information, please do not hesitate to contact familyharvestfoundation@gmail.com or our www.familyharvestfoundation.org. We look forward to hearing from you.

# Project Context and Objectives

Family Harvest Foundation is a registered CBO in Gulu district. The foundation operates a Vocational Skills Training Center located at Laliya Oguru, Laliya Trading Centre approximately 4km from Gulu Town Centre along Patiko Road, in Bungatria Sub Country. The Skills Training Center started in 2014 when the founders with the guidance from proprietor of Gulu Central High School felt it necessary to establish a skills training unit to train job creators and self-employable youth, women, war returnees, and vulnerable people who got dropped out of formal education or cannot afford it and build the capacity of educated job searchers.

Family Harvest Foundation (registration no. 6739) as a CBO is destined to provide skills training in line with the Ministry of Education, Science Technology and Sports (MoESTS) and to prepare students to be examined in Uganda Business and Technical Examination Board UBTEB and the Directorate of Industrial Training (DIT) – TVET reg. no UVQF/475. We offer a range of technical vocational and business courses that provide the learner a practical exposure to job creativity, innovativeness and self-employability.

Our other objectives are: a) market linkages, b). recruitment of volunteers, health services, water and sanitation services with key emphasis on the skills training.

# Development Objective

The over twenty years civil war devastated the northern region and it has impacted women, the youth that have no education or job, war returnees, youth including those who graduate with degrees, diplomas or certificates but in a theoretical discipline. We have a conviction that by facilitating these people in vocational skills, they will find a good fit for themselves in the community, because they have been left out and are undergoing a lot of psychological torture from the war experiences. Because of these reasons we intend to provide them with skills and financial assistance by well-wishers after their training so that their living standards are restored. Our target is mainly the youth, young mothers, graduates holding degrees, diplomas, certificates in non-skilled education and war returnees from Gulu district and any part of Uganda. Those with physical disability in any form shall equally benefit. Our training uses both Luo and English, and we have interest in introducing Swahili or any other business languages to provide other opportunities for the trainees during the training and after completion.

# Purpose

The main goal of this project is to equip our target group with appropriate skills and necessary knowledge to make them self-sustaining and contribute to national development.

# Project activities

- to provide hands-on skills training to 180 youth, young mothers or war returnees in different skills arena of Hair dressing, design/cutting/ tailoring, Electrical installation and Welding and metal fabrication and building and concreate practice within Acholi sub region within a 2 years education program in tradesof hair dressing and beauty, tailoring, electrical installation, and welding/ metal fabrication and building and concrete practice.

- to procure basic practical material kits and accessories for the five trades mentioned in this project, required for the hands-on exposure to the trainees to hold the skills expertise within the six to twelve months trainings.

- to provide administrative support and employee cost to effectively train the youth & young mothers and equip them with marketable skills for self-sustenance and national development.

- to link the trained youth with job creator centered organizations and build the capacity of local master craftsmen & women to conduct non-formal or on-site skills transfer and ease start-up by the trainees

# Needed Equipment

In order to be able to cover the above educational activities in terms of tailoring and welding/ metal fabrication our school needs the following items:

Hair dressing and beauty

- salon chairs

- dummy head with short and long hair

- blowers

- assorted saloon accessories.

- assorted saloon accessories.

- assorted set of weaves

- wave glow lounger

Tailoring

- 25 sewing machines

- 3 embroidery/designer sewing machine

- 3 set of a tailor’s tools

- accessories and clothing materials for students

Welding/ metal fabrication

- 3 cutting discs

- 3 grinding machines

- 3 vices

- 2 portable welding machines

- 2 welding machines

- 1 iron bar/pipe molding machine

- 3 pieces of assorted welding tools

- 1 generator machine with 10 Kw power

- assorted pieces of iron bars/pipes

Electrical Installation

- Electrician tool kits

Building and construction practice

- Set of begginer builder and concrete practice

# Framing the Program Goal and Beneficiary Outcomes

(Direct Impact on Program Goal)

Inputs

Pro Bono Services

Volunteers & Employees

Cash

Program Goal by 2020:

180 people equipped with skills to get a job or build a business

Outputs

- people equipped

with skills who go on

to get a job

Conversion Rate of Skills to Jobs and Businesses

Outcomes

Increase economic resilience

Build sustainable business and enterprise

Create employment opportunities for others

Increase a person’s competitiveness in the Job Market

Illustrative Details

- jobs created by the entrepreneur’s business

- people trained by the entrepreneur’s business

- people supported in addition to employees of the business (family / community members)

- people getting employed or grow existing small business by

end of 2020

- people who report an increased actual income/ earning potential

- people who are supported by the individual (family / community members

- people who report improved quality of job

- businesses that obtained external investment

who get a job at

Target Organizations

- who report

improvement in ability

to compete in job

market

- who report positive

change in attitude,

confidence, aspiration

or ambition

Measuring Outcomes for Our Nonprofit partners

(Outcome measures are tailored to individual projects – options are illustrated below – and used to identify and share where value is being created)

Framing Nonprofit Outcomes

Outcome Area

(Outcome areas are selected as relevant to a project or initiative)

- USD value of efficiency savings made that can be invested in further educational services

- increase in conversion rate of skilling programs to employment / business outcome

- non-profit staff trained to deliver education to end beneficiaries

- volunteers trained to deliver education to end beneficiaries e.g. community leaders,

successful entrepreneurs

- employees trained to provide support to end beneficiaries

- end beneficiaries equipped with new skills; list of the different skills built

- contracted new donors / partners

- new donors / or value of new funding grants gained / government contracts won to deliver services / achieving financial sustainability of successful partnerships or collaborations with other non-profits to expand scope of impact

Increase efficiency and effectiveness of program delivery

- new trainees served each year (because of program expansion):

  - 180 trainees within 2 years: 90 new trainees each year between 2019 – 2020

  - increase the number of women in education: 66% of overall number of trainees is women

  - supporting the education of the disabled: total disabled yearly enrollment 5 (3F and 2M)

- maintain and increase the current staff:

  - Keep 15 employees (7 F and 8 M)

  - Recruit 6 Volunteers (3 national and 3, International with 4F and 2M) and Support staff 3 (2 F, 1 M)

Accelerate and scale impact

Achieve marketplace recognition

- awards gained

- mentions in media / media hits

- new public supporters as a result of enhanced media profile or campaign

# Appendix

## Target Group – Key Terms

Gender

- Men

- Women

Age

- Youth (16-25)

- Women and girls

- Adults

Further Definition

- Persons with physical disabilities

- Young mothers

- Students  /trainees

- Graduates holding degrees/diplomas/certificates in non-vocational education

- War returnees

Supporting Information:

- Location: peri-urban

- Level of formal educational attainment: vocational

# Problem introduction/Background

Northern Uganda and the Acholi sub region is more prone to unemployment than any other part of the country as a result of low level of education in comparison. The high level of unemployment is more imbedded in the LRA war which has made the youth in the Acholi community rely more on hand-outs and fail to provide financial support to encourage children to go for formal school making the local people find it difficult to get jobs and are hopeless for future living. Since the youth, young mothers, war returnees live with the un-educated or illiterate youth for a husband in most cases both without any reasonable earnings, they separate with their husband and go back to their parents’ home creating a vicious cycle of dependency, un-employability, un-productiveness and continued living in poverty with the parents/guardian.

With the approval of this project and contributions from similar training institutions, partners and government initiatives, the community psychosocial services that will be provided will change the mentality of the community. The training will capacitate the trainees with skills that will make the disabled, young mothers and youth affected by lack of education and war due to lack of skills-education or arrogance due to old traditional mentality to stabilize families. If other actors contribute to financing the start-up or machines for the trainees to have immediate take-off of earning money from the work they can do out of their skills to improve their livelihood and reduce unemployment (joblessness) and idleness. We therefore need to create equality in the community and sustain the lives of our youth who had undergone difficulties during their job searches, war and restore their happiness. Northern Uganda and the Acholi sub region is more prone to unemployment than any other part of the country as a result of low level of education in comparison. The high level of unemployment is more imbedded in the LRA war which has made the youth in the Acholi community rely more on hand-outs and fail to provide financial support to encourage children to go for formal school making the local people find it difficult to get jobs and are hopeless for future living. Since the youth, young mothers, war returnees live with the un-educated or illiterate youth for a husband in most cases both without any reasonable earnings, they separate with their husband and go back to their parents’ home creating a vicious cycle of dependency, un-employability, un-productiveness and continued living in poverty with the parents/guardian.

With the approval and receipts of the in-kind or financial donor support for this project and contributions from similar training institutions, partners and government initiatives, the community psychosocial services that will be provided will change the mentality of the community. The training will capacitate the trainees with skills that will make the disabled, young mothers and youth affected by lack of education and war due to lack of skills-education or arrogance due to old traditional mentality to stabilize families. If other actors contribute to financing the start-up or machines for the trainees to have immediate take-off of earning money from the work they can do out of their skills to improve their livelihood and reduce unemployment (joblessness) and idleness. We therefore need to create equality in the community and sustain the lives of our youth who had undergone difficulties during their job searches, war and restore their happiness.

# Non-profit Organization Details

| Stated Mission and/or Goals | Vision: To contribute to a community that everyone is capable of contributing to national development. Mission: To provide hands-on skills as a means to community development |
| --- | --- |
| Registered Charity Number | FHF registration no. 6739 |
| Details of Board Membership | Leadership, Organization and Human Resources We have a Board of trustees, Board of Directors, Management Team and staffs. The Board of trustees and board of directors do not make any day today decision in managing the affairs of the institution. The Management team is headed by the Executive Officer who is the top manager of the institution and is consulted on all day today decisions that need his/her opinion. The staff comprise of qualified tutors, and non-qualified casual laborer Key management positions: Our key Management includes Executive Officer who is the chief operations manager of the organization. He/she supervises the Skills Centre Manager, and the Administrative Assistant. The Skills Centre Manager manages the heads of department and the tutors. The roles and duties of the board of trustees and board of directors are provided in the constitution of the CBO while the job description of the Skills Center Manager, the tutors, the Administrative staffs are all provided in the job description booklet of the institution, as well as the terms and conditions of services in the employment handbook. |

| Setup of the organization | The organization is member initiated. Our partners are from civil, government sector and international organizations are: a). Gulu District Local Government b) Gulu NGO Forum, c) Save the Children international, TPO Uganda and UNV Online services. We are destined to provide skills training in line with the Ministry of Education Science Technology and Sports of the Republic of Uganda and to prepare students to be examined in Uganda Business and Technical Examination Board (UBTEB) that of the Directorate of Industrial Training (DIT) – TVET and any other internationally recognised certification. |
| --- | --- |
| Members of the organization |  |
| Bank Details | Centenary Rural Development Bank Limited; Branch: Gulu; Account Name: Family Harvest Foundation; Account No: 7510600981 |
| Further details about the organization | See profile attached. |

| Name of Key Contact | #### Ms. Juliet Acen |
| --- | --- |
| Position/Title | #### Center Administrator |
| Contact address | #### Plot 8 Nehru Road Laroo Division #### Site: Laliya Oguru Village, Laliya Parish, Laliya Sub County, #### P. O. Box 531, Gulu district |
| Preferred Telephone Number | +256772649180 |
| Email | familyharvestfoundation@gmail.com |
| Website | www.familyharvestfoundation.org |
| Date | 15.02.2019 |

# Logical framework for the project

| Project Component/ Narrative Summary | Objectively Verifiable Indicators (OVIs) | Means of Verification (MoV) | Risks/ Important Assumptions |
| --- | --- | --- | --- |
| Goal/Impact: |  |  |  |
| Purpose/Outcomes: |  |  |  |
| To provide quality skills training to youths, women and young mothers to improve their livelihood and make them job creators or be self employed | Qualified tutors teach the trainees skills of the trainees’ interest. | Tutor for hair dressing, tailoring, welding, electrical installation andbuilding and concrete practice teaches 80%: 20% practical & theory to skill the trainees | Getting few individuals willing to train in any of the skills |
| Outputs : |  |  |  |
| Qualified youth, disabled person & young mothers graduate | All the 180 selected youth recruited, complete the training | The 180 qualified youths, young mothers, certificates, photos are issued in a ceremony | Getting the trainees |
|  | Number of youth who have benefited Age of the war affected youth 15 -25 years |  |  |
| Qualified youth, young mothers and war returnees start making money and creating jobs | Number of youths who have businesses and are working to earn a decent living. | Available data on each recruited trainee making money & is innovative and destined for better livelihood | Failure by the youth to create jobs or start making money |
| Good network for the products of the trainees | List and kind of institutions for networking | No. of productive networks No. of products sold to networks | Failure to network |
| Activities |  |  |  |
| Teaching the trainees | Number of lessons covered, Number of practical conducted | Ready timetable according to work plan | Inability by the recruited teachers to teach the students |
| Acquisitions of teaching materials | Kind of teaching materials, Quantity and quality of teaching aid | Teaching kits, practical materials are received in the store by GRNs, delivery note & are in the Bin Cards | High prices as a result of inflation. Poor storage practices. |
| Providing a list of institution for field attachments. | A data bank of potential business units for field attachments | The number of potential businesses displayed or recorded in the school | The existing institution refusing to take students for internship |
| Inputs | Budget estimate / Cost | Presumptions |  |
| Sponsorship (Training fees) | USD11,880.00 | Funding is enough to pay the 180 trainees targeted | Approval of funding is dependent on funds availability and successful approval of this proposal |
| Administrative cost | USD21,360.00 | Funding avaialbility covering the admin cost | Funding approval and locally raised funds enough for the purpose. |
| Equipment and tools | USD18,225.85 | Funding for the equipment and tools generated | Physical of cash donation approval for the items. |
| Practical materials | USD consoildated in equipment cost above | Funding availability from Ministry of Education Science Technology & Sports | Approval of funding is dependant on funds availability and successful approval of this proposal |
| Miscellaneous & tutors available | USD120.00 | Tutors do not leave the teaching job for alternative place of work | The high demand for Skilled Tutors |

|  | Budget estimate for vocational training of 180 youth in Gulu district, northern Uganda |  |  |  |
| --- | --- | --- | --- | --- |
| S/N | Equipment/Tools | Unit Price in $ | Quantity | Total Price in ($) |
| 1. Sponsorship |  |  |  |  |
| 1.1 | Students sponsorship (day scholar) (44@3 term) in a year | 132 | 180 | 23,760.00 |
| 2. Administative cost |  |  |  |  |
| 2.1 | staff cost | 85 | 360 | 30,600.00 |
| 2.2 | Volunteers allowance | 40 | 288 | 11,520.00 |
| 2.3 | office cost | 25 | 24 | 600.00 |
|  | Sub total |  |  | 42,720.00 |
| 3. Hair and Beauty items |  |  |  |  |
| 3.1 | salon chairs | 1,653 | 4 | 6,612 |
| 3.2 | dummy head with short and long hair | 81 | 20 | 1,620.00 |
| 3.3 | blowers | 57.5 | 3 | 337.5 |
| 3.4 | assorted saloon accessories. | 2,100 | 3 sets | 6,300 |
| 3.5 | assorted set of weaves | 752.5 | 3 sets | 2,257.50 |
| 3.6 | head steamers | 68 | 3 | 204 |
|  | Sub total |  |  | 17,331.00 |
| 4. Welding and metal fabrication |  |  |  |  |
| 4.1 | cutting disc | 45 | 3 | 135 |
| 4.2 | grinding machine | 110 | 3 | 330 |
| 4.3 | VICE | 65 | 3 | 195 |
| 4.5 | portable welding machine | 85.85 | 2 | 171.7 |
| 4.6 | Welding mechine | 899 | 2 | 1798 |
| 4.7 | iron bar/pipe molding machine | 5,050 | 1 | 5050 |
| 4.8 | assorted welding tools | 102 | 3 pieces | 306 |
| 4.9 | assorted pieces of iron bars/pipes | 80 | 5 pieces | 400 |
| 4.1 | 22 KVA Cummins C22D5 diesel power generator machine | 4,950.00 | 1 | 4,950.00 |
|  | Sub total |  |  | 13,335.70 |
| 5. Electrical Installation |  |  |  |  |
| 5.1 | Set of electrician kit, More Klein 80028 | 505 | 2 | 1010 |
|  | Sub total |  |  | 1,010.00 |
| 6. Tailoring and design |  |  |  |  |
| 6.1 | sewing machine | 105 | 20 | 2,100 |
| 6.2 | embroidery/designer sewing machine | 450 | 3 | 1,350 |
| 6.3 | set of tailor’s tools | 100 | 3 sets | 300 |
| 6.4 | clothing materials and ACCESSORIES for student’s practical in the tailoring department. | 115 | 5 sets | 575 |
|  | Sub total |  |  | 4,325 |
| 7. Building and Concrete Practice |  |  |  |  |
| 7.1 | Set of begginers construction equipment and tools | 450 | 1 | 450 |
|  | Sub total |  |  | 450.00 |
| 8 | Miscellaneous expenditurees 2 year period | 120 | 2 | 240.00 |
|  | GRAND TOTAL |  |  | 103,171.70 |

Workplan for the the project supported by GlobalGiving 2019 to 2020

| Expected Results | Planned Activities | Implementation Period |  |  |  | Responsible Party | Amount in USD |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Formal recruitment and Administration system established |  | Year 1 |  | Year 2 |  |  | GlobalGiving One year | Others |
|  |  | 1/2 | 1/2 | 1/2 | 1/2 | Director/Skills Centre Manager/Administrator & Tutors Local community, Parents/Guardians or Sponsors |  |  |
|  | Public radio annoucement in 3 radio stations in Gulu. Admission and carrying out sensitization to the youth/trainees. |  |  |  |  |  | 51,581.85 | 200.00 |
|  | Preparation of teaching plans |  |  |  |  |  |  |  |
|  | Acquisition of practical materials |  |  |  |  |  |  |  |
|  | Acquisition of more office facilities like computers |  |  |  |  |  |  |  |
| Receiving certificate of registration the Directorate of Industrial Training (DIT) office – Kampala. | Conduct a mid M&E process considering depreciation. |  |  |  |  | Skills centre manager,Administrator,Local community, Guardian/Parents |  |  |
|  | Provision of mentorship program and home visits to the trainees. |  |  |  |  |  |  |  |
|  | Graduation and awarding of certificates of the qualified trainees. |  |  |  |  |  |  |  |
|  | Acquisition of the start-up materials. |  |  |  |  |  |  |  |
| New customised skills training program introduced to improve livelihood | Purchase of the materials for practicals |  |  |  |  | Skills centre Administrator and the Project officer |  |  |
|  | Implementation of the other supportive skills. |  |  |  |  |  |  |  |
|  | Recruitment of more expatriates in skills training, management. |  |  |  |  |  |  |  |
|  | Purchase of more tools |  |  |  |  |  |  |  |
| Healthy beneficiaries | Giving health tips about home sanitation |  |  |  |  | Head of department health and sanitation, skills centre Administrator. |  |  |
|  | Recruitment of more health staffs |  |  |  |  |  |  |  |
|  | Continuous check-up of the trainees. |  |  |  |  |  |  |  |
|  | Provision of health sensitisation program |  |  |  |  |  |  |  |
| Reliable manpower base | Implementing budgetary plan |  |  |  |  | Director & Head of Accounting department. |  |  |
|  | Recruitment of internal Auditors, board approvals |  |  |  |  |  |  |  |
|  | Continuous checking of the book of Accounts. |  |  |  |  |  |  |  |
|  | Preparation of half year and Annual reports timely. |  |  |  |  |  |  |  |