FORWARDIT CHARITY VOCATIONAL YOUTH SKILLS TRAINING PROJECT BUDGET 2019-2021

| Budget line | Q1, UGX | Q2,UGX | Q3,UGX | Q4,UGX | Subtotals,UGX |
| --- | --- | --- | --- | --- | --- |
| People and time (salaries) |  |  |  |  |  |
| Director | 600,000 | 600,000 | 600,000 | 600,000 | 2,400,000 |
| Field officers (2) | 1080,000 | 1080,000 | 1080,000 | 1080,000 | 4,320,000 |
| Instructors (4) | 1,800,000 | 1,800,000 | 1,800,000 | 1,800,000 | 7,200,000 |
| Accountant (1) | 750,000 | 750,000 | 750,000 | 750,000 | 3,000,000 |
| Office and administration |  |  |  |  |  |
| Office rent | 450,000 | 450,000 | 450,000 | 450,000 | 1,800,000 |
| Communication services (telephone, email, internet) | 500,000 | 450,000 | 450,000 | 450,000 | 1,850,000 |
| Administrative Cost | 1,100,000 | 1,100,000 | 1,100,000 | 1,100,000 | 4,400,000 |
| Capital/equipment |  |  |  |  |  |
| Audio Visual equipment and accessories (1set) | 8,00,000 |  |  |  | 8,00,000 |
| Computers Units (1feild laptop set) | 1,400,000 |  |  |  | 1,400,000 |
| Generator (1 item) | 8,00,000 |  |  |  | 8,00,000 |
| Flip Chart Stand (1tem) | 3,00,000 |  |  |  | 3,00,000 |
| Other (please specify) Program Costs |  |  |  |  |  |
| Training community workshops (5 trainings) | 3,050,000 | 3,050,000 | 3,050,000 | 3,050,000 | 12,200,000 |
| IEC Materials (20,000 copies) | 2,000,000 |  |  |  | 2,000,000 |
| Radio Program | 1,500,000 | 1,500,000 | 1,500,000 | 1,500,000 | 6,000,000 |
| Instructional Requirements | 3,548,750 | 3,548,750 | 3,548,750 | 3,548,750 | 14,195,000 |
| Community interaction meetings (5meetings) | 500,000 | 500,000 | 500,000 | 500,000 | 2,000,000 |
| T-Shirts | 1,499,400 |  |  |  | 1,499,400 |
| Certificate | 751,400 |  |  |  | 751,400 |
| Monitoring and Evaluation | 300,000 | 300,000 | 300,000 | 300,000 | 1,200,000 |
| Audit | 500,000 | 500,000 | 500,000 | 500,000 | 2,000,000 |
| TOTALS | 23,229,550 | 15,628,750 | 15,628,750 | 15,628,750 | 70,115,800 |

The total program cost for 1year is 70,115,800, but the program is expected to run 3years

Budget Notes:

- Program Costs:                                                                                                                     Training workshops for community support groups (Volunteers).                                                                                                                                This is purposely to identify the potential youths who will be trained to restore consultation and sustainability in their respective communities.

- Facilitators transport                     :     2 officers x 30,000 = 60,000

- Participant break first                    :        50 ppts x 2,000 = 100,000

- Participants lunch                          :        50 ppts x 5,000 = 250,000

- Evening tea for participants           :               50 x 2000 =   100,000

- Venue (hire)                                  :       100,000 x 1       =   100,000

- Total =                                       :                                      610,000/=

The result will be 610,000/= x 5 days x 4 workshops = 12,200,000/=

Instructional requirements

- Carpentry (timber and accessories)

- Timber (12 x 1 ½ x 12               :        200 peaces x 20,000 = 4,000,000

- Adhesive (wood glue pono)      :                     tins x 7,000  =     175,000

- Drying  Agents                           :                                             =  50,000

- Nails ( assorted)                         :                      30 kg x 4,000 = 120,000

- Vanish (2 jyracan 40 Lt)            :                       100,000 x 2    = 200,000

- Sand Paper                                  :        3,000 per (M) x 20(M) = 60,000

- Ply wood  (10 peaces)                :                         20,000 x 10 = 200,000

- Total =                                       :                                             = 4,805,000/=

- Tailoring (rolls of clothes)

  - Sugar Paper (20 reams)                 :             20 x 60,000 = 1,200,000

  - Polyester material (24 rolls)          :               24 x 60,000 = 1,440,000

  - Accessories                                    :                                 =    500,000

  - Total =                                           :                               =  3,140,000/=

c) Shoe Making and other works:

Vegetable leather square foot                 :                      5000 x 50 =     250,000/=

Close contact Adhesive (tough bond)     :                   40,000 x 25 = 1,000,000/=

Soles (flat soles)                          : 40,000 x 2 sheets x 50 people = 4,000,000/=

Accessories                               :                                                    = 1,000,000/=

Total                                       :                                                 =   6,250,000/=

Therefore all this will be 6,250,000 UGX for 4.quarters

All instruction materials will cost 14,195,000/= a full year

- Community interaction meetings:                                                                                                                                  This will be conducted targeting stake holders (community leaders/elders) who will be an eye for effective planning and implementation of the project.

Venue (hire)                     :                        100,000 x 1 = 100,000/=

Refreshment                                    :                         3,000 x  80 = 240,000/=

Facilitators                                          :                           30,000 x 2 =   60,000/=                                         Total                                                                                                 = 400,000/=

Therefore the meetings will cost 300,000 x 4 meetings =1, 200,000/

- Radio talk show                                                                                                              Vocational training programs will be conducted through sustainable skills awareness work shops, involvement of youths planning aspects, Radio programs running on monthly bases, talk shows organized at the center. Radio programs will be broken down as below:-

Radio programs                                     :               450,000 x 1 = 450,000   Technical officer allowance                  :                   		          50,000 x 1 =   50,000                                                   	Total =                                                                           = 500,000/=

All radio talk shows will be 12 x 500,000 = 6,000,000/=

5.  Project Monitoring and Evaluation (M $ E)

The project team will offer this M & E on monthly basis for one year. The breakdown is as follows:-

Officers Transport and Lunch                 :     50,000 x 2 officers = 100,000

Therefore, each M & E activity will be 100,000 x 12 months = 1,200,000/=