Plan for 2019 School water filter projects

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Action** | **Responsible Authorities** | **Due Date** | **Completed Date** | **Budget**  **USD** |
| Determine if CDC is interested in projects for 2019 | Ha, CDC | Dec 2018 | Yes they are | 0 |
| **Phase 1** |  |  |  |  |
| Determine MEDRIX budget contribution ($400) | MEDRIX board | Jan 2019 | done | 0 |
| Write plan for 3 LifeStraw Community model systems for Nam Dong schools | Robert, MEDRIX | Feb 2019 | done | 0 |
| Get Vietnamese provincial Center for Disease Control (CDC) approval of plan | MEDRIX Ha, CDC | Mar 2019 | done | 0 |
| Get provincial People’s Committee approval of plan | CDC | Mar 2019 | done | 0 |
| Create Global Giving fund raising project | Robert | Apr 2019 |  | 0 |
| Order three LifeStraw Community water filter systems | MEDRIX Ha | Jul 2019 |  | 1500 |
| Transport and install systems and train operators | CDC | Aug 2019 |  | 300 |
| Evaluate LifeStraw Community systems for acceptable performance | MEDRIX, CDC | Sep-Nov 2019 |  | 100 |

|  |  |  |  |
| --- | --- | --- | --- |
| DEPARTMENT OF HEALTH SERVICE OF THUA THIEN HUE PROVINCE **CDC CENTER**  No: 06/KSBT-SKMT-YTTH  Re: Proposal for project “Improving health and hygiene at the high risk areas of Thua Thien Hue province” in 2019 | | **THE SOCIALIST REPUBLIC OF VIETNAM** **Independence - Freedom - Happiness**  *Thua Thien Hue, January 3, 2019* | |
| To: MEDRIX Organization. | |

Base on the Dispatch No. 3458/NVY-SYT dated 28/12/2018 of Department of Health Service of Thua Thien Hue province regarding the proposal to the support of MEDRIX. The Department of Health Service assigned CDC center continue to assess the real need to improving the health and Hygiene at the high risk areas of Thua Thien Hue province; Put on the detail project plan that **suitable to the budget of MEDRIX** and send proposal to MEDRIX for project 2019 and the years to come.

Base on the Decision No. 2234/QĐ-UBND dated 10/10/2018 of People Committee of Thua Thien Hue Province regarding the adjusting the Point 6 and point 7 of Article 1 of Decision No. 1700/QĐ-UBND dated 31/ 8/ 2015. In 2018, The CDC center cooperated with the District Health Center and Center for education and training of Quang Dien and Nam Dong Districts to implement project “Improving the health and hygiene of the high risk areas of thua Thien Hue province” funded by MEDRIX in 2018 at 12 preschools of Quang Dien and Nam Dong.Project provided training for the leadership of schools, Health workers at 17 preschool and 11 clinics of Quang Dien, 181 teachers of 8 preschools of Quang Dien, 84 teachers from 4 preschools of Nam Dong District. Provided 36 sets of flip chart and 54 picture books for 12 preschools. Project also supported 20 water treatment systems for 12 preschools, these water systems have been used to get safe drinking water for children.

In November 2018, CDC team has conducted the survey on the usage of LifeStraw water systems that were supported by MEDRIX project, each system capacity can support only 50-60 children. The schools would like to continue receive the support from project focusing the following activities: to provide more water system especially the branches. To provide training on health education such as: personal hygiene, environmental sanitation, use safe water for the teachers and the chiefs at schools.

The CDC center would like to proposal MEDRIX to continue the support to the project “Improving the health and hygiene of the high risk areas of thua Thien Hue province” in 2019 and the years to come.

Thanks and best regards,

***To:* DEPUTY DIRECTOR PHỤ TRÁCH**

- Sender; (Signed)

- Health service of TTHue (reported); **Nguyễn Đình Sơn**

- Filed: Office, Environment department*.*