PROJECT PROPOSAL

PROJECT TITLE:	PROMOTION OF GRASSROOTS ENGAGEMENT TO REDUCE MATERNAL AND INFANT MORBIDITY AND MORTALITY.

CONTACT PERSON: 	KOMAKECH DENIS

Email:        komden08@gmail.com

Teleph:        +256-772876267 / -711876267

ORGANIZATION:	CONCERNED ACTION FOR HEALTH (CAFH).

Email:           concernedactionforhealth@yahoo.com

www:concernedactionforhealth.com

COST OF OPERATIONS:		UGX 12,092,500/= ($ 3455)

- ACKNOWLEDGEMENT

I am grateful to the STEP UP-USA team who greatly inspired my ideology, work and facilitated the preparation of this document by allowing CAFH work closely with STEP UP-Uganda, through pioneering the first TBRAs/VHT training that has provided bases of the concept of engaging community grassroots in the effort to reduce maternal and infant morbidity and mortality in Aswa Health Sub district, Awach H/C IV, Gulu.

I am particularly thankful to Ann and Mathew, Professor Joshua, for their valuable guidance. I am also equally thankful to Board of Trustee of STEP Uganda, especially Doctor Maria, Patrick, and Father Remijo for accepting to work with CAFH to pioneer the VHT/TBRAs training.

- EXECUTIVE SUMMARY:

Promotion of grassroots engagement to reduce maternal and infant Morbidity and mortality project is a collaborative effort of the village health care team especially the TBRAs(VHT) to reduce MCH morbidity/mortality in Aswa Health Sub District in Gulu.

This project was conceived after a careful assessment of the gaps and factors that promote high maternal and infant mortality and morbidity in the community.

Studies have however shown that, although a modest reduction in newborn deaths can be achieved when TBAs are trained and supported, a reduction in maternal deaths does not occur. And against this background the Government of Uganda in 2010 abolished the use of TBAs to aid community safe deliveries, but to make diagnosis of labour and ensure referrals and escort mothers to facilities for skilled attendant delivery (SBA), as a way to improve on maternal and infant morbidity and mortality in the country.

This transitional change in their role and responsibilities as Traditional Birth Referral Assistants (TBRAs) were not formally communicated and more especially reasons for such a drastic decision was not disseminated to the community and to the TBAs themselves.

This project therefore seeks to train and actively engage the TBRAs on their new roles and responsibilities and disseminate the reasons as to why their duties as TBAs were recalled, and the benefits of them being involved passively as caretaker of expectant women other than active delivery service provider, and in that manner there will be improved access and utilization of health center delivery and reduced Maternal and infant morbidity and mortality.

- INTRODUCTION TO THE PROJECT:

Project title: “Promotion of grassroots engagement to reduce Maternal and Infant Morbidity and Mortality”.

Promotion of grassroots engagement to reduce maternal and infant Morbidity and mortality project is a contributive effort of primary health care activity by village health care team especially the TBRAs(VHT) to reduce MCH morbidity/mortality in Aswa Health Sub District in Gulu.

This project was conceived after a careful assessment of the gaps and factors that promote high maternal and infant mortality and morbidity in the community.  These high rates are attributed to insufficient and poor-quality care during pregnancy and childbirth,  inadequate access to a skilled birth attendant (SBA),  professionally trained staff are often in short supply and there is a tendency for women to rely on traditional birth attendants (TBAs) for delivery.

Studies have however shown that, although a modest reduction in newborn deaths can be achieved when TBAs are trained and supported, a reduction in maternal deaths does not occur. And against this background the Government of Uganda in 2010 abolished the use of TBAs to aid community safe deliveries, but to make diagnosis of labour and ensure referrals and escort mothers to facilities for skilled attendant delivery, as a way to improve on maternal and infant morbidity and mortality in the country.

This transitional change in the roles and responsibilities of the TBAs were not formally communicated especially concerning their new role as Traditional Birth Referral Assistants (TBRAs).

Furthermore the TBAs were assumed to be co-opted into the Village Health Team (VHT) without any formal training pertaining their new roles and responsibilities.

“Promotion of grassroots engagement to reduce maternal and infant Morbidity and mortality” is therefore a project conceived to address the following concept:-

- To clearly identify and communicate the role of the TBRAs;

- To train in the best way to include these experienced women in the continuum of maternal and infant care excluding their carrier in delivery of expectant mothers;

- To restore the respect and trust by the community on to the TBRAs as a role model and are linked with the existing health system;

- To continue to act as community-based providers or promoters of maternal and infant health care;

- BACKGROUND OF THE PROBLEM:

Maternal mortality remains a significant public health problem in developing countries, especially in sub-Saharan Africa, where 87 % of global maternal mortality occurs. These high rates are attributed to insufficient and poor-quality care during pregnancy and childbirth. Though the number of deliveries taking place in health facilities has increased globally, about 40 million women still deliver without skilled care every year, about a third of whom are assisted by a TBA.

The World Health Organization (WHO) recommends one midwife for every 175 pregnant women but this standard is far from being achieved; in Uganda, where 1.5 million women give birth every year, there are approximately 15,184 well-trained midwives to assist in the childbirth process. The MMR has dropped to 338 per 100,000 live birth from 486/100,000 which is still quite high above the required standard.

Since the 1994 International Conference on Population and Development, male involvement in reproductive health issues has been advocated as a means to improve maternal and child health outcomes, but to date, health providers have failed to achieve successful male involvement in pregnancy care especially in rural and remote areas where majority of the underserved populations live. In an effort to enhance community participation in maternity care, TBAs were trained and equipped to ensure better care and quick referral.

Studies have however shown that, although a modest reduction in newborn deaths can be achieved when TBAs are trained and supported, a reduction in maternal deaths does not occur. And against this background the Government of Uganda in 2010 abolished the use of TBAs to aid community safe deliveries, but to make diagnosis of labour and ensure referrals and escort mothers to facilities for skilled attendant delivery, as a way to improve on maternal and infant morbidity and mortality in the country.

This transitional change in the roles and responsibilities of the TBAs were not formally communicated especially concerning their new role as Traditional Birth Referral Assistants (TBRAs).

Furthermore the TBAs were assumed to be coopted into the Village Health Team (VHT) without any formal training pertaining their new roles and responsibilities.

- STATEMENT TO THE PROBLEM:

Abolishment of the use of TBAs in conducting community safe delivery has been met with mixed reaction from both the community and the TBAs themselves. In 2010 the government decided to stop the use of the TBAs on the grounds that studies have indicated there was no reduction in maternal mortality and morbidity because TBAs have been unsuccessful in detecting and handling obstetric complications (such as postpartum hemorrhage, postpartum sepsis, eclampsia, obstructed labour, and complications of unsafe abortion), hence resulting into high mortality and morbidity.

This government position affected the communities who had gain confidence and trust in the efforts of the TBAs in handling safe community deliveries after several years of government involvement, implementation and training of TBAs.

However the government co-opted the TBAs into the VHT structure and change their role and responsibilities to include;- to make diagnosis of labour, ensure referrals and escort mothers to facilities for skilled attendant delivery, as Traditional Birth Referral Assistants (TBRAs).

This transitional change in their role and responsibilities as Traditional Birth Referral Assistants (TBRAs) were not formally communicated and more especially reasons for such a drastic decision was not disseminated to the community and the TBAs themselves. This phenomena only changed the approaches of the TBAs in conducting their illegal activities underground and more so unsupervised putting more lives at risk.

This project therefore seeks to address this situation by actively engaging the TBRAs and training them on their roles and responsibilities and disseminate the reasons as to why their duties were recalled. and the benefits of them being involved passively as caretaker of expectant women other than active delivery service provider, and in that manner there will be improved access and utilization of health center delivery and reduced Maternal and infant morbidity and mortality.

- PROJECT JUSTIFICATION:

Following a random telephone call to a certain the total number of health center skilled delivery in both Gulu and Omoro District, the midwives gave an average skilled delivery attendance of 65% to 70% meaning that a good percentage of the expectant women still give birth at home or presents to the facility as Birth Before Arrival (BBA).

The 2016 Uganda Demographic and Health survey indicates that 73% of deliveries are conducted in the facilities, 55% of the children received all the basic vaccination, and 29% of the children under 5 are stunted.

The above figures therefore implies that at least 30% of unskilled deliveries are still occurring in the community in the hands of TBAs, 45% of the children in the community are not accessing complete immunization services, and lastly 29% of the children are not having the right amounts of food to eat.

These figures have remained stagnantly high despite biomedical interventions to improve the situation due to a number of challenges that includes; - poor male involvement, poor behavioural change practices, poor community attitudes, sociocultural influences and so on.

Maternal child health and nutrition interventions play a critical role in the reduction of maternal and child morbidity and mortality rates in the 1,000 days in child’s life which is a period from conception up to 2 years provides a basis for child’s physical and mental development. Compromised maternal health and nutrition for the child within this period presents far reaching consequences  that  include;  physical  stunting,  mental  impairment,  higher  susceptibility to disease, increased risk of mortality, poor performance in school, and lower future incomes.  Poor  maternal  health  and  nutrition  during  the  1,000  days  results  into  a vicious  cycle  of  inter-generation  malnutrition  and  poor  health  which  can  be  broken by timed and targeted health and nutrition interventions.

CAFH/SUU and its management found it necessary to institute a project to address the grassroots causes of maternal and infant morbidity/mortality through promotion of community engagement by actively involving the VHT/TBRAs to create demand and promote health seeking behavior amidst the community targeting pregnant women and their spouses.

“Promotion of grassroots engagement to reduce Maternal and Infant Morbidity and Mortality” is justified on the following grounds:

- There is still high illegal community deliveries under the care of the TBAs who are not recognized or supervised by government and hence putting the lives of many at risk.

- There is immediate need to train and formalize the roles and responsibility of the TBRAs amidst the VHT

- Tap the wealth of knowledge and experience of trained TBRAs to provide basic health information on: referral, neonatal care, postpartum care, breastfeeding, weaning practices, detecting of danger signs in pregnancy, nutritional education, advocate for family planning and other health interventions

- To use the TBRAs to enable pregnant mothers deliver in the health centers by referral and escorting them to the facility.

- Ensuring birth preparedness by both couples(savings, clothing, transport means etc )

- In a study conducted by Turinawe et al 2015, found out that men trust and have confidence in TBAs; and therefore closer collaboration with TBAs may provide a suitable platform through which communities can be sensitized and men actively brought on board in promoting maternal health services for women in rural communities.

- Help to bridge the relationship between the TBRAs and the health care providers in ensuring continuum of care.

- Over 70% of the VHTs are male and out of the 30% female and none is a TBRAs, therefore using this opportunity to integrate the TBRAs in the VHT structure is critical.

- Lastly there has been a total of 37 TBRAs accompanied deliveries made since the last VHT/TBRAs training was done in Aswa HSD, which is a good indication that the intervention is feasible and working. The midwives report that their relationship with the TBRAs have greatly improved with ability to share information relating to the pregnant mothers.

- MISSION STATEMENT OF THE PROJECT:

The Mission Statement of the project is to promote community engagement to reduce Maternal and infant mortality.

- THE VISION:

The Vision of project is “A SMILE AT THE END OF EVERY PREGNANCY”

- PROJECT OBJECTIVES

To contribute to the general prevention of maternal-infant mortality and morbidity by training VHTs/TBRAs on their new roles and responsibilities as birth referral Assistants.

- SPECIFIC OBJECTIVES

To provide training and supervision so that the VHT/TBRAs can effectively:-

- Train the VHT/TBRAs on timed and targeted counseling a package of key health and nutrition messages disseminated to pregnant and breastfeeding mothers to cause sustainable behavioral change at specific timelines in the 1,000 days of the pregnancy and child life.

- Evaluate and assess pregnant women; detect early pregnancy, danger signs before, during, and following childbirth; and provide timely escort referral

- Provide basic biomedical health information on FP, breastfeeding practices, weaning and nutritional education for the women and infant, Antenatal care and emphasis the benefit of hospital delivery

- Create a working relationship and referral systems between the TBRAs/VHTs with the facility health care providers

- PROJECT ACTIVITIES

To achieve the various objectives, the project shall undertake the following activities.

Objective 1: To train selected VHT/TBRAs on their new roles and responsibility using the timed and targeted counselling strategy to address maternal child health.

Indicative activities.

a)	Identification, mapping out and invitation of VHT/TBRAs 3 per village per sub-county a total of 222. The process is expected to take 2 days.

b)	Training of selected VHT/TBRAs. There will be 6 training, one per each sub-county of Palaro, Patiko, Awach, Paicho, Bungatira, and Unyama.

c)	Report writing and sharing with stakeholders.

Objective 2: Evaluate and assess pregnant women; detect early pregnancy, danger signs before, during, and following childbirth; and provide timely escort referral

Indicative activities.

a)	VHT/TBRAs conduct village registration of pregnant mothers and provide timed and targeted counselling on pregnant and infant care.

b)	Providing monthly reports to the nearest health center of the outcome of their interaction with the community.

Objective 3: Provide basic biomedical health information on FP, breastfeeding practices, weaning and nutritional education for the women and infant, antenatal care and emphasis the benefit of hospital deliver

Indicative Activities

a)	Conduct community mobilization and sensation on basic biomedical health information.

b)	Distribution of IEC materials on maternal and child health

c)       Support the health center in mobilization and sensitization on health information as required.

Objective 4: Create a working relationship and referral systems between the TBRAs/VHTs with the facility health care providers

Indicative activities.

a)	Conduct regular meetings with the health center staffs (midwifes) to discuss issues that affect service delivery and how to address them.

b)	Ensuring feedback from the health center staffs on the referral of cases, outcome of the interventions and recommendations for the VHT/TBRAs.

12.	PROJECT ACTIVITY AND BUDGET COSTS.

| Budget Item | Activity Code |  | Item Description |  | No of Units | Cost Per Unit /person | UGs | US $ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Direct activity Costs | 1.1 Selection and training of VHT/TBRAs |  | Invitation and training of VHT/TBRAs 222 ppt (3 per Village). |  | Persons | Lunch 5000 x 37 ppt x 6 training Evening tea 2000/= x 37 ppts x 6 training Break tea 2000/= x 37 ppts x 6 training | 1,110,000 444,000 444,000 | 317 127 127 |
|  | SUB TOTAL |  |  |  |  |  | 1,998,000 | 571 |
|  | 1.2 b materials cost for trainings |  | Training and facilitation cost |  |  | Allowances 4 staffs x 50,000= x 2days x 6 trainings Tpt for facilitators 20,000 x 4 staffs x 2 times x 6 Lc iii opening 30,000 x 6 training Stationary flip chart 6 pcs x 20,000/= Markers 3 boxes x 9000/= Masking tapes 4 pcs x 5000/= Exercise books 100,000 Pens 7 boxes x 15,000 | 2,400,000 960,000 180,000 120.000 27,000 20,000 100,000 105,000 | 686 274 51 34 8 6 29 30 |
|  | Sub-Total |  |  |  |  |  | 3,912,000 | 1118 |
| Sub Total |  |  |  |  |  |  | 5,910,000 | $1689 |
| Indirect Support Costs & Supplies | 1.1 a Local administrative cost |  | Communication Internet Reports Developing reporting tools |  |  | Air time Internet services Typing and printing reports Printing reporting and referral tools | 100,000 100,000 200,000 200,000 | 29 29 58 58 |
| Sub-Total |  |  |  |  |  |  | 600,000/= | $174 |
| Project management |  | 1.1 Monitoring and Evaluation |  | Monitoring of project |  | Facilitation for meeting 100,000 x 5 staffs 3 times Data collection filling 200,000 x 2 staffs x 3times | 1,500,000 1,200,000 | 429 343 |
|  |  |  |  | Evaluation of project |  | Mid and End evaluation 500,000.x 2staffs x 2time | 2,000,000 | 572 |
|  |  |  |  | Dissemination meeting |  | Inchargers of HCs and TBRAs rep 30 ppt x 20,000 DHO representative 1 x 50,000 LC III 6 x 20,000 Facilitators allowences 50,000 x 2 staffs | 600,000 50,000 120,000 100,000 | 171 14 34 29 |
| Sub total |  |  |  |  |  |  | 5.570,000 | 1592 |
| Grand-Total |  |  |  |  |  |  | 12,092,500= | $3455 |

NOTE: this budget targets the whole Aswa county including all its village. However in case of any budget constrain, adjustment and redrawing can be done accordingly.

This is a guide to the financing which is liable to adjustment.

13. MONITORING AND EVALUATION

MONITORING

Monitoring will be a continuous process throughout the project life.

a)	This will take the form of field visits by health center staffs and CAFH/SUU leadership. This will be done using monitoring tools through;

b)	Focus group discussions with structures and community. In other places, informative interviews will be conducted with conducted with selected key stakeholders

c)	Other forms will be through review of documentation at the health center and data validation through VHT team leaders.

d)	Executive of CAFH/SUU will conduct periodic visits to health center and participation in planed activates to ascertain that implementation is according to the plan. This will also ensure that unforeseen challenges and learning are adapted.

EVALUATION PLAN

There will be midterm review at sub county levels and a final evaluation at the end of the project.  Such evaluation will bring stakeholders together for the purpose of determining impact and effectiveness of the project interventions.  Findings will be disseminated through a final report to be submitted to Step Up USA and other stakeholders.

- SUSTAINABILITY

The project shall be sustained as follows.

- Implementation shall use the local government structures that will carry on with the work as the normal mandate and the management of CAFH will continue working with the VHTs/TBRAs to improve on maternal and child health.

- Each of the VHT/TBRAs shall be encouraged to link with the sub county leadership to help address concerns that requires the attention of the local leadership.

- PROJECT FEASIBILITY

- Over 70% of the VHTs are male and out of the 30% female and none is a TBRAs, therefore using this opportunity to integrate the TBRAs in the VHT structure is critical.

- Lastly there has been a total of 37 TBRAs accompanied deliveries made since the last VHT/TBRAs training was done in Aswa HSD, which is a good indication that the intervention is feasible and working.

- The midwives report that their relationship with the TBRAs have greatly improved with ability to share information relating to the pregnant mothers.

- MANAGEMENT OF THE PROJECT

The project will be managed by SU-USA/SU-Uganda and CAFH will only provide technical insight and on the ground implementation and mobilization for the VHT/TBRAs activities with periodic feedback to the management of SU-USA and SU-Uganda. The authority and leadership in this partnership with lie in the hands and steer-ship of SUU.

- PROJECT OUTCOME

•	Trained TBRAs who know their new roles and responsibilities

•	coopting of the TBRAs into the VHT structures officially

•	Introduction of the TRBAs to the health unit management and staffs

•	Improved working relationship between the health unit and the TBRAs

•	Identification and referral of pregnant mothers by TBRAs to the facility.

•	Advise mothers to go for antenatal care

•	Talk with husbands/male involvement on MCNH

•	Encourage pregnant mothers to save money

•	Form groups among TBRAs and VHTs

•	Reduced home deliveries

•	improved health unit deliveries.