DLSU SAGIP METRO: A University-led Relief Drive for the Victims of Typhoon Ondoy

Weeks after the typhoon Ondoy (Ketsane) brought rain and inundated with floods many areas in Metro Manila and nearby provinces (Rizal, Laguna, and Bulacan), the situation on-ground remains challenging. As of October 8, 2009, the National Disaster Coordinating Council (NDCC) has pegged the total damage caused by Ondoy at PhP 9.7 billion. Lives were also lost. A total of 298 people were killed, 5 injured, and 39 missing. The NDCC has also claimed that about 829,498 families or 4 million people have been affected by the typhoon. Of this, more than 100,000 families are still requesting for assistance.

On September 28, two days after the devastating typhoon wrought havoc to the lives of many Filipinos, De La Salle University (DLSU) started relief operations via project “Sagip Metro (Save Metro),” jointly organized by DLSU’s Center for Social Concern and Action (COSCA), Student Council (SC), and the Office of the President and Chancellor.

The project has proven to be an opportunity for Lasallians to rekindle the spirit of damayan in time of disaster. Students, faculty members, staff, parents, and alumni have shown their support for the relief drive by serving as volunteers, donating goods and money, offering vehicles for the relief distribution, asking network and partner organizations for donations and reporting situations of other Lasallians who need special assistance or intervention.

First Phase Operation

During the first day of the relief drive, more than 400 volunteers showed up and assisted in soliciting donations, packing and distributing goods to identified communities. Some students and faculty volunteers even went to malls near the university to solicit goods for the relief operation. In the succeeding days of the operation, the project team had to organize at least two shifts to accommodate the increasing number of volunteers. Donations also poured in as other members of the academic community helped in disseminating the information about the university-led relief drive. Below are graphs showing the detailed information on the involvement of volunteers and the donations received during the first phase of relief drive.

By the end of the first wave of relief operation, 11,616 bags of food, toiletries, clothing, water, and medicine were given away to 29 communities across 14 cities and provinces. The distribution of relief goods was done in coordination with 22 partner community-based organizations, church institutions, local government units, civil society and other organized groups.

Project Structure & Committees

To make the relief drive organized and systematic, the project team put up a structure and mechanisms for operation. Sagip Metro has assigned an overall coordinator to harmonize the activities of the identified committees. The five major committees are: a) Donations; b) Deployment & Distribution; c) Mobilization of Volunteers; d) Documentation, and e) Dissemination of Information.

The Donations Committee receives donations both in kind and in cash, makes the necessary inventory of the received donations and donors, and sorts and packs the received items for distribution.

The second committee, Deployment & Distribution, identifies and prioritizes the target beneficiaries and facilitates the deployment and actual distribution of the relief goods. This committee also makes sure that there is at least one organized group in the identified communities.

The third committee, volunteer mobilization, deals with concerns related to effective and efficient way of mobilizing volunteers. It assigns volunteers to a particular task. The committee also gives pre and post-activity orientation/de-briefing for volunteers (e.g. deployment, packing etc.). Meanwhile, the Dissemination of Information Committee is responsible for sending out official announcements and correspondences to the university’s institutional partners and to the public in general on Sagip Metro.

Lastly, the Documentation Committee is in-charge of consolidating all the reports of other committees (e.g. list of members of DLSU community - students, faculty, staff etc. - and partner communities that have been badly hit by Ondoy). It is also tasked to organize the information on the situation of the affected Lasallians and partner communities as well as their immediate needs. It updates the Information Dissemination committee so the latter can come up with regular announcements.

Aside from the structure and ad hoc committees, the team also came up with a set of criteria for selecting and prioritizing target beneficiaries of the relief goods. The criteria are as follows: a) partner communities/members of DLSU community as priorities; b) urgency of needed intervention; c) extent of damage to community; d) extent of assistance needed; e) extent of assistance already received (from NGOs, GOs, Church groups etc.); f) existence of organized & credible group to lead identification & distribution (based on information from coordination efforts and news).

Second Phase of Relief Drive & Future Plans

After four days of relief operations (September 28 to October 1), the project team decided to temporarily cease relief goods packing and deployment activities due to safety threats posed by tropical storm Pepeng (Parma). The second phase of relief project resumed last October 5 (Monday) and ended October 10 (Saturday). Cash donations, however, are continually being accepted to support more comprehensive rehabilitation efforts to be undertaken by the university.

Rehabilitation intervention includes physical assistance (house build, environmental clean up, putting up/installation of water and lighting systems, solid waste management etc.), psychological & post-disaster trauma counseling, community rebuilding & development (livelihood, disaster prevention etc.) interventions. Plans for reconstruction and rehabilitation of affected families are already being discussed with partner communities. The university will also conduct series of workshops on disaster preparedness and management as part of the long-term institutional intervention on disaster.

Efforts to help those affected by Pepeng in Northern Luzon are also being finalized and coordinated with other institutions.

# Footnotes

Damayan literally means extending assistance with empathy. It is part of Filipino culture pertaining to helping one another through communal efforts without expecting something in return.