## Sheet1
Objective | Activity | Target Beneficiary | Estimated Number to reach | Means of verification | Yr 2Time Frame: 2019
QUARTER ONE (YEAR 2)
[5 empty] | MONTH 1: JANUARY | [19 empty] | MONTH 2: FEBRUARY | [19 empty] | MONTH 3: MARCH
[5 empty] | WEEK 1 |  |  |  |  | WEEK2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4
[5 empty] | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27
To reduce the risk of HIV infections among 5040 women and men of reproductive age in Makurdi and Tarka LGAs of Benue state by the end of 2015 | Dialogue meetings | MRA, WRA | 900 | Activity Report, pictures, attendance sheet etc | bar: WEEK 4 26 to WEEK 4 30; WEEK 4 23 to WEEK 4 27; WEEK 4 23 to WEEK 4 27
To reach 5040 women and men of reproductive age with HCT, care and support services in Makurdi and Tarka LGAs of Benue state by the end of 2015 | Referrals | MRA, WRA | 900 | Report, referral forms, referral registers | bar: WEEK 1 5 to WEEK 3 23; WEEK 1 2 to WEEK 3 20; WEEK 1 2 to WEEK 3 20
| HCT | MRA, WRA | 900 | Client In -Take forms, activity report | bar: WEEK 1 5 to WEEK 3 23; WEEK 1 2 to WEEK 3 20; WEEK 1 2 to WEEK 3 20
To increase utilization of care and support servicesin 8 selecected health facilities of Makurdi and Tarka LGAs of Benue state by the end of 2014 | M&E | MRA, WRA | 900 | Reports | bar: WEEK 4 24 to WEEK 4 27
To build the capacity of 60 Peer Educators who will recruit, refer and reach 2064 women and 2976 men of reproductive age with HIV prevention messages by the end of 2015 | Review meetings | MRA, WRA | 60 | Report, snapshots, attendance sheet | bar: WEEK 4 28 to WEEK 4 29; WEEK 4 26 to WEEK 4 27; WEEK 4 26 to WEEK 4 27
| Graduation of peers | MRA, WRA | 900 | Report, snapshots | bar: WEEK 4 27
| Coordination of project staff | MRA, WRA |  | PVs, Financial reports | bar: WEEK 3 23
To strengthen and support institutions for effective service delivery | Office running cost | MRA, WRA |  | PVs, Financial reports | bar: WEEK 1 5; WEEK 1 2; WEEK 1 2
QUARTER TWO (YEAR 2)
[5 empty] | MONTH 1: APRIL | [19 empty] | MONTH 2: MAY | [19 empty] | MONTH 3: JUNE
[5 empty] | WEEK 1 |  |  |  |  | WEEK2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4
[5 empty] | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 |  | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26
To reduce the risk of HIV infections among 5040 women and men of reproductive age in Makurdi and Tarka LGAs of Benue state by the end of 2015 | Dialogue meetings | MRA, WRA | 900 | Report, snapshots, attendance sheet | [14 empty] | x | x | x | x | x | bar: WEEK 4 25 to WEEK 4 29; WEEK 4 22 to WEEK 4 26
To reach 5040 women and men of reproductive age with HCT, care and support services in Makurdi and Tarka LGAs of Benue state by the end of 2015 | Referrals | MRA, WRA | 900 | Report, referral forms, referral registers | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x |  |  |  |  | x | bar: WEEK 1 4 to WEEK 3 21; WEEK 1 1 to WEEK 3 19
| HCT | MRA, WRA | 900 | Client In -Take forms, activity report | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x |  |  |  |  | x | bar: WEEK 1 4 to WEEK 3 21; WEEK 1 1 to WEEK 3 19
To increase utilization of care and support servicesin 8 selecected health facilities of Makurdi and Tarka LGAs of Benue state by the end of 2014 | M&E | MRA, WRA | 900 | Reports | bar: WEEK 4 23 to WEEK 4 26
To build the capacity of 60 Peer Educators who will recruit, refer and reach 2064 women and 2976 men of reproductive age with HIV prevention messages by the end of 2015 | Review meetings | MRA, WRA | 60 | Report, snapshots, attendance sheet | [17 empty] | x | x | bar: WEEK 4 28 to WEEK 4 29; WEEK 4 25 to WEEK 4 26
| Graduation of peers | MRA, WRA | 900 | Report, snapshots | bar: WEEK 4 26
| Coordination of project staff | MRA, WRA |  | PVs, Financial reports
To strengthen and support institutions for effective service delivery | Office running | MRA, WRA |  | PVs, Financial reports | x | bar: WEEK 1 4; WEEK 1 1
QUARTER THREE (YEAR 2)
[5 empty] | MONTH 1: JULY | [19 empty] | WEEK 1 4: MONTH 2: AUGUST; WEEK 1 1: MONTH 3: SEPTEMBER
[5 empty] | WEEK 1 |  |  |  |  | WEEK2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 4: WEEK 1; WEEK 2 11: WEEK 2; WEEK 3 18: WEEK 3; WEEK 4 25: WEEK 4; WEEK 1 1: WEEK 1; WEEK 2 8: WEEK 2; WEEK 3 15: WEEK 3; WEEK 4 22: WEEK 4
[5 empty] | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26
To reduce the risk of HIV infections among 5040 women and men of reproductive age in Makurdi and Tarka LGAs of Benue state by the end of 2015 | Dialogue meetings | MRA, WRA | 900 | Report, snapshots, attendance sheet | bar: WEEK 4 27 to WEEK 4 31; WEEK 4 24 to WEEK 4 28; WEEK 4 22 to WEEK 4 26
To reach 5040 women and men of reproductive age with HCT, care and support services in Makurdi and Tarka LGAs of Benue state by the end of 2015 | Referrals | MRA, WRA | 900 | Report, referral forms, referral registers | bar: WEEK 1 6 to WEEK 3 24; WEEK 1 3 to WEEK 3 21; WEEK 1 1 to WEEK 3 19
| HCT | MRA, WRA | 900 | Client In -Take forms, activity report | bar: WEEK 1 6 to WEEK 3 24; WEEK 1 3 to WEEK 3 21; WEEK 1 1 to WEEK 3 19
To increase utilization of care and support servicesin 8 selecected health facilities of Makurdi and Tarka LGAs of Benue state by the end of 2014 | M&E | MRA, WRA | 900 | Reports | bar: WEEK 4 23 to WEEK 4 26
To build the capacity of 60 Peer Educators who will recruit, refer and reach 2064 women and 2976 men of reproductive age with HIV prevention messages by the end of 2015 | Review meetings | MRA, WRA | 60 | Report, snapshots, attendance sheet | bar: WEEK 4 30 to WEEK 4 31; WEEK 4 27 to WEEK 4 28; WEEK 4 25 to WEEK 4 26
| Graduation of peers | MRA, WRA | 900 | Report, snapshots | bar: WEEK 4 26
| Coordination of project staff | MRA, WRA |  | PVs, Financial reports
To strengthen and support institutions for effective service delivery | Office running | MRA, WRA |  | PVs, Financial reports | bar: WEEK 1 6; WEEK 1 3; WEEK 1 1
QUARTER FOUR (YEAR 2)
[5 empty] | MONTH 1: OCTOBER | [19 empty] | MONTH 2: NOVEMBER | [19 empty] | MONTH 3: DECEMBER
[5 empty] | WEEK 1 |  |  |  |  | WEEK2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4
[5 empty] | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26
To reduce the risk of HIV infections among 5040 women and men of reproductive age in Makurdi and Tarka LGAs of Benue state by the end of 2015 | Dialogue meetings | MRA, WRA | 900 | Report, snapshots, attendance sheet | bar: WEEK 4 26 to WEEK 4 30; WEEK 4 23 to WEEK 4 27; WEEK 4 22 to WEEK 4 26
To reach 5040 women and men of reproductive age with HCT, care and support services in Makurdi and Tarka LGAs of Benue state by the end of 2015 | Referrals | MRA, WRA | 900 | Report, referral forms, referral registers | bar: WEEK 1 5 to WEEK 3 23; WEEK 1 2 to WEEK 3 20; WEEK 1 7 to WEEK 3 19
| HCT | MRA, WRA | 900 | Client In -Take forms, activity report | bar: WEEK 1 5 to WEEK 3 23; WEEK 1 2 to WEEK 3 20; WEEK 1 7 to WEEK 3 19
To increase utilization of care and support servicesin 8 selecected health facilities of Makurdi and Tarka LGAs of Benue state by the end of 2014 | M&E | MRA, WRA | 900 | Reports | bar: WEEK 4 23 to WEEK 4 26
To build the capacity of 60 Peer Educators who will recruit, refer and reach 2064 women and 2976 men of reproductive age with HIV prevention messages by the end of 2015 | Review meetings | MRA, WRA | 60 | Report, snapshots, attendance sheet | bar: WEEK 4 29 to WEEK 4 30; WEEK 4 26 to WEEK 4 27; WEEK 4 25 to WEEK 4 26
| Graduation of peers | MRA, WRA | 900 | Report, snapshots | bar: WEEK 4 26
| Coordination of project staff | MRA, WRA |  | PVs, Financial reports | bar: WEEK 3 23
To strengthen and support institutions for effective service delivery | Office running | MRA, WRA |  | PVs, Financial reports | bar: WEEK 1 5; WEEK 1 2; WEEK 1 7