## Preliminaries
NAMATAPA ZONE CDSS BILLS OF QUANTITIES
PRELIMINARIES
ITEM | DESCRIPTION | QTY | UNIT | RATE | K | t
1 | Preliminaries to construct:- a) two classroom blocks, b) Laboratory and Library block, c) Two 4 Hole Pit latrine block, d) Administration block e) 2 Hole Pit Latrine block, f) Staff House g) 1 Hole Pit Latrine block, h) External Works | 1 | sum | 16500000 | 16500000
| Preliminaries to final summary |  |  |  | 16500000
1.1

## classroom block
CLASSROOM BLOCK
SUBSTRUCTURE
ITEM | DESCRIPTION | QTY | UNIT | RATE | K
Notes: The substructure has been measured to the
top surface of the concrete floor slab
generally and will be adjusted at completion.
EXCAVATION
Excavation / Filling (provisional)
A | excavate trench from reduced level for strip footings,
| 0 to 1500mm deep. | 66 | m3 | 750 | 49500
B | excavate in pit from reduced level for pier bases,
| 0 to 1500mm deep. | 4 | m3 | 750 | 3000
C | Selected earth filling deposit, spread and
| compacted in 150mm layers around foundations | 37 | m3 | 700 | 25900
Rock excavation (provisional)
D | Extra over excavation for excavating in rock | 1 | m3 | 3500 | 3500
Disposal (provisional)
E | Surplus excavated material from excavations
transported a distance average 100 linear metres
from excavations, deposit, spread and level
| where directed on site | 29 | m3 | 750 | 21750
Hardcore filling to pass a 50mm ring all ways
F | 150mm Thick (consolidated) filling well compacted
| and rolled | 201 | m2 | 550 | 110550
Hand pack hardcore/excavation to slopes,
G | 150 mm wide | 10 | m1 | 350 | 3500
Sand blinding
H | 50mm Bed of sand on hardcore rolled to receive
| damp proof membrane | 252 | m2 | 500 | 126000
J | 125 microns (500 gauge) polythene damp proof
membrane with welted joints, lapped 150mm at
| joints and laid on blinded hardcore | 201 | m2 | 750 | 150750
Ant treatment
K | Saturate surface of hardcore and top of block
| walls with approved ant repellent | 64 | m2 | 850 | 54400
| To Collection |  |  |  | 548850
SUBSTRUCTURE
ITEM | DESCRIPTION | QTY | UNIT | RATE | Amount
A | Saturate bottom of excavated trenches with
| approved ant repellent. | 65 | m2 | 850 | 55250
Sundries
B | Allow for keeping excavations free from water | 1 | item |  | 0
C | Allow for planking and strutting to sides of
| excavations | 1 | item |  | 0
CONCRETE WORK
Plain in -situ concrete (Class 14N/mm2/40mm)
D | Strip footings | 13 | m3 | 80000 | 1040000
E | Column bases | 0 | m3
Reinforced vibrated in-situ concrete (class 21N/
mm 2/20mm)
F | 100mm thick horizontal bed, laid in bays generally
25 square metres, including formwork to
| construction joints | 201 | m2 | 9000 | 1809000
G | Extra over 100 mm thick concrete floor slab for
thickenesing a total depth of 200 mm and average
width 405 mm including extra excavation and
| hardcore filling to trimmed sloping sides. | 48 | m1 | 1500 | 72000
Plain concrete
Precast vibrated concrete (Class 20N/mm2/10mm
H | 500x500x50mm thick precast concrete paving slabs
with'brushed finish, spot bedded on sand bed
(meausred separately) including 25mm thick cement
mortar with (1:5) and jointed 20mm deep recessed
joints in cement mortar (1:5) to falls and cross falls
| not exceeding 15 degrees from horizontal | 71 | m2 | 5000 | 355000
J | Raking cutting on precast concrete paving slabs | 10 | m | 850 | 8500
Sawn formwork
K | Edge of slab, 100mm wide. | 102 | m1 | 400 | 40800
| To Collection |  |  |  | 3380550
SUBSTRUCTURE
ITEM | DESCRIPTION | QTY | UNIT | RATE | Amount
Reinforcement
A | Hard drawn mild steel fabric reinforcement (Ref
| A98) weighing 1.54kg/m2 in beds | 201 | m2 | 1850 | 371850
Movements joints
B | 19mm Thick "Flexcell" fibreboard 100mm wide
| fixed to brickwork/concrete with bitumen compound | 1 | m1 | 2650 | 2650
C | 19mm Thick"flexcell"fire board 250mm wide fixed to
| brickwork/concrete with bitumen compound | 1 | m1 | 2650 | 2650
D | Rake out edge of 12.5mm "flexcell" for a depth of
20mm and point with an approved polysulphide
| sealant | 1 | m1 | 3500 | 3500
BLOCKWORK (PROVISIONAL
Loadbearing hollow concrete blocks (Class A)
mix (1:5) and jointed in cement mortar (1:4)
E | 150 mm Thick wall. | 94 | m2 | 9500 | 893000
F | 310 mm Thick wall. | 40 | m2 | 19000 | 760000
PLASTERWORK (PROVISIONAL)
G | 15mm rendering (1:4) cement and sand,
finished with a wood float
| Brick/concrete walls | 30 | m2 | 1800 | 54000
PAINTING AND DECORATING (PROVISIONAL)
H | Prepare and apply two coats of black'bituminous
| paint on'Rendered walls | 30 | m2 | 1500 | 45000
| To Collection |  |  |  | 2132650
COLLECTION
| Page No. CR/1 |  |  |  | 548850
| Page No. CR/2 |  |  |  | 3380550
| Page No. CR/3 |  |  |  | 2132650
| SUBSTRUCTURE TO SUMMARY |  |  |  | 6062050
ROOF
ITEM | DESCRIPTION | QTY | UNIT | RATE | Amount
CORRUGATED OR TROUGHED SHEET ROOFING
28 Gauge galvanised steel; inverted box rib (IBR)
roof sheeting 0.6mm thick; single lengths; no
horizontal joints chromadeck factory finish to
underside.
A | Coverings; fixing to timber purlins at 1500mm
general spacing with galvanised drive screws with
covers and water proof washers; one flute side
| laps. | 294 | m2 | 12500 | 3675000
B | 28 Gauge IBR cranked capping 450 mm girth fixed
| to IBR and roof timbers. | 27 | m | 4000 | 108000
C | Serrated eaves closure piece pop riveted at 343 mm
| centres to roof sheets. | 54 | m | 3500 | 189000
Roof trusses
Framed sawn softwood timber roof trusses fabricated
at ground level and hoisted approximately 3650mm
above ground level
Treated sawn softwood
D | 50 x 75mm Purlins | 280 | m | 1000 | 280000
E | 50 x 100 mm Wall plate and fixing to blockwork with
| tying wire. (measured separately) | 56 | m | 1500 | 84000
F | 50 x 150mm Rafters | 412 | m | 2000 | 824000
G | 50 x 100 mm Struts | 258 | m | 1500 | 387000
H | 50 x 100 mm Chord | 213 | m | 1500 | 319500
J | 50 x 150 mm Beam | 152 | m | 2000 | 304000
K | 40 x 225 mm Wrot softwood fascia board and fixing | 54 | m | 3000 | 162000
L | 40 x 225 mm Wrot softwood barge board and fixing | 21 | m | 3000 | 63000
Metal work
M | 3 mm Diameter galvanised tying wire 450 mm girth
| tied round ring beam and truss. | 38 | No. | 1250 | 47500
N | 40 x 40 x 3mm Angle 250mm long | 4 | No. | 6500 | 26000
| To Collection |  |  |  | 6469000
ROOF
ITEM | DESCRIPTION | QTY | UNIT | RATE | Amount
A | 12 mm Diameter mild steel bolt 200 mm long
including nut and round washer 40mm diameter
| and 3mm thick washer | 12 | No | 4500 | 54000
B | M16 x 210mm mild steel bolts complete with nut and washers
| washer. | 988 | No | 1500 | 1482000
Sundries
20mm Shutterply fixed on both sides of rafter as per Engineers drawing No
C | 20x300mm wide | 76 | No | 250 | 19000
D | 20x650mm wide | 38 | No | 550 | 20900
Painting
Prepare and apply primer, one undercoat and two coats gloss on general wood surfaces
E | Over 300mm wide | 20 | m2 | 2400 | 48000
F | 200 - 300mm wide | 564 | m1 | 720 | 406080
G | 100 - 200mm wide | 538 | m1 | 480 | 258240
| To Collection |  |  |  | 2288220
COLLECTION
| Page No. CR/4 |  |  |  | 6469000
| Page No. CR/5 |  |  |  | 2288220
| ROOF TO SUMMARY |  |  |  | 8757220
EXTERNAL AND INTERNAL WALLS
ITEM | DESCRIPTION | Qty | UNIT | RATE | Amount
CONCRETE WORK
Reinforced vibRATEd in-situ concrete
(Class 21N/mm2/ 20mm)
A | Ring Beam | 3 | m3 | 90000 | 270000
Sawn formwork
B | Sides and soffit of beam | 70 | m2 | 4000 | 280000
Reinforcement
C | 6mm diameter mild steel rod reinforcement | 84 | kg | 1500 | 126000
D | 10mm Diameter deformed high yield mild steel rod
| Reinforcement | 255 | kg | 1500 | 382500
Movement joints
E | 12mm thick "flexile" fibre board 290mm wide fixed to
| SS Blocks/concrete with bitumen compound | 1 | m | 1700 | 1700
F | Rake out edge of 12mm thick "flexcell" for a depth of
| 25mm and point with an approved polysulphide sealant | 1 | m | 3500 | 3500
BLOCKWORK
Soil Stabilsed Blocks built with cement and
sand mortar (1:6)
G | 140 mm Thick wall of Soil Stabilised Blocks mix
(1:12) cement and soil or as instructed depending on
soil type on site with and including "Bickforce"
| reinforcement layer every fourth course. | 107 | m2 | 10500 | 1123500
H | 290 mm Thick ditto. | 106 | m2 | 16500 | 1749000
J | 140 mm Thick wall of Soil Stabilised Blocks mix (1:8)
| cement and soil solidier course. | 57 | m1 | 1500 | 85500
K | 290 mm Thick wall ditto. | 45 | m1 | 3000 | 135000
L | 140 mm Thick wall to door openings and windows ditto | 31 | m2 | 10500 | 325500
M | 290 mm Thick wall ditto. | 32 | m2 | 16500 | 528000
Fairface Work
N | Extra over fair face for pointing blockwork. | 252 | m2 | 1500 | 378000
O | Prepare and apply two coats brick sealer to fair
| blockwork. | 86 | m2 | 1500 | 129000
| To Collection |  |  |  | 5517200
EXTERNAL AND INTERNAL WALLS
ITEM | DESCRIPTION | Qty | UNIT | RATE | Amount
Damp proof course
A | 3 ply malthoid damp proof course, 140mm wide, laid
| under brickwork | 127 | m | 250 | 31750
B | Ditto 290 mm wide , laid under half brick walls | 60 | m | 500 | 30000
Sundries
C | eaves filling 375mm high; splayed; fitting to
| underside IBR | 54 | m | 2450 | 132300
PVC air vents; building in
D | 110mm diameter x 170mm long; mosquito gauze
| wire fixed to one end; | 28 | No | 765 | 21420
E | Form cavities for brick air vents | 28 | No | 250 | 7000
| To Collection |  |  |  | 222470
COLLECTION
| Page No. CR/6 |  |  |  | 5517200
| Page No. CR/7 |  |  |  | 222470
| EXTERNAL & INTERNAL WALLS TO SUMMARY |  |  |  | 5739670
WINDOWS AND DOORS
ITEM | DESCRIPTION | Qty | UNIT | RATE | Amount
CONCRETE WORK
Precast vibRATEd concrete (Class 21N/mm2/10mm)
bedded, jointed and pointed in mortar (1:3)
A | 100 x 190 x 1110mm long sill, splay rebated once grooved
and two edges chamfered, finished fair on all exposed
| surfaces and built into blockwork | 28 | No | 2000 | 56000
B | 210x240x80 mm Trapezoidal block for door stop built into
| 210 x 240 x 80mm trapezoidal block for door stop built into blockwork bedding in cement mortar 1:6 | 2 | No | 500 | 1000
METAL WORK
C | Solid rolled mild steel metal window prefabricated with 20 x 4mm mild steel bars; type WAD1 size 910 x 1200mm high | 28 | No. | 55000 | 1540000
D | Expamet expanded metal welded to metal windows as
| burglar proof. | 4.4 | m2 | 11500 | 50600
E | Brass sliding stays and fixing to windows. | 56 | No. | 3500 | 196000
DOORS
F | 920 x 2070 x 40mm Framed , ledged , braced and
battened door comprising of 40 x 120 mm top,middle
bottom rails and stiles,24 x 100 mm ledging and bracing
| 16 x 100 mm boarding tongued and grooved | 4 | No. | 85000 | 340000
G | Pressed steel door frame for 140 mm Soil Stabilised
Block wall door opening 1000 x 2100mm with and
| including 125 mm steel hinges welded on the frame. | 4 | No. | 60000 | 240000
(Accessible to Physical Challnged)
IRONMONGERY
H | Three lever mortice lock and rose furniture | 2 | No. | 12500 | 25000
J | Two lever mortice lock and rose furniture | 2 | No | 10000 | 20000
K | Rubber door stop fixed to concrete floor | 2 | No. | 2000 | 4000
L | Ditto fixed to wall. | 2 | No. | 2000 | 4000
M | 125 mm Butt hinges fixed with 9 no. counter sunk screws | 4 | No | 1895 | 7580
GLAZING
Clear sheet glass
N | 4mm Thick clear plate glass and glazing to metal windows with and including putty | 30 | m2 | 8500 | 255000
PAINTING AND DECORATING
Prepare, knot, stop, seal and apply two coats of
polyurethane on
| Hardwood doors | 14 | m2 | 1500 | 21000
| To Collection |  |  |  | 2760180
WINDOWS AND DOORS
ITEM | DESCRIPTION | Qty | UNIT | RATE | Amount
Prepare and apply one undercoat and two
finishing coats of gloss paint on metal surfaces
A | Surfaces over 300mm girth. (measured overall) | 61 | m2 | 2400 | 146400
B | Surfaces over 200 mm but not exceeding 300 mm girth | 6 | m | 720 | 4320
| To Collection |  |  |  | 150720
COLLECTION
| Page No. CR/8 |  |  |  | 2760180
| Page No. CR/9 |  |  |  | 150720
| WINDOWS AND DOORS TO SUMMARY |  |  |  | 2910900
WALL FINISHES
ITEM | DESCRIPTION | Qty | UNIT | RATE | Amount
INTERNAL
15mm Rendering (1:4) cement and sand finished
with a final coat of line putty, steel trowelled
A | Block/concrete walls | 184 | m2 | 1800 | 331200
B | Ditto, in narrow widths | 57 | m2 | 1800 | 102600
PAINTING AND DECORATING
Prepare and apply one water thinned coat and
two coats of internal quality PVA on
C | Rendered walls | 184 | m2 | 1800 | 331200
| WALL FINISHES TO SUMMARY |  |  |  | 765000
FLOOR FINISHES
ITEM | DESCRIPTION | Qty | Unit | RATE | Amount
PLASTERWORK
1:3 cement and sand screed finished with a sand
screed finished with a steel trowel
A | 25mm thick to concrete slabs | 202 | m2 | 3000 | 606000
B | 100mm high skirting with small cove at bottom and "V"
| joint to junction of rendering | 91 | m | 350 | 31850
C | Wash and rub down; clean and apply two coats wax polish to floors | 202 | m2 | 900 | 181800
| FLOOR FINISHES TO SUMMARY |  |  |  | 819650
FITTINGS AND FURNISHING
ITEM | DESCRIPTION | Qty | Unit | RATE | Amount
Pinboards
2No 2400x1200mm CHALKBOARDS
4No 745X1200mm PINBOARDS
4No 600X1200mm PINBOARDS
GENERAL JOINERY
Wrot hardwood
A | 25x50mm hardwood frame mitred at corners plugging | 15 | m | 1700 | 25500
B | 35x50mm;rebuted; plugging | 2 | m | 2400 | 4800
C | Ditto twice rebuted | 2 | m | 2400 | 4800
D | 10mm thick ivory faced soft board | 12 | m2 | 6500 | 78000
Chalk rails
E | 90x50mm;grooved | 7 | m | 6000 | 42000
Chalkboard
F | 15mm cement and sand in 1:4 mix | 9 | m2 | 2000 | 18000
SHELVING
2No 340x3740x2100mmHIGH
GENERAL JOINERY
Wrot softwood
G | 50 x 50mm styles | 36 | m | 1000 | 36000
H | 50 x 50mm framing | 72 | m | 1000 | 72000
Divisions
J | 20mm thick blockboard | 4 | m2 | 14500 | 58000
Shelves
K | 20mm thick blockboard; lipped all round | 4 | m2 | 14500 | 58000
Doors
20mm Blockboard doors having 20x20 mm hardwood
lipping all round
| 450x400mm wide | 8 | No. | 3000 | 24000
CUPBOARDS
1No 600x745x1810mm HIGH
Softwood; wrot
| 50x50mm posts | 9 | m | 1000 | 9000
| 40x50mm posts;plugged | 20 | m | 950 | 19000
| 40x50mm rails | 13 | m | 950 | 12350
| 40x50mm rails plugged | 7 | m | 950 | 6650
| To Collection |  |  |  | 468100
FITTINGS AND FURNISHING
ITEM | DESCRIPTION | Qty | Unit | RATE | Amount
Divisions
A | 20mm thick blockboard | 2 | m2 | 14500 | 29000
shelves
B | 20mm thick blockboard; lipped all round | 2 | m2 | 15500 | 31000
Doors
C | 20 x 730 x 500mm blockboard door lipped all round | 4 | No. | 1500 | 6000
PAINTING AND DECORATING
D | Prepare and apply two coats ceiling white paint | 12 | m2 | 1600 | 19200
Prepare, knot, stop, seal and apply two coats of
polyurethane on
E | Hardwood frame; 0 - 100mm girth | 30 | m | 200 | 6000
F | Prepare and apply one thinned coat, two coats
| blackboard paint on chalkboard | 26 | m2 | 1600 | 41600
IRONMONGERY
Union fittings; miscellaneous ironmongery
To hardwood or the like
A | piano butt hinges; brass; 35mm(10No lengths) | 7 | m | 3500 | 24500
B | cupboard ball catch; zinc plated steel; double nylon
| roller, 19 x 31.5mm | 5 | No | 2400 | 12000
C | 75mm chromium plated barrel bolts | 2 | No | 1400 | 2800
D | Cupboard lock reference 4137;52.5 | 4 | No | 4500 | 18000
SIGNAGE
E | Provide perspex name plates to the School Blocks
average size of letters being 50 mm to the approval of
the Project Architect. The lettering to be white on blue
background to read as: -
CLASSROOM (1-4)
STORE ROOM
F | Provide plastic key tags. | 12 | No. | 3500 | 42000
| To Collection |  |  |  | 232100
COLLECTION
Pages
| CR/12 |  |  |  | 468100
| CR/13 |  |  |  | 232100
| FITTINGS AND FURNISHING TO SUMMARY |  |  |  | 700200
SOLAR ELECTRICAL
ITEM | DESCRIPTION | Qty | Unit | RATE | Amount
PRIME COST SUMS
Allow the following Prime Cost Sums;
A | Solar Electrical | 1 | Item | 2500000 | 2500000
B | Main Contractor's Profit | % |  |  | 750000
C | Add for Attendance |  | Item |  | 243750
| To collection |  |  |  | 3493750
| SOLAR ELECTRICAL TO SUMMARY |  |  |  | 3493750
CLASSROOM BLOCK SUMMARY
| SUBSTRUCTURE | CR/3 |  |  | 6062050
| ROOF | CR/5 |  |  | 8757220
| EXTERNAL AND INTERNAL WALLS | CR/7 |  |  | 5739670
| WINDOWS AND DOORS | CR/9 |  |  | 2910900
| WALL FINISHES | CR/10 |  |  | 765000
| FLOOR FINISHES | CR/11 |  |  | 819650
| FITTINGS AND FURNISHINGS | CR/14 |  |  | 700200
| SOLAR ELECTRICAL | CR/15 |  |  | 3493750
| CLASSROOM BLOCK TO SUMMARY |  |  |  | 29248440

## Lab & Library block
LABORATORY AND LIBRARY BLOCK
SUBSTRUCTURE
ITEM | DESCRIPTION | QTY | UNIT | RATE | K
Notes: The substructure has been measured to the
top surface of the concrete floor slab
generally and will be adjusted at completion.
EXCAVATION
Excavation / Filling (provisional)
A | excavate trench from reduced level for strip footings,
| 0 to 1500mm deep. | 95 | m3 | 750 | 71250
B | Selected earth filling deposit, spread and
| compacted in 150mm layers around foundations | 45 | m3 | 700 | 31500
Rock excavation (provisional)
C | Extra over excavation for excavating in rock | 1 | m3 | 3500 | 3500
Disposal (provisional)
D | Surplus excavated material from excavations
transported a distance average 100 linear metres
from excavations, deposit, spread and level
| where directed on site | 50 | m3 | 750 | 37500
Hardcore filling to pass a 50mm ring all ways
E | 150mm Thick (consolidated) filling well compacted
| and rolled | 285 | m2 | 550 | 156750
Hand pack hardcore/excavation to slopes,
F | 150 mm wide | 25 | m1 | 350 | 8750
Sand blinding
G | 50mm Bed of sand on hardcore rolled to receive
| damp proof membrane | 300 | m2 | 500 | 150000
H | 125 microns (500 gauge) polythene damp proof
membrane with welted joints, lapped 150mm at
| joints and laid on blinded hardcore | 285 | m2 | 750 | 213750
Ant treatment
J | Saturate surface of hardcore and top of brick
| walls with approved ant repellent | 285 | m2 | 850 | 242250
K | Saturate bottom of excavated trenches with
| approved ant repellent. | 137 | m2 | 850 | 116450
| To Collection |  |  |  | 1031700
SUBSTRUCTURE
ITEM | DESCRIPTION | QTY | UNIT | RATE | K
Sundries
A | Allow for keeping excavations free from water | 1 | item |  | 0
B | Allow for planking and strutting to sides of
| excavations | 1 | item |  | 0
CONCRETE WORK
Plain in -situ concrete (Class 14N/mm2/40mm)
C | Strip footings | 15 | m3 | 80000 | 1200000
Reinforced vibrated in-situ concrete (class 21N/
mm 2/20mm)
D | 100mm thick horizontal bed, laid in bays generally
25 square metres, including formwork to
| construction joints | 288 | m2 | 9000 | 2592000
Plain concrete
Precast vibrated concrete (Class 20N/mm2/10mm
E | 500x500x50mm thick precast concrete paving slabs
with'brushed finish, spot bedded on sand bed
(meausred separately) including 25mm thick cement
mortar with (1:5) and jointed 20mm deep recessed
joints in cement mortar (1:5) to falls and cross falls
| not exceeding 15 degrees from horizontal | 91 | m2 | 5000 | 455000
F | Raking cutting on precast concrete paving slabs | 15 | m | 850 | 12750
Sawn formwork
G | Steps to strip footings (provisional) | 1 | m2 | 4000 | 4000
H | Edge of slab, 100mm wide. | 123 | m1 | 400 | 49200
Reinforcement
J | Hard drawn mild steel fabric reinforcement (Ref
| A98) weighing 1.54kg/m2 in beds | 288 | m2 | 1850 | 532800
Movements joints
K | 19mm Thick "Flexcell" fibreboard 100mm wide
| fixed to brickwork/concrete with bitumen compound | 1 | m1 | 2650 | 2650
| To Collection |  |  |  | 4848400
SUBSTRUCTURE
ITEM | DESCRIPTION | QTY | UNIT | RATE | K
BLOCKWORK (PROVISIONAL
Loadbearing hollow concrete blocks (Class A)
mix (1:5) and jointed in cement mortar (1:4)
A | 150 mm Thick wall. | 52 | m2 | 9500 | 494000
B | 310 mm Thick wall. | 59 | m2 | 19000 | 1121000
PLASTERWORK (PROVISIONAL)
C | 15mm rendering (1:4) cement and sand,
finiLLed with a wood float
| Brick/concrete walls | 112 | m2 | 1800 | 201600
PAINTING AND DECORATING (PROVISIONAL)
D | Prepare and apply two coats of black
| bituminous paint on'rendered walls | 112 | m2 | 1500 | 168000
| To Collection |  |  |  | 1984600
COLLECTION
| Page No. LL/1 |  |  |  | 1031700
| Page No. LL/2 |  |  |  | 4848400
| Page No. LL/3 |  |  |  | 1984600
| SUBSTRUCTURE TO SUMMARY |  |  |  | 7864700
ROOF
ITEM | DESCRIPTION | QTY | UNIT | RATE | K
CORRUGATED OR TROUGHED SHEET ROOFING
28 gg Galvanised steel; inverted box rib(IBR) roof sheeting;
,0.6mm thick; single lengths; no horizontal joints
chromadeck factory finish to underside
Coverings; fixing to timber purlins at 1500mm general spacing with galvanised drive srews with covers and wateproof washers; one flute side laps
A | sloping not exceeding 50 degrees from horizontal | 403 | m2 | 12500 | 5037500
Accessories; fixing with galvanised steel drive screws
B | cappings; 1000mm girth, cranked 30degrees to
| ridges | 33 | m | 4000 | 132000
C | Eaves flashings; twice bent; welted and pop revetted
| at 343mm centres to brackets; 0.71 x 100mm girth | 66 | m | 3500 | 231000
Roof trusses
Framed sawn softwood timber roof trusses fabricated
at ground level and hoisted approximately 3650mm
above ground level
Treated sawn softwood
D | 50 x 75mm Purlins | 397 | m | 1000 | 397000
E | 50 X 100 mm Wall plateand fixing to blockwork with
| tying wire. (measured separately) | 64 | m | 1500 | 96000
F | 50x100 internals of truss | 437 | m | 1500 | 655500
G | 50 x 150mm Top,bottom of truss | 965 | m | 2000 | 1930000
H | 50 x 150mm beam | 22 | m | 2000 | 44000
J | 38 x 255 mm Wrot softwood fascia board and fixing | 66 | m | 3000 | 198000
K | 25 x 250 mm Wrot softwood barge board and fixing | 25 | m | 3000 | 75000
METALWORK
L | Galvanised iron straps;3x1600mm,built into blockwork
| and spiked to timber | 46 | No. | 1250 | 57500
M | M16 Bolts complete with nuts and washers | 531 | No. | 1500 | 796500
| To Collection |  |  |  | 9650000
ROOF
ITEM | DESCRIPTION | QTY | UNIT | RATE | K
A | M12 Bolts complete with nuts and washers | 30 | No. | 1250 | 37500
B | 40x40x3L Angle 250mm long | 15 | No. | 6500 | 97500
Shutterply (used as gusset plates)
C | 500x200x20mm thick | 30 | No. | 400 | 12000
D | 230x190x20mm ditto | 30 | No. | 300 | 9000
E | 350x600x20mm ditto | 30 | No. | 600 | 18000
F | 500x200x20mm ditto | 16 | No. | 400 | 6400
G | 600x350x20mm ditto | 32 | No. | 600 | 19200
H | 50 X 1.60 mm Hoop iron 380 mm in girth one end
cast in concrete ring beam and the other fixed to
| softwood rafter with and including wire nails. | 24 | No. | 985 | 23640
Painting
Prepare and apply primer, one undercoat and two coats gloss on general wood surfaces
J | Over 300mm wide | 1 | m2 | 2400 | 2400
K | 200 - 300mm wide | 1 | m1 | 720 | 720
L | 100 - 200mm wide | 247 | m1 | 480 | 118560
M | 0 - 100mm wide | 32 | m1 | 240 | 7680
| To Collection |  |  |  | 352600
COLLECTION
| Page No. LL/4 |  |  |  | 9650000
| Page No. LL/5 |  |  |  | 352600
| ROOF TO SUMMARY |  |  |  | 10002600
EXTERNAL AND INTERNAL WALLS
ITEM | DESCRIPTION | Qty | UNIT | Rate | K
CONCRETE WORK
Reinforced vibrated in-situ concrete
(Class 21N/mm2/ 20mm)
A | Ring Beam | 4 | m3 | 90000 | 360000
Sawn formwork
B | Sides and soffit of beam | 305 | m2 | 4000 | 1220000
Reinforcement
C | 6mm diameter mild steel rod reinforcement | 141 | kg | 1500 | 211500
D | 10mm Diameter deformed high yield mild sTeel rod
| Reinforcement | 282 | kg | 1500 | 423000
Movement joints
E | 12mm thick "flexell" fibre board 290mm wide fixed to
| SS Blocks/concrete with bitumen compound | 1 | m | 3500 | 3500
BLOCKWORK
Soil Stabilsed Blocks built with cement and
sand mortar (1:6)
F | 140 mm Thick wall of Soil Stabilised Blocks mix
(1:12) cement and soil or as instructed depending on
soil type on site with and including "Bickforce"
| reinforcement layer every fourth course. | 154 | m2 | 10500 | 1617000
G | 290 mm Thick ditto. | 127 | m2 | 16500 | 2095500
H | 140 mm Thick wall of Soil Stabilised Blocks mix (1:8)
| cement and soil solidier course. | 76 | m | 1500 | 114000
J | 290 mm Thick wall ditto. | 58 | m | 3000 | 174000
K | 140 mm Thick wall to door openings and windows ditto | 12 | m2 | 10500 | 126000
L | 290 mm Thick wall ditto. | 8 | m2 | 16500 | 132000
Fairface Work
M | Extra over fair face for pointing blockwork. | 290 | m2 | 1500 | 435000
Damp proof course
N | 3 ply malthoid damp proof course, 140mm wide, laid
| under brickwork | 76 | m | 250 | 19000
O | Ditto 290 mm wide , laid under half brick walls | 58 | m | 500 | 29000
| To Collection |  |  |  | 6959500
EXTERNAL AND INTERNAL WALLS
ITEM | DESCRIPTION | Qty | UNIT | Rate | K
Sundries
PVC air vents; building in
A | 110mm diameter x 170mm long; mosquito gauze
| wire fixed to one end; | 30 | No | 765 | 22950
| To Collection |  |  |  | 22950
COLLECTION
| Page No. LL/6 |  |  |  | 6959500
| Page No. LL/7 |  |  |  | 22950
| EXTERNAL & INTERNAL WALLS TO SUMMARY |  |  |  | 6982450
WINDOWS AND DOORS
ITEM | DESCRIPTION | Qty | UNIT | Rate | K
CONCRETE WORK
Precast vibrated concrete (Class 21N/mm2/10mm)
bedded, jointed and pointed in mortar (1:3)
A | 200 x 100 x 910mm long sill, splay rebated once grooved
and two edges chamfered, finiLLed fair on all exposed
| surfaces and built into blockwork | 30 | No | 2000 | 60000
B | 210 x 240 x 80mm trapezoidal block for door stop built into blockwork bedding in cement mortar 1:6 | 2 | No | 450 | 900
METAL WORK
C | Solid rolled mild steel metal window prefabricated with 20 x 4mm mild steel bars; type WLB1 size 910 x 1200mm high | 30 | No. | 55000 | 1650000
D | Expamet expanded metal welded to metal windows as
| burglar proof. | 31 | m2 | 11500 | 356500
E | Brass peg stays and fixing to windows. | 90 | No. | 3500 | 315000
F | Brass handles | 90 | No | 3500 | 315000
DOORS
G | 920x2100x40 mm Framed , ledged , braced and
battened door comprising of 40x120 mm top,middle
bottom rails and stiles,24x100 mm ledging and bracing
| 16x100 mm boarding tongued and grooved | 5 | No. | 85000 | 425000
H | Pressed steel door frame for 140 mm Soil Stabilised
Block wall door opening 1000 x 2100mm with and
| including 100 mm sTeel hinges welded on the frame. | 6 | No. | 60000 | 360000
(Accessible to Physical Challnged)
J | 1000 X 2070 mm Lasec's transformer metal door with
| vents | 1 | No. | 125000 | 125000
(Accessible to Physical Challnged)
K | Metal grill overall size 1100x22000 mm comprising of
30x30 mm RHS main frame and 30x30 mm
intermediates, the vertical members spaced at 156 mm
centres and the horizontals spaced at 428 mm centres
welded together including 2 no. hinges and 2 no. hooks
| for padlocks. | 5 | No. | 165000 | 825000
IRONMONGERY
L | Three lever mortice lock and rose furniture | 3 | No. | 12500 | 37500
M | Two lever mortice lock and rose furniture | 2 | No | 10000 | 20000
N | Rubber door stop fixed to concrete floor | 3 | No. | 2000 | 6000
O | Ditto fixed to wall. | 2 | No. | 2000 | 4000
| 100 mm Wide Union padlock | 10 | No. | 8500 | 85000
| To Collection |  |  |  | 4584900
WINDOWS AND DOORS
ITEM | DESCRIPTION | Qty | UNIT | Rate | K
GLAZING
Clear sheet glass
M | 4mm thick clear plate glass and glazing to metal windows with and including putty | 33 | m2 | 8500 | 280500
PAINTING AND DECORATING
Prepare, knot, stop, seal and apply two coats of
polyurethane on
A | Hardwood doors | 11 | m2 | 1500 | 16500
Prepare and apply one undercoat and two
finishing coats of gloss paint on metal surfaces
B | Surfaces over 300mm girth. | 65 | m2 | 2400 | 156000
C | Surfaces over 200 mm but not exceeding 300 mm girth | 30 | m | 720 | 21600
| To Collection |  |  |  | 474600
COLLECTION
| Page No. LL/8 |  |  |  | 4584900
| Page No. LL/9 |  |  |  | 474600
| WINDOWS AND DOORS TO SUMMARY |  |  |  | 5059500
WALL FINISHES
ITEM | DESCRIPTION | Qty | UNIT | Rate | K
INTERNAL
15mm Rendering (1:4) cement and sand finished
with a final coat of line putty, steel trowelled
A | Block/concrete walls | 413 | m2 | 1800 | 743400
B | Ditto, in narrow widths | 99 | m | 200 | 19800
PAINTING AND DECORATING
Prepare and apply one water thinned coat and
two coats of internal quality PVA on
C | Rendered walls | 413 | m2 | 1800 | 743400
D | Ditto, in narrow widths | 99 | m | 200 | 19800
| WALL FINISHES TO SUMMARY |  |  |  | 1526400
FLOOR FINISHES
ITEM | DESCRIPTION | Qty | Unit | Rate | K
PLASTERWORK
1:3 cement and sand screed finishes with a sand
screed finishes with a Steel trowel
A | 25mm thick to concrete slabs | 265 | m2 | 3000 | 795000
B | 100mm high skirting with small cove at bottom and "V"
| joint to junction of rendering | 151 | m | 350 | 52850
C | Wash and rub down; clean and apply two coats wax polish to floors | 265 | m2 | 900 | 238500
| FLOOR FINISHES TO SUMMARY |  |  |  | 1086350
SANITARY INSTALLATION (PROVISIONAL)
ITEM | DESCRIPTION | QTY | UNIT | RATE | K
Fittings
A | Armitage Shanks' Modula white glazed fire clay laboratory
sink (305 x 405) complete with integral overflow, 38mm
diameter hole for waste outlet and loose lift out grid, 125mm
steel tube overflow and 4No. 7216074 fixing clips, fix
| and seal to timber top | 17 | No | 72500 | 1232500
Gas Bottles
B | 3Kg, 200mm high 'Cadac' gas bottle complete with
| regulator and 500mm length of rubber hose fitted | 5 | No | 91500 | 457500
Taps
C | '15mm Diameter chronium plated; pillar tap and joint to
| pipework | 1 | No | 16500 | 16500
D | 15mm Diameter bench mounted 'Marklab 8500AC
laboratory water tap with 150mm projection and 220mm
| bench to nozzle height, and jint to pipework | 16 | No | 55000 | 880000
E | 10mm Diameter Marklab 87043 PG lever operated double
| outlet bench gas cock and joint to pipework | 15 | No | 65800 | 987000
Connector pipes
F | 12mm Diameter copper connector, 300mm girth, bent
as required, including joint to union of fitting and
| galvanised mild steel pipe with gunmetal connector | 17 | No | 6500 | 110500
Testing
G | Allow to test the foregoing sanitary fittings as described | 1 | item | 85000 | 85000
Soil, waste and vent pipework; BS 4514 pipes and fittings
PVC and Upvc
Pipes; solvent welded joints in the running length; fiixing
with standard slips to background requiring plugging
H | 40mm; in chases | 2 | m | 800 | 1600
J | 50mm; in trenches | 3 | m | 850 | 2550
K | Extra; swep bends 201.50.92 | 1 | No | 2500 | 2500
L | Extra; trap outlet adaptor 215.40.125 | 1 | No | 6500 | 6500
M | Extra; socket reducer 224.50.40 | 1 | No | 6500 | 6500
| To collection |  |  |  | 3788650
SANITARY INSTALLATION (PROVISIONAL)
ITEM | DESCRIPTION | QTY | UNIT | RATE | K
Traps
A | 'S' trap 632.125.40 | 1 | No | 18500 | 18500
Vulcathene pipework and fittings; to manufacturer's
specifications
Pipes; fittings; fixing to walls with standard clips to backgrounds
requiring plugging
B | 38mm | 6 | m | 3600 | 21600
C | 50mm; in chases | 10 | m | 4500 | 45000
D | 50mm; in chases | 15 | m | 4500 | 67500
E | 76mm; in trenches | 45 | m | 6000 | 270000
F | Extra; 38mm x 135 degrees bend (W191) | 20 | No | 5000 | 100000
G | Extra; 50mm x 45 degrees bend (W192) | 10 | No | 3600 | 36000
H | Extra; 50mm x 135 degrees bend (W192) | 12 | No | 6000 | 72000
J | Extra; 76mm x 45 degrees bend (W193) | 14 | No | 4000 | 56000
K | Extra 50mm x 45degrees single 'Y' junction (W372) | 15 | No | 4000 | 60000
L | Extra; 50mm x 45degrees double 'Y' junction (382) | 6 | 4No | 4000 | 24000
M | Extra; 76mm x 45degrees single 'Y' junction (W373) | 12 | No | 4000 | 48000
N | Extra; 51 x 38mm reducer (W3921) | 29 | No | 4000 | 116000
O | Extra; 76 x 50mm blanking off plug | 12 | No | 3000 | 36000
P | Extra; 50mm blanking off plug | 23 | No | 2400 | 55200
Q | Extra; 76mm rodding eye access (W24) | 8 | 1No | 2400 | 19200
Gullies
R | Vulcathene 4.5L gully trap; reference W810 set up;
excavation, concrete bed surround and connect to
| pipework | 5 | No | 40000 | 200000
| To collection |  |  |  | 1245000
SANITARY INSTALLATION (PROVISIONAL)
ITEM | DESCRIPTION | QTY | UNIT | RATE | K
Wastes
A | Vulcathene 38mm Waste Cat No. 504; removable plug
| Cat No. 506 and standing waste tube Cat No. 507 | 17 | No | 12500 | 212500
Traps
B | Vulcathene 38mm anti siphone bottle trap Cat No. 561;
| 38mm loose nut coupling | 15 | No | 20000 | 300000
BUILDER'S WORK
Excavation
Excavating trench for amall diameter pipe including backfill
and disposal; average 500mm deep
C | not exceeding 1.5m deep | 10 | m | 950 | 9500
Excavating trench for large diameter pipe including backfill
and disposal; average 500mm deep
950
D | not exceeding 1.5mm deep | 45 | m |  | 0
Sleeved holes for pipes or the like
E | one brick wall; small | 5 | No | 500 | 2500
F | one and half brick wall; large | 5 | No | 750 | 3750
G | one and half brick wall angled; large | 2 | No | 800 | 1600
Testing
H | Allow for testing for water-tightness, air-tightness and
| perfomance; one stage prior to the final test | 1 | item. | 85000 | 85000
| To collection |  |  |  | 614850
COLLECTION
| Page No. LL/12 |  |  |  | 3788650
| Page No. LL/13 |  |  |  | 1245000
| Page No. LL/14 |  |  |  | 614850
| SANITARY INSTALLATION TO SUMMARY |  |  |  | 5648500
FITTINGS AND FURNISHINGS
ITEM | DESCRIPTION | Qty | Unit | Rate | K
LIBRARY JOINERY
COUNTER:
BLOCK WORK
A | 140 mm Thick soil stabilised block mix cement and
soil (1:12) built to stretcher bond with cement and
| sand mortar (1:6) ; plinth | 2 | m2 | 10500 | 21000
B | 15mm screed; 1:3 cement and sand screed finished
| with a steel trowel to blocks | 1 | m2 | 1800 | 1800
GENERAL JOINERY
Wrot softwood
C | 50 x 50mm plugging | 7 | m | 750 | 5250
D | 50 x 50mm framing | 6 | m | 750 | 4500
E | 45x45mm framing | 2 | m | 700 | 1400
F | 45x45mm plugging | 6 | m | 700 | 4200
G | 20 x 410x 400mm long blockboard drawer front, 25 x 145 x 450mm blockboard drawer sides and 25 x 145 x 395mm drawer back; 12mm plywood bottom complete with runners and guides | 6 | No | 7500 | 45000
H | 20mm blockboard work top; lipped all round | 2 | m2 | 13600 | 27200
J | 25mm blockboard shelves | 1 | m2 | 17000 | 17000
K | 20mm x 636 x 745mm high; ditto | 2 | No | 6500 | 13000
PAINTING AND DECORATING
L | Prepare and apply primer, undercoat and two finishing coats velvaglo paint | 3 | m2 | 1800 | 5400
coats velvaglo paint.
WALL SHELVING
2No 350x2010x8110mm long
2No 350x2010x5250mm long
BLOCK WORK
M | 140 mm Thick soil stabilised block mix cement and
soil (1:12) built to stretcher bond with cement and
| sand mortar (1:6) ; plinth | 9 | m2 | 10500 | 94500
| To Colletion |  |  |  | 240250
FITTINGS AND FURNISHINGS
ITEM | DESCRIPTION | Qty | Unit | Rate | K
A | 15mm screed; 1:3 cement and sand screed finished
| with a steel trowel to blocks | 5 | m2 | 1800 | 9000
GENERAL JOINERY
Wrot softwood
B | 50 x 50mm plugging | 80 | m | 750 | 60000
C | 50 x 50mm framing | 269 | m | 750 | 201750
D | 75X20mm blockboard shelves; lipped all round | 255 | m2 | 13600 | 3468000
E | 25X25 mm supports | 25 | m | 450 | 11250
PAINTING
F | Prepare and apply primer, undercoat and two finishing coats velvaglo paint 100-200 girth | 40 | m | 360 | 14400
CABINET 1No.
1No 350x690x1449mm long
GENERAL JOINERY
Wrot softwood
G | 50x20mm bearers | 7 | m | 350 | 2450
H | 20mm blockboard shelves; lipped | 2 | m2 | 13600 | 27200
J | Blockboard door lipped all round complete with
| 25mm diametre pull hole | 2 | No. | 16000 | 32000
sink below cabinet
K | 50x50mm batterns plugged | 3 | m | 750 | 2250
PAINTING AND DECORATING
L | Prepare and apply primer, undercoat and two finishing coats velvaglo paint
| coats velvaglo paint. | 5 | m2 | 1800 | 9000
| To Colletion |  |  |  | 3837300
FITTINGS AND FURNISHES
ITEM | DESCRIPTION | Qty | Unit | Rate | K
STAND ALONE BLOCKBOARD SHELVING
3No 600x2100x5250mm long
GENERAL JOINERY
Wrot softwood
A | 50 x 50mm styles | 29 | m | 750 | 21750
B | 75X20mm blockboard lipped all round | 79 | m | 1200 | 94800
C | 20mm thick blockboard | 67 | m2 | 13600 | 911200
Painting
D | Prepare and apply primer, undercoat and two finishing coats gloss paint | 95 | m2 | 2400 | 228000
coats gloss paint.
E | Ditto 200-300mm girth | 29 | m | 720 | 20880
CUPBOARD UNITS
Normal; designed mix 21N/mm2 10mm aggregate
vibrated; fair finish all exposed surfaces
F | 75mm thick slab | 1 | m2 | 7000 | 7000
G | Ref:A98,weight 1.54kg/m2: | 1 | m2 | 1895 | 1895
H | Formwork to soffit | 1 | m2 | 4000 | 4000
J | 140 mm Thick soil stabilised block mix cement and
soil (1:12) built to stretcher bond with cement and
| sand mortar (1:6) ; plinth | 1 | m2 | 10500 | 10500
K | 15mm screed; 1:3 cement and sand screed finished
| with a steel trowel to blocks100-200 girth | 2 | m | 360 | 720
GENERAL JOINERY
L | 50x20mm bearers | 10 | m | 300 | 3000
M | 20mm thick blockboard lipped | 3 | m2 | 13600 | 40800
metal work
N | Pressed steel door frame for 140 mm Soil Stabilised
Block wall door opening 1510x 1995mm with and
| including 100 mm steel hinges welded on the frame. | 1 | No. |  | 0
| To Colletion |  |  |  | 1344545
FITTINGS AND FURNISHES
ITEM | DESCRIPTION | Qty | Unit | Rate | K
Door
A | 760 x 1800 x 34 mm Internal quality hollow core flush
door faced both sides with 5 mm thick internal quality
plywood and lipped all round with 25x50 mm softwood
| strip. | 2 | No. | 65000 | 130000
Painting
B | Prepare and apply primer, undercoat and two finishing coats gloss paint
| coats gloss paint. | 9 | m2 | 2400 | 21600
C | ditto;100-200 girth | 10 | m | 480 | 4800
D | ditto;200-300 girth | 5 | m | 720 | 3600
Ironmongery
E | `D` handle;brass;100mm | 1 | No | 1200 | 1200
F | cabinet lockset | 1 | No. | 6500 | 6500
G | 75mm chromium plated barrel bolts |  |  | 950
LABORATORY FITTINGS
The following in 1 No. 2700 mm long bench, 6 No.
1500 mm long benches and 3 No. 4200 mm long
benches.
H | 50 mm Thick reinforced vibbrated in-situ concrete
| ( Class 21N/mm2/20mm) woktop. | 20 | m2 | 4500 | 90000
J | Sawn formwork to soffit of suspended slab | 20 | m2 | 4000 | 80000
K | Wrot formwork to edge of slab 50 mm high. | 61 | m | 200 | 12200
L | Hard drawn mild steel fabric reinforcement ( Ref A 98)
| weighing 1.54 kg/m2 | 20 | m2 | 1850 | 37000
M | 140 mm Thick wall of Soil Stabilised Blocks mix
(1:12) cement and soil or as instructed depending on
soil type on site with and including "Bickforce"
| reinforcement layer every fourth course biult in cement | 17 | m2 | 10500 | 178500
and sand mortar (1:6)
N | Ditto plinth to laboratory benches. | 22 | m2 | 10500 | 231000
O | 15mm Rendering (1:4) cement and sand finished
| with a final coat of line putty, steel trowelled to walls | 34 | m2 | 1800 | 61200
P | Prepare and apply one water thinned coat and
| two coats of internal quality PVA on walls | 34 | m2 | 1800 | 61200
| To Colletion |  |  |  | 918800
FITTINGS AND FURNISHES
ITEM | DESCRIPTION | Qty | Unit | Rate | K
A | 25 mm Thick cement and sand (1:3) screed finishes
| with a steel trowel | 20 | m2 | 3000 | 60000
B | 20 mm Thick 105 mm high skirting with cove at bottom
| and bullnosed at junction of rendering | 61 | m | 350 | 21350
C | 20 mm Thick approved white polished terrazzo on
| concrete worktop | 20 | m2 | 15500 | 310000
CUPBOARDS
D | 30X30 mm Wrot softwood frames and fixing to wood | 24 | m | 550 | 13200
E | 50x50 Ditto | 42 | m | 750 | 31500
F | 50x100 mm Ditto | 9 | m | 1000 | 9000
G | 20x20 mm Wrot hardwood lippinged tongued and
| grooved to blockboard. | 250 | m | 300 | 75000
H | 20 mm Thick blockboard shelves | 13 | m2 | 13600 | 176800
J | 550x745x20 mm Blockboard doors and fixing to
| softwood. | 80 | No. | 6000 | 480000
Ironmongery
K | Piano hinges and fixing to softwood and blockboard | 60 | m | 1100 | 66000
L | 25 mm Chromium plated pull handle and fixing to
| softwood. | 80 | No. | 2500 | 200000
M | Ball catches and fixing to sotwood. | 80 | No. | 1200 | 96000
Painting
N | Prepare and apply primer, undercoat and two finishing coats gloss paint on general wood surfaces | 100 | m2 | 2400 | 240000
O | Ditto not exceeding 100mm girth | 96 | m | 240 | 23040
P | Ditto not exceeding 300 mm girth. | 9 | m | 720 | 6480
( End of Laboratory Benches)
The following in 1 No. Terrazzo Finished Bench in
Preparation Room,
Q | 50 mm Thick reinforced vibbrated in-situ concrete
| ( Class 21N/mm2/20mm) woktop. | 1.4 | m2 | 4500 | 6300
| To Colletion |  |  |  | 1814670
FITTINGS AND FURNISHES
ITEM | DESCRIPTION | Qty | Unit | Rate | K
A | Sawn formwork to soffit of suspended slab | 1.4 | m2 | 4000 | 5600
B | Wrot formwork to edge of slab 50 mm high. | 3 | m | 200 | 600
C | Hard drawn mild steel fabric reinforcement ( Ref A 98)
| weighing 1.54 kg/m2 | 1.4 | m2 | 1850 | 2590
D | 140 mm Thick wall of Soil Stabilised Blocks mix
(1:12) cement and soil or as instructed depending on
soil type on site with and including "Bickforce"
| reinforcement layer every fourth course biult in cement | 2 | m2 | 10500 | 21000
and sand mortor (1:6)
E | Ditto plinth to laboratory benches. | 2 | m2 | 10500 | 21000
F | 15mm Rendering (1:4) cement and sand finished
| with a final coat of line putty, steel trowelled to walls | 4 | m2 | 1800 | 7200
G | Prepare and apply one water thinned coat and
| two coats of internal quality PVA on walls | 4 | m2 | 1800 | 7200
H | 25 mm Thick cement and sand (1:3) screed finishes
| with a steel trowel | 1.4 | m2 | 3000 | 4200
J | 20 mm Thick 105 mm high skirting with cove at bottom
| and bullnosed at junction of rendering | 3 | m | 350 | 1050
K | 20 mm Thick approved white polished terrazzo on
| concrete worktop | 1.4 | m2 | 15500 | 21700
CUPBOARDS
L | 30X30 mm Wrot softwood frames and fixing to wood | 4 | m | 550 | 2200
M | 50x50 Ditto | 10 | m | 700 | 7000
N | 20x20 mm Wrot hardwood lippinged tongued and
| grooved to blockboard. | 8 | m | 300 | 2400
O | 20 mm Thick blockboard shelves | 1 | m2 | 13600 | 13600
P | 630x745x20 mm Blockboard doors and fixing to
| softwood. | 1 | No. | 6500 | 6500
Q | 590x745x20 Ditto | 2 | No. | 6000 | 12000
Ironmongery
R | Piano hinges and fixing to softwood and blockboard | 2.3 | m | 1100 | 2530
S | 25 mm Chromium plated pull handle and fixing to
| softwood. | 3 | No. | 2500 | 7500
T | Ball catches and fixing to sotwood. | 3 | No. | 1200 | 3600
| To Colletion |  |  |  | 149470
FITTINGS AND FURNISHES
ITEM | DESCRIPTION | Qty | Unit | Rate | K
Painting
A | Prepare and apply primer, undercoat and two finishing coats gloss paint on general wood surfaces | 13 | m2 | 2400 | 31200
B | Ditto not exceeding 100mm girth | 13 | m | 240 | 3120
( End of Terrazzo Finished Bench in Preparation)
FUME CUPBOARD;
1No 630x700x2600mm high
C | 140 mm Thick soil stabilised block mix cement and
soil (1:12) built to stretcher bond with cement and
| sand mortar (1:6) ; plinth | 1 | m2 | 10500 | 10500
D | 15mm screed; 1:3 cement and sand screed finished
| with a steel trowel to blocks100-200 girth | 2 | m | 1800 | 3600
Hardwood wrot
E | 15x15mm Beads | 1 | m | 450 | 450
F | 50x50 frame | 5 | m | 1000 | 5000
G | 38x50mm Rebated | 1 | m | 850 | 850
H | 100x38mm Top rail plugged and chamfered and rebated | 4 | m | 1200 | 4800
J | 20x50mm Member | 6 | m | 600 | 3600
K | 20x100mm Member | 3 | m | 1200 | 3600
L | 38x38mm Rebated frame | 2 | m | 800 | 1600
Sashes
M | 38x38mm Framing one labour grooved and 15x15mm
| beads 650x500 wide | 2 | No. | 950 | 1900
Blockboard
N | 20mm thick blockboard | 1 | m | 13600 | 13600
O | 20mm x 350 x 745mm high block board doors lipped all round complete with 25mm diameter pull hole
| all round complete with 25 mm diameter pull hole. | 1 | No. | 4000 | 4000
Wall tiles
ceramic tiles;white glazed; laid at random bedded in
cement mortar (1:4) and grouting and pointing with
cement putty
P | 150x150x60mm thick tiles | 2 | m2 | 14500 | 29000
| To Colletion |  |  |  | 116820
FITTINGS AND FURNISHES
ITEM | DESCRIPTION | Qty | Unit | Rate | K
A | extra over for raking cutting | 1 | m | 1500 | 1500
Glazing
B | laminated sheet 6mm thick to wood with putty and beads
| over 0.1 <0.5m2 | 1 | m2 | 10500 | 10500
C | ditto over0.5 <1.0m2 | 1 | m2 | 10500 | 10500
FUME COUNTER(WORKTOP)
Hardwood ; wrot
D | 100x50mm | 5 | m | 3000 | 15000
E | ditto;fixed to floor | 4 | m | 3000 | 12000
F | 20mm thick blockboard worktop; lipped all round | 1 | m2 | 13600 | 13600
Metal work
G | 56x40x6mm Thick mild steel angle | 4 | No | 3000 | 12000
PAINTING
H | Prepare and apply primer, undercoat and two finishing coats velvaglo paint on blockboard general surface
| coats velvaglo paint on blackboard general surface. | 44 | m2 | 2400 | 105600
K | Prepare and apply polyurethen varnish 100-200mm girth | 18 | m | 360 | 6480
L | Ditto 200-300mm girth | 122 | m | 450 | 54900
STORE AND PREPARATION AREA
wrot softwood
M | 50x50mm frames | 115 | m | 1000 | 115000
N | ditto fixed to wall | 93 | m | 1000 | 93000
O | 20mm thick blockboard worktop; lipped one side | 37 | m2 | 13600 | 503200
P | 75x20mm thick lipped one side | 36 | m | 1500 | 54000
Q | 20mm x 620 x 745mm high block board doors lipped all round complete with 25mm diameter pull hole
| all round complete with 25 mm diameter pull hole. | 54 | No | 6500 | 351000
R | Extra over, forming 500mm diameter sink opening | 1 | No. | 1500 | 1500
S | 140 mm Thick soil stabilised block mix cement and
soil (1:12) built to stretcher bond with cement and
| sand mortar (1:6) ; plinth | 13 | m2 | 10500 | 136500
T | 15mm screed; 1:3 cement and sand screed finished
| with a steel trowel to blocks100-200 girth | 26 | m | 1800 | 46800
| To Colletion |  |  |  | 1543080
FITTINGS AND FURNISHES
ITEM | DESCRIPTION | Qty | Unit | Rate | K
IRONMONGERY
A | piano hinges(183No) brass; 32mm | 144 | No | 850 | 122400
B | cupboard catches;zinc plated; double nylon roller;
| 19x1.5mm | 72 | No | 950 | 68400
C | `D` handle; brass; 100mm | 72 | No | 250 | 18000
D | Sliding sash pully ;cutting timber sash and traming;
| 30mm diametre | 1 | No | 5000 | 5000
E | 6mm nylon rope in 1m lengths, connecting to sash and
| mild steel pipe | 2 | No | 1450 | 2900
F | 38mm diametre mild steel pipe ;lead filled; 300mm long | 2 | No | 3600 | 7200
G | 50mm CP barrel bolts | 144 | No | 1500 | 216000
H | double cylinder lockset; ref CZ 682-13-205 suit
| `A`to metal | 72 | No | 8500 | 612000
PAINTING
J | Prepare and apply primer, undercoat and two finishing coats velvaglo paint on blockboard general surface
| coats velvaglo paint on blockboard general surface. | 98 | m2 | 2400 | 235200
PIBBOARDS AND CHALKBOARD
2No. 1539x1200mm pinboard
1No. 4500x1200mm chalkboard
General joinery
Hardwood; wrot
K | 45x30mm rebated; plugged to blockwork | 35 | m | 1500 | 52500
L | 90x50mm twice rebated; plugged to blockwork | 4 | m | 3000 | 12000
M | 60x30mm; dittot | 10 | m | 2600 | 26000
N | 90x50mm grooved | 4 | m | 3000 | 12000
Celotex softboard sheet
O | 13mm thick pinboard ;close butt joint; fixing with
| adhesive to wall | 5 | m2 | 9000 | 45000
Chalkboard
P | 13mm thick plaster steel trawel; cement and sand
| mix (1:4) | 5 | m2 | 1800 | 9000
| To Colletion |  |  |  | 1443600
FITTINGS AND FURNISHES
ITEM | DESCRIPTION | Qty | Unit | Rate | K
PAINTING
A | Prepare and apply primer, undercoat and two finishing coats velvaglo paint on blockboard general surface
| coats velvaglo paint on blockboard general surface. | 36 | m2 | 2400 | 86400
Prepare and apply polyurethen varnish on wood surface
| ditto 100-200mm girth | 17 | m | 300 | 5100
B | ditto 200-300mm girth | 122 | m | 450 | 54900
C | Prepare and apply one thinned coat;two coats internal quality PVA paint on softboard surface
| quality PVA paint on softboard surface. | 17 | m2 | 1800 | 30600
D | Prepare amd apply blackboard paint;matt finish on
| plastered surface | 5 | m2 | 1800 | 9000
SIGNAGE
E | Provide perspex name plates to the School Blocks
average size of letters being 50 mm to the approval of
the Project Architect. The lettering to be Red on White
background to read as: -
LABORATORY
PREPARATION
| STORE | 1 | Item | 65000 | 65000
F | Provide plastic key tags. | 14 | No. | 2500 | 35000
| To Colletion |  |  |  | 286000
COLLECTION
| Page No. LL/15 |  |  |  | 240250
| Page No. LL/16 |  |  |  | 3837300
| Page No. LL/17 |  |  |  | 1344545
| Page No. LL/18 |  |  |  | 918800
| Page No. LL/19 |  |  |  | 1814670
| Page No. LL/20 |  |  |  | 149470
| Page No. LL/21 |  |  |  | 116820
| Page No. LL/22 |  |  |  | 1543080
| Page No. LL/23 |  |  |  | 1443600
| Page No. LL/ 25 |  |  |  | 286000
| FITTINGS AND FURNISHES TO SUMMARY |  |  |  | 11694535
SOLAR ELECTRICAL
Item | Description | Qty | Unit | Rate | K
PRIME COST SUMS
Allow the following Prime Cost Sums;
A | Solar Electrical | 1 | Item | 3000000 | 3000000
B | Main Contractor's Profit | % |  |  | 900000
C | Add for Attendance |  | Item |  | 292500
| To collection |  |  |  | 4192500
| SOLAR ELECTRICAL TO SUMMARY |  |  |  | 4192500
| LABORATORY AND LIBRARY SUMMARY | PAGE
| SUBSTRUCTURE | LL/3 |  |  | 7864700
| ROOF | LL/5 |  |  | 10002600
| EXTERNAL AND INTERNAL WALLS | LL/7 |  |  | 6982450
| WINDOWS AND DOORS | LL/9 |  |  | 5059500
| WALL FINISHES | LL/10 |  |  | 1526400
| FLOOR FINISHES | LL/11 |  |  | 1086350
| SANITARY INSTALLATION | LL/14 |  |  | 5648500
| FITTINGS AND FURNISHINGS | LL/24 |  |  | 11694535
| SOLAR ELECTRICAL | LL/25 |  |  | 4192500
| LABORATORY AND LIBRARY TO MAIN SUMMARY |  |  |  | 54057535

## 4 Hole Pit latrine block
4 HOLE PIT LATRINE BLOCK (for Staff)
| SUBSTRUCTURE | Qty | Unit | Rate | Amount
Refer SMM paragraph F19(a). It has been assumed that strip
footings, bases, beds and the like within the ground will be
poured against natural ground. If formwork is required to such
surfaces, the contractor must include for same in his
excavations/concrete rates
EXCAVATION
Excavation/Filling (provisional)
A | Excavate trench from reduced level for strip footings
| 0 to 1500mm deep | 5 | m3 | 750 | 3750
B | Excavate pit from reduced level for pit latrine
| 0 to 1500mm deep | 20 | m3 | 750 | 15000
C | Excavate pit from reduced level for pit latrine
| 1500 to 3000mm deep | 20 | m3 | 850 | 17000
D | Excavate pit from reduced level for pit latrine
| 3000 to 4500mm deep | 12 | m3 | 950 | 11400
E | Graded stone filling as filter media, backfilled around chamber
| chamber | 12 | m3 | 8500 | 102000
Excavation/Filling (provisional)
F | Selected earth filling, deposited, spread and
| compacted in 150mm layers around foundations | 6 | m3 | 700 | 4200
Rock excavation (provisional)
G | Extra over excavation for excavation in rock | 14 | m3 | 3500 | 49000
Disposal
H | Surplus excavated material from excavations, transported
a distance average 100 linear metres from excavations and
| deposit in spoil heaps on site | 51 | m3 | 750 | 38250
Hardcore filling to pass a 50mm ring all ways
I | 150mm Thick (consolidated) filling well compacted
| and rolled | 4 | m2 | 550 | 2200
Sand blinding
J | 50mm Bed of sand on hardcore rolled to receive
| damp proof membrane | 4 | m2 | 500 | 2000
Damp proof membrane
H | 250mm Micros (1000 gauge) polythene damp proof
membrane with welted joints, lapped 150mm at joints
| and laid on blinded hardcore | 7 | m2 | 750 | 5250
Ant treatment
I | Saturate surface of hardcore and top of block walls
| with approved ant repellant | 14 | m2 | 850 | 11900
| To Collection |  |  |  | 261950
5.1
| SUBSTRUCTURE | Qty | Unit | Rate | Amount
Sundries
A | Allow for keeping excavations free from water | 1 | Item |  | 0
B | Allow for planking and strutting to sides of excavation | 1 | Item |  | 0
CONCRETE WORK
Precast vibrated concrete (Class 21N/mm2/10mm)
bedded, jointed and pointed in cement mortar (1:3)
C | 50mm "Sanplat" cover slab size 600 x 600mm reinforced with
and including 8mm diameter mild steel bar reinforcement at
150mm centres both ways finished fair on all exposed faces and
| include forming key hole shape and foot rest marks | 4 | No | 3500 | 14000
D | 75mm Suspended slab size 3320 x 1360mm ditto, and include
| forming 100mm diameter hole | 1 | No | 30000 | 30000
Precast vibrated concrete (Class 21N/mm2/10mm)
bedded, jointed and pointed in cement mortar (1:3)
E | 50mm Thick slabs, general size 600 x 600mm having smooth
finish, bedded, jointed and pointed in cement mortar (1:3) laid
to falls and cross falls on sand bed (measured separately),
include for all cutting/or mortar packing to edges and joints
| and allow for pattern as shown on the drawings | 16 | m2 | 5000 | 80000
Plain in-situ concrete (Class 21N/mm2/20mm)
F | Strip footings | 2 | m3 | 80000 | 160000
BLOCKWORK (PROVISIONAL)
Hollow precast cement and sand blocks, filled
solid with concrete (Grade 15/20) in cement
mortar (1:4)
G | 140mm Thick block wall in stretcher bond and reinforced
| with one layer of "brickforce" reinforcement every third course | 22 | m2 | 9500 | 209000
H | Ditto, honey comb | 48 | m2 | 9500 | 456000
| To Collection |  |  |  | 949000
5.2
| SUBSTRUCTURE | Qty | Unit | Rate | Amount
COLLECTION
Page Nos.
| 5.1 |  |  |  | 261950
| 5.2 |  |  |  | 949000
| To Summary |  |  |  | 1210950
5.3
| ROOF | Qty | Unit | Rate | Amount
ROOFING
TRAFFIC GREEN CHROMADECK IBR
A | 28 gauge Chromadeck IBR roofing sheets fixed on softwood purlins
accordance with the manufacturer's specifications and
| recommendations | 24 | m2 | 12500 | 300000
B | 450mm girth Ridges | 6 | m1 | 4000 | 24000
C | Ridge Closures | 12 | m1 | 3500 | 42000
CARPENTRY
Unframed
D | 50 x 75mm Rafters/Sprockets | 18 | m1 | 1000 | 18000
E | 50 x 75mm Treated battens/purlins | 36 | m1 | 1000 | 36000
F | 50 x 85mm ditto | 6 | m1 | 1150 | 6900
G | 50 x 150mm Purlins | 37 | m1 | 2000 | 74000
Treated wrot softwood
H | 30 x 250mm Softwood fascia/barge boards | 28 | m1 | 3000 | 84000
Sundries
I | Two strand 4mm Diameter high tensile steel wire tie 1500mm
girth with one end built into block wall and other end around
| roof timber | 13 | No | 985 | 12805
PAINTING AND DECORATING
Prepare, knot, stop, prime and apply one undercoat
and two finishing coats of gloss paint on
J | Timber general surfaces | 15 | m2 | 2400 | 36000
K | Ditto, 200 to 300mm girth | 43 | m1 | 720 | 30960
| To Summary |  |  |  | 664665
5.4
| EXTERNAL AND INTERNAL WALLS | Qty | Unit | Rate | Amount
BLOCKWORK
Stabilised soil blocks bedded and jointed in
gauged mortar (1:10)
A | 140mm Thick block wall in stretcher bond and reinforced with
| one layer of "blockforce" reinforcement every fifth course | 6 | m2 | 10500 | 63000
B | Fair splay cutting | 3 | m1 | 1500 | 4500
C | Extra over block wall for strengthened
| stabilised soil blocks | 11 | m2 | 12000 | 132000
D | 140mm x 290mm girth block wall in stretcher bond and
reinforced with one layer of "blockforce" reinforcement
| every fifth course | 19 | m1 | 1500 | 28500
Selected stabilised soil blocks bedded and jointed
in gauged mortar (1:1:6) - pointing measured
separately
E | 140mm Thick block wall in stretcher bond and reinforced with
| one layer of "blockforce" reinforcement every fifth course | 47 | m2 | 10500 | 493500
F | Fair splay cutting | 2 | m1 | 1500 | 3000
Sundries
G | Form a hole size 600 x 450mm through 140mm block wall
including forming rough arch over and plastering around
| internally in cement mortar (1:4) and make good | 4 | No | 850 | 3400
Damp proof course
H | 3 Ply malthoid damp proof course, over 140mm wide, laid
| under blockwork | 19 | m1 | 250 | 4750
| To Summary |  |  | K | 732650
5.5
| WINDOWS AND DOORS | Qty | Unit | Rate | Amount
CONCRETEWORK
Precast vibrated concrete (Class 21N/mm2/10mm)
bedded, jointed and pointed in cement mortar (1:3)
A | 140 x 150 x 1050mm long lintel, two edges chamfered finished
fair on all exposed surfaces and reinforced with and including
| 6kg of mild steel rod reinforcement and built into blockwork | 4 | No | 2000 | 8000
Doors
Framed, ledged, braced and battened doors shall be
constructed having 45 x 100mm stiles top, centre,
bottom rail and bracing, grooved, morticed, tenoned
and glued together clad one side with 25 x 100mm
tongued and grooved "v" jointed boarding
B | 920 x 2050mm High framed, braced and battened door | 4 | No | 85000 | 340000
Door frames
Rates shall include for lugs welded to back, building into
blockwork and filling cavity with cement and sand (1;3)
Prior to delivery on site, the whole to be treated at works
with one coat red oxide primer
C | Standard metal door frame, size 1000 x 2110mm overall,
suitable for 140mm blockwall, complete with one pair of
| butts | 4 | No | 60000 | 240000
(Accessible to Physical Challnged)
PAINTING AND DECORATING
Prepare, knot, stop, prime and apply one undercoat
and two finishing coats of gloss enamel on
D | Timber framed, ledged, braced and battened doors
| (measured overall) | 12 | m2 | 2400 | 28800
Prepare, prime and apply one undercoat and two
finishing coats of gloss enamel on
E | General surfaces, exceeding 200mm and not exceeding
| 300mm girth | 20 | m1 | 720 | 14400
| To Summary |  |  | K | 631200
5.6
| IRONMONGERY | Qty | Unit | Rate | Amount
Unless otherwise stated, fixing is to timber
Doors
A | "Union AL643-24-77" 3 lever lockset and furniture set | 4 | No | 12500 | 50000
B | "Union AL 8730" rubber door stop, fixed to floor screed | 4 | No | 2000 | 8000
C | "Union AL 8722" rubber tipped hat and coat hook | 4 | No | 2000 | 8000
| To Summary |  |  | K | 66000
5.7
| WALL FINISHES | Qty | Unit | Rate | Amount
INTERNAL
PLASTERWORK
15mm Rendering (1:4) cement and sand, finished
with a wood float
A | Block/concrete wall | 48 | m2 | 1800 | 86400
B | Ditto, ditto | 2 | m2 | 1800 | 3600
PAINTING AND DECORATING
Prepare and apply one water thinned coat and
two coats of internal quality wash "n" wear silk
white on
C | Rendered walls | 50 | m2 | 1800 | 90000
EXTERNAL
BLOCKWORK
D | Point in cement and sand mortar (1:4) recessed joints
| of blockwork | 61 | m2 | 1500 | 91500
PLASTERWORK
15mm Rendering (1:4) cement and sand, finished
with a wood float
E | Block/concrete walls (provisional) | 13 | m2 | 1800 | 23400
F | Block/concrete walls | 1 | m2 | 1800 | 1800
PAINTING AND DECORATING
Prepare and apply two coats styrene acrylic
emulsion clear sealer on
G | Fairface block walls | 61 | m2 | 1500 | 91500
PAINTING AND DECORATING
Prepare and apply two coats of black bituminous
paint on
H | Rendered walls (provisional) | 13 | m2 | 1500 | 19500
Prepare, prime and two coats of external quality
wash "n" wear silk white on
I | Rendered walls | 1 | m2 | 1800 | 1800
| To Summary |  |  | K | 409500
5.8
| FLOOR FINISHES | Qty | Unit | Rate | Amount
PLASTERWORK
1:3 Cement and sand screed finished with a steel
trowel
A | 100mm High skirting with small cove at bottom and
| "V" joint to junction of rendering | 15 | m1 | 350 | 5250
PAINTING AND DECORATING
Washdown, clean and apply two coats of wax
polish on
B | Steel trowelled slabs | 6 | m2 | 900 | 5400
| To Summary |  |  | K | 10650
5.9
| SOIL, WASTE AND VENT SERVICES | Qty | Unit | Rate | Amount
(ALL PROVISIONAL)
This section has been measured from fittings up to
gulley or first manhole
Pipework and fittings
Soil system shall be "Key Terrain 100" PVC to BS 4514
Waste system shall be "Key Terrain 200" UPVC
Diameters stated are outside in accordance with the
manufacturers metric catalogues
Generally joints are solvent welded
Fixing to walls, slabs etc shall be with standard pipe, clips
plugged and screwed
A | 110mm Diameter pipe fixed to brick/concrete wall | 12 | m1 | 1650 | 19800
B | Extra over 150.4 vent cowl | 4 | No | 6500 | 26000
Testing
C | Allow to test the foregoing soil, waste and vent pipework
| installation | 1 | item | 30000 | 30000
D | Form sleeved opening through iron sheets for 110mm diameter
| pipe | 4 | No | 850 | 3400
| To Summary |  |  | K | 79200
5.1
SUMMARY
Pages No.
| SUBSTRUCTURE | 5.3 |  |  | 1210950
| ROOF | 5.4 |  |  | 664665
| EXTERNAL AND INTERNAL WALLS | 5.5 |  |  | 732650
| WINDOwS AND DOORS | 5.6 |  |  | 631200
| IRONMONGERY | 5.7 |  |  | 66000
| WALL FINISHES | 5.8 |  |  | 409500
| FLOOR FINISHES | 5.9 |  |  | 10650
| SOIL, WASTE AND VENT SERVICES (ALL PROVISIONAL) | 5.1 |  |  | 79200
| To Final Summary |  |  | K | 3804815
5.11

## Administration block
ADMINISTRATION BLOCK
| SUBSTRUCTURE | Qty | Unit | Rate | Amount
Refer SMM paragraph F19(a). It has been assumed that strip
footings, bases, beds and the like within the ground will be
poured against natural ground. If formwork is required to such
surfaces, the contractor must include for same in his
excavations/concrete rates
EXCAVATION
Excavation/Filling (provisional)
A | Excavate trench from reduced level for strip footings
| 0 to 1500mm deep | 22 | m3 | 750 | 16500
Excavation/Filling (provisional)
N | Selected earth filling, deposited, spread and
| compacted in 150mm layers around foundations | 10 | m3 | 700 | 7000
Rock excavation (provisional)
A | Extra over excavation for excavation in rock | 2 | m3 | 3500 | 3500
Disposal
F | Surplus excavated material from excavations, transported
a distance average 100 linear metres from excavations and
| deposit in spoil heaps on site | 12 | m3 | 750 | 9000
Hardcore filling to pass a 50mm ring all ways
K | 150mm Thick (consolidated) filling well compacted
| and rolled | 39 | m2 | 550 | 21450
Sand blinding
P | 50mm Bed of sand on hardcore rolled to receive
| damp proof membrane | 39 | m2 | 500 | 19500
Damp proof membrane
A | 250mm Micros (1000 gauge) polythene damp proof
membrane with welted joints, lapped 150mm at joints
| and laid on blinded hardcore | 45 | m2 | 550 | 24750
Ant treatment
F | Saturate surface of hardcore and top of block walls
| with approved ant repellant | 45 | m2 | 850 | 38250
Sundries
K | Allow for keeping excavations free from water | 1 | Item |  | 0
L | Allow for planking and strutting to sides of excavation | 1 | Item |  | 0
| To Collection |  |  |  | 139950
SFS/249/10 LOT 3 3.1
| SUBSTRUCTURE | Qty | Unit | Rate | Amount
Precast vibrated concrete (Class 21N/mm2/10mm)
bedded, jointed and pointed in cement mortar (1:3)
A | 50mm Thick slabs, general size 600 x 600mm having smooth
finish, bedded, jointed and pointed in cement mortar (1:3) laid
to falls and cross falls on sand bed (measured separately),
include for all cutting/or mortar packing to edges and joints
| and allow for pattern as shown on the drawings | 18 | m2 | 5000 | 90000
Plain in-situ concrete (Class 21N/mm2/20mm)
B | Strip footings | 4 | m3 | 80000 | 320000
Reinforced in-situ concrete (Class 21N/mm2/20mm)
C | Slab thicknessing to form external seat (0.21m3) | 1 | item | 20000 | 20000
D | 75mm Thick horizontal bed, laid in bays generally 25 square
| metres, including formwork to construction joints | 45 | m2 | 7000 | 315000
E | Extra over horizontal bed for steel
| trowel finish | 39 | m2 | 850 | 33150
Sawn formwork
F | Edge of slab, 75 to 150mm wide | 32 | m1 | 600 | 19200
Reinforcement (provisional)
G | Hard drawn mild steel fabric reinforcement (Ref A98)
| weighing 1.54kg/m2 in beds | 61 | m2 | 1850 | 112850
BLOCKWORK (PROVISIONAL)
Hollow precast cement and sand blocks, filled
solid with concrete (Grade 15/20) in cement
mortar (1:4)
H | 140mm Thick block wall in stretcher bond and reinforced
| with one layer of "brickforce" reinforcement every third course | 52 | m2 | 9500 | 494000
| To Collection |  |  |  | 1404200
SFS/249/10 LOT 3 3.2
| SUBSTRUCTURE | Qty | Unit | Rate | Amount
COLLECTION
Page Nos.
| 3.1 |  |  |  | 139950
| 3.2 |  |  |  | 1404200
| To Summary |  |  |  | 1544150
SFS/249/10 LOT 3 3.3
| ROOF | Qty | Unit | Rate | Amount
ROOFING
TRAFFIC GREEN CHROMADECK IBR
A | 28 gauge Chromadeck IBR roofing sheets fixed on softwood purlins
accordance with the manufacturer's specifications and
| recommendations | 61 | m2 | 12500 | 762500
B | 450mm girth Ridges | 8 | m1 | 4000 | 32000
C | Ridge Closures | 16 | m1 | 3500 | 56000
CARPENTRY
Roof trusses
Framed softwood pressure treated with CCA timber roof
trusses erected at eaves level and hoisted approximately
2410mm above ground level
D | 50 x 150mm Top chord | 57 | m1 | 2000 | 114000
E | 50 x 150mm Bottom chord | 40 | m1 | 2000 | 80000
F | 50 x 150mm King Post | 11 | m1 | 2000 | 22000
G | 50 x 100mm Tie or strut | 33 | m1 | 1500 | 49500
Unframed
H | 50 x 50mm Treated battens/purlins | 136 | m1 | 750 | 102000
I | 50 x 75mm Treated battens/purlins | 17 | m1 | 1125 | 19125
J | 50 x 100mm Wall Plate | 15 | m1 | 1500 | 22500
Saligna Glulam
K | 30 x 250mm Glulam fascia/barge boards | 31 | m1 | 4000 | 124000
L | Bore 50mm softwood for 10mm diameter bolt (Measured
| separately) | 9 | No | 450 | 4050
METALWORK (AS SUPPLIED BY CASHBUILD
ACCORD CENTRE, LILONGWE) OR ANY OTHER
APPROVED SUPPLIER
M | 1.2mm x 150 x 250mm galvanised gang nail plate fixed to timber | 14 | No | 3200 | 44800
N | 1.2 x 250 x 150mm Ditto | 28 | No | 3200 | 89600
O | 1.2 x 300 x 150mm Ditto | 28 | No | 3600 | 100800
P | 1.2 x 80 x 250mm Ditto | 28 | No | 2000 | 56000
Sundries
Q | 10mm diameter bar 1500mm girth twice bent with one
end built into concrete ring beam and other end wrapped
| around roof timber | 14 | No | 1150 | 16100
| To Collection |  |  |  | 1694975
SFS/249/10 LOT 4 3.4
| ROOF | Qty | Unit | Rate | Amount
Sundries
A | 3mm diameter x 500mm girth galvanised steel binding
| wire fixed around purlin and rafter end as tie | 14 | No | 1150 | 16100
B | 10mm Diameter screw bolt 75mm long complete with
| head, nut and washer | 4 | No | 2500 | 10000
PAINTING AND DECORATING
Prepare, knot, stop, seal and apply two coats
of polyrethane on
C | Timber general surfaces | 9 | m2 | 1500 | 13500
| To Collection |  |  | K | 39600
SFS/249/10 LOT 4 3.5
| ROOF | Qty | Unit | Rate | Amount
COLLECTION
Page Nos.
| 3.4 |  |  |  | 1694975
| 3.5 |  |  |  | 39600
| To Summary |  |  | K | 1734575
SFS/249/10 LOT 4 3.6
| EXTERNAL AND INTERNAL WALLS | Qty | Unit | Rate | Amount
CONCRETE WORK
Reinforced vibrated in-situ concrete (Class 25N/
mm2/20mm)
A | Beams | 1 | m3 | 90000 | 90000
B | Lintols (0.08m3) | 1 | m3 | 90000 | 90000
Sawn formwork
C | Sides and soffit of beams | 20 | m2 | 4000 | 80000
Reinforcement (provisional)
D | 6mm Diameter mild steel rod reinforcement | 2 | kg | 1500 | 3000
E | 12mm Diameter deformed high yield mild steel rod
| reinforcement | 60 | kg | 1500 | 90000
BLOCKWORK
Stabilised soil blocks bedded and jointed in
gauged mortar (1:10)
F | 140mm Thick block wall in stretcher bond and reinforced with
| one layer of "blockforce" reinforcement every fifth course | 20 | m2 | 10500 | 210000
Strengthened stabilised soil blocks bedded and
jointed in gauged mortar (1:1:6) pointing measured
G | 140mm Thick block wall in stretcher bond and reinforced with
| one layer of "blockforce" reinforcement every fifth course | 2 | m2 | 12000 | 24000
H | 140 x 290mm soldier course, ditto | 43 | m1 | 1600 | 68800
Selected stabilised soil blocks bedded and jointed
in gauged mortar (1:1:6) - pointing measured
separately
I | 140mm Thick block wall in stretcher bond and reinforced with
| one layer of "blockforce" reinforcement every fifth course | 94 | m2 | 10500 | 987000
J | 140mm Thick beam filling, 300mm high including cutting and
| pinning or building ends of rafters | 15 | m1 | 1100 | 16500
K | Fair splay cutting | 30 | m1 | 1000 | 30000
Sundries
L | Form opening size 150 x 225mm through 140mm blockwall
for air brick (measured separately) including forming rough
arch over and plastering around internally in cement mortar
| (1:4) and make good | 9 | No | 850 | 7650
M | 150 x 225mm precast cement and sand (1:4) air brick with
| insect gauze at back and built in and make good | 9 | No | 1250 | 11250
Damp proof course
N | 3 Ply malthoid damp proof course, over 140mm wide, laid
| under blockwork | 42 | m1 | 250 | 10500
| To Summary |  |  | K | 1718700
SFS/249/10 LOT 4 3.7
| WINDOWS AND DOORS | Qty | Unit | Rate | Amount
CONCRETEWORK
Precast vibrated concrete (Class 21N/mm2/10mm)
bedded, jointed and pointed in cement mortar (1:3)
A | 165 x 65 x 633mm long sill, once splayed, once grooved and
two edges chamfered, finished fair on all exposed surfaces
| built into blockwork | 1 | No | 950 | 950
B | 165 x 65 x 1122mm long sill, ditto | 4 | No | 1500 | 6000
JOINERY
Unless otherwise stated, all timber is hardwood
C | 25 x 50mm Batten | 6 | m1 | 1500 | 9000
Pelmets
D | 20 x 150mm Top fixed to batten (batten measured separately) | 6 | m1 | 2500 | 15000
E | 20 x 150mm Fascia Top into facing | 6 | m1 | 2500 | 15000
F | 20mm End size 150 x 150mm Facing with rounded edges | 6 | No | 650 | 3900
Doors
Framed, ledged, braced and battened doors shall be
constructed having 45 x 100mm stiles top, centre,
bottom rail and bracing, grooved, morticed, tenoned
and glued together clad one side with 25 x 100mm
tongued and grooved "v" jointed boarding
G | 920 x 2032mm High framed, braced and battened door | 2 | No | 85000 | 170000
Flush panel doors shall be 45mm finished thickness, faced
both sides with plywood (as described) and lipped all round
with 25 x 15mm strip faced both sides with commercial
plywood
H | 920 x 2032mm High semi solid core flush door | 1 | No | 60000 | 60000
Door frames
Rates shall include for lugs welded to back, building into
blockwork and filling cavity with cement and sand (1;3)
Prior to delivery on site, the whole to be treated at works
with one coat red oxide primer
I | Standard metal door frame, size 1000 x 2062mm overall,
suitable for 140mm blockwall, complete with one pair of
| butts | 3 | No | 60000 | 180000
(Accessible to Physical Challnged)
| To Collection |  |  | K | 459850
SFS/249/10 LOT 4 3.8
| WINDOWS AND DOORS | Qty | Unit | Rate | Amount
Grille doors
All prices for the items described are deemed to include for
complete installation shown on the drawing and no extra cost
will be allowed for any omission or brevity of description in the
billed items that is apparent with reference to the drawings
Rates shall include for lugs welded to back and whole to be
treated at works with one coat primer, building into blockwork
and filling cavity with cement and sand (1:3)
The contactor must see sample of door and window as in
Client's/Architect's office
A | Mild steel door size 1100 x 2062mm comprising 40 x 40mm
SHS top, bottom and middle members and vertical members
| at 740mm centres, with hinges welded to metal door frame | 2 | No | 165000 | 330000
Window frames
Standard mild steel horizontal bar windows with lugs welded,
all opening lights complete with ironmongery including
projecting hinges and whole to be treated at works with one
coat red oxide primer, built into blockwork
B | Window E1H (size 533 x 654mm) complete with burglar bars | 1 | No | 25000 | 25000
C | Window D7H (size 1022 x 1854mm) complete with burglar bars | 4 | No | 90000 | 360000
GLAZING
Clear sheet glass
D | 4mm Glass fixed to metal with mastic putty, in panes,
| 0.10 to 0.50m2 | 8 | m2 | 8500 | 68000
PAINTING AND DECORATING
Prepare, knot, stop, seal and apply two coats
of polyurethane on
E | Timber framed, ledged, braced and battened doors
| (measured overall) | 4 | m2 | 1500 | 6000
Prepare, knot, stop, prime and apply one undercoat
and two finishing coats of gloss enamel on
G | Timber general surfaces | 7 | m2 | 2400 | 16800
Prepare, prime and apply one undercoat and two
finishing coats of gloss enamel on
H | Grille doors (measured overall) | 4 | m2 | 2400 | 9600
I | Metal glazed windows | 18 | m2 | 2400 | 43200
| To Collection |  |  |  | 805800
SFS/249/10 LOT 4 3.9
| WINDOWS AND DOORS | Qty | Unit | Rate | Amount
PAINTING AND DECORATING
Prepare, prime and apply one undercoat and two
finishing coats of gloss enamel on
A | General surfaces, exceeding 200mm and not exceeding
| 300mm girth | 10 | m1 | 720 | 7200
| To Collection |  |  | K | 7200
SFS/249/10 LOT 4 3.10
| WINDOWS AND DOORS | Qty | Unit | Rate | Amount
COLLECTION
Page Nos.
| 3.8 |  |  |  | 459850
| 3.9 |  |  |  | 805800
| 3.1 |  |  |  | 7200
| To Summary |  |  | K | 1272850
SFS/249/10 LOT 4 3.11
| IRONMONGERY | Qty | Unit | Rate | Amount
Unless otherwise stated, fixing is to timber
Doors
A | "Union CZ682-24-52CH" 3 lever lockset and furniture set | 3 | No | 12500 | 37500
B | "Union AL 8730" rubber door stop, fixed to floor screed | 3 | No | 2000 | 6000
Grille doors
C | Heavy duty padlock | 2 | No | 8500 | 17000
Sundries
D | Silent Gliss "C" section curtain track, complete with
| nylon runners, guides and end stops | 5 | m1 | 4500 | 22500
E | 150mm Chromium plated coat and hat hook | 5 | No | 2000 | 10000
| To Summary |  |  | K | 93000
SFS/249/10 LOT 4 3.12
| WALL FINISHES | Qty | Unit | Rate | Amount
INTERNAL
PLASTERWORK
30mm Rendering (1:4) cement and sand finished
with a steel trowel
A | Block/concrete walls (chalkboard) | 3 | m2 | 3600 | 10800
15mm Rendering (1:4) cement and sand, finished
with a final coat of lime putty, steel trowelled
B | Block/concrete wall | 97 | m2 | 1800 | 174600
C | Ditto, in narrow widths | 1 | m2 |  | 0
1800
Prepare and apply one undercoat and two
coats of internal quality wash "n" wear apple
white on
D | Rendered walls | 70 | m2 | 1800 | 126000
Prepare and apply one undercoat and two
coats of internal quality wash "n" wear apricot
white on
E | Rendered walls | 28 | m2 | 1800 | 50400
Prepare, apply one undercoat and two finishing
coats of green chalk board paint on
F | Rendered walls | 3 | m2 | 1800 | 5400
EXTERNAL
BLOCKWORK
G | Point in cement and sand mortar (1:4) recessed joints
| of blockwork | 113 | m2 | 1500 | 169500
H | Ditto, in narrow widths | 1 | m2 | 1500 | 1500
PLASTERWORK
15mm Rendering (1:4) cement and sand, finished
with a wood float
I | Block/concrete walls (provisional) | 7 | m2 | 1800 | 12600
Prepare and apply two coats styrene acrylic
emulsion clear sealer on
J | Fairface block walls | 114 | m2 | 1500 | 171000
Prepare and apply two coats of black bituminous
paint on
K | Rendered walls (provisional) | 7 | m2 | 1500 | 10500
| To Summary |  |  | K | 550800
SFS/249/10 LOT 4 3.13
| FLOOR FINISHES | Qty | Unit | Rate | Amount
PLASTERWORK
1:3 Cement and sand screed finished with a steel
trowel
A | 100mm High skirting with small cove at bottom and
| "V" joint to junction of rendering | 40 | m1 | 350 | 14000
PAINTING AND DECORATING
Washdown, clean and apply two coats of wax
polish on
B | Steel trowelled slabs | 43 | m2 | 900 | 38700
| To Summary |  |  | K | 52700
SFS/249/10 LOT 4 3.14
| JOINERY FITTINGS | Qty | Unit | Rate | Amount
The following in 2No. Pinboards
A | 25 x 50mm Top and side plugged and screwed | 5 | m1 | 1150 | 5750
B | 25 x 100mm, ditto bottom frame, ditto | 8 | m1 | 2300 | 18400
C | 13mm Ivory faced softwood lining fixed to framing (measured
| separately) | 6 | m2 | 10000 | 60000
Painting and Decorating
D | Prepare and apply three coats of ceiling paint on softwood
| wall lining | 6 | m2 | 1600 | 9600
The following in 1No. Chalkboard (provisional)
Wrot softwood
E | 25 x 50mm Top and side frames, plugged and screwed | 3 | m1 | 1150 | 3450
F | 25 x 100mm Coved chalk rail framing tied to bottom edge of
| chalkboard (measured separately) | 1 | m1 | 2500 | 2500
Painting and Decorating
G | Prepare and apply one coat primer for new plaster and
one undercoat and two school board black finishing
| coats on general surfaces | 3 | m2 | 1800 | 5400
| To Summary |  |  | K | 99700
SFS/249/10 LOT 4 3.15
| SHELVING | Qty | Unit | Rate | Amount
CONCRETE WORK
Precast vibrated concrete (Class 21N/mm2/10mm)
built into blockwork
A | 50 x 600 x 1650mm panel shelf (fast wall) | 4 | No | 4500 | 18000
B | 50 x 300 x 1378mm ditto | 24 | No | 2000 | 48000
Plain in-situ concrete (Class 15N/mm2/40mm)
C | Plinth, 100mm thick | 4 | m2 | 9000 | 36000
Reinforced vibrated concrete (Class 21N/mm2/10mm)
D | Suspended slab, 75mm thick | 1 | m2 | 7000 | 7000
Sawn formwork
E | Soffit of slab | 1 | m2 | 4000 | 4000
Blockwork
Stabilised soil blocks bedded and jointed in
gauged mortar (1:10)
F | 140mm thick blockwall in stretcher bond and reinforced
with one layer of "brickforce" reinforcement every fourth
| course | 8 | m2 | 10500 | 84000
Reinforcement
G | Hard drawn mild steel reinforcement (Ref A98) weighing 1.54kg/m2
| in slab | 1 | m2 | 1850 | 1850
PAINTING AND DECORATING
Prepare and apply one water thinned coat and
two coats of interial quality wash & wear silk
white paint on
H | Shelving | 28 | m2 | 1800 | 50400
| To Summary |  |  | K | 249250
SFS/249/10 LOT 4 3.16
SUMMARY
Pages No.
| SUBSTRUCTURE | 3.3 |  |  | 1544150
| ROOF | 3.6 |  |  | 1734575
| EXTERNAL AND INTERNAL WALLS | 3.7 |  |  | 1718700
| WINDOwS AND DOORS | 3.11 |  |  | 1272850
| IRONMONGERY | 3.12 |  |  | 93000
| WALL FINISHES | 3.13 |  |  | 550800
| FLOOR FINISHES | 3.14 |  |  | 52700
| JOINERY FITTINGS | 3.15 |  |  | 99700
| SHELVING | 3.16 |  |  | 249250
| To Final Summary |  |  | K | 7315725
SFS/249/10 LOT 4 3.17

## 2 Hole Pit Latrine block
SAVE THECHILDREN INTERNATIONAL
2 HOLE PIT LATRINE BLOCK
| SUBSTRUCTURE | Qty | Unit | Rate | Amount
Refer SMM paragraph F19(a). It has been assumed that strip
footings, bases, beds and the like within the ground will be
poured against natural ground. If formwork is required to such
surfaces, the contractor must include for same in his
excavations/concrete rates
EXCAVATION
Excavation/Filling (provisional)
A | Excavate trench from reduced level for strip footings
| 0 to 1500mm deep | 3 | m3 | 750 | 2250
B | Excavate pit from reduced level for pit latrine
| 0 to 1500mm deep | 12 | m3 | 750 | 9000
C | Excavate pit from reduced level for pit latrine
| 1500 to 3000mm deep | 12 | m3 | 850 | 10200
D | Excavate pit from reduced level for pit latrine
| 3000 to 4500mm deep | 6 | m3 | 950 | 5700
E | Graded stone filling as filter media, backfilled around chamber
| chamber | 6 | m3 | 8500 | 51000
Excavation/Filling (provisional)
F | Selected earth filling, deposited, spread and
| compacted in 150mm layers around foundations | 4 | m3 | 700 | 2800
Rock excavation (provisional)
G | Extra over excavation for excavation in rock | 6 | m3 | 3500 | 21000
Disposal
H | Surplus excavated material from excavations, transported
a distance average 100 linear metres from excavations and
| deposit in spoil heaps on site | 26 | m3 | 750 | 19500
Hardcore filling to pass a 50mm ring all ways
I | 150mm Thick (consolidated) filling well compacted
| and rolled | 2 | m2 | 550 | 1100
Sand blinding
J | 50mm Bed of sand on hardcore rolled to receive
| damp proof membrane | 2 | m2 | 500 | 1000
Damp proof membrane
H | 250mm Micros (1000 gauge) polythene damp proof
membrane with welted joints, lapped 150mm at joints
| and laid on blinded hardcore | 2 | m2 | 750 | 1500
Ant treatment
I | Saturate surface of hardcore and top of block walls
| with approved ant repellant | 8 | m2 | 850 | 6800
| To Collection |  |  |  | 131850
5.1
| SUBSTRUCTURE | Qty | Unit | Rate | Amount
Sundries
A | Allow for keeping excavations free from water | 1 | Item |  | 0
B | Allow for planking and strutting to sides of excavation | 1 | Item |  | 0
CONCRETE WORK
Precast vibrated concrete (Class 21N/mm2/10mm)
bedded, jointed and pointed in cement mortar (1:3)
C | 50mm "Sanplat" cover slab size 600 x 600mm reinforced with
and including 8mm diameter mild steel bar reinforcement at
150mm centres both ways finished fair on all exposed faces and
| include forming key hole shape and foot rest marks | 2 | No | 3500 | 7000
D | 75mm Suspended slab size 3320 x 1360mm ditto, and include
| forming 100mm diameter hole | 2 | No | 30000 | 60000
Precast vibrated concrete (Class 21N/mm2/10mm)
bedded, jointed and pointed in cement mortar (1:3)
E | 50mm Thick slabs, general size 600 x 600mm having smooth
finish, bedded, jointed and pointed in cement mortar (1:3) laid
to falls and cross falls on sand bed (measured separately),
include for all cutting/or mortar packing to edges and joints
| and allow for pattern as shown on the drawings | 8 | m2 | 5000 | 40000
Plain in-situ concrete (Class 21N/mm2/20mm)
F | Strip footings | 1 | m3 | 80000 | 80000
BLOCKWORK (PROVISIONAL)
Hollow precast cement and sand blocks, filled
solid with concrete (Grade 15/20) in cement
mortar (1:4)
G | 140mm Thick block wall in stretcher bond and reinforced
| with one layer of "brickforce" reinforcement every third course | 14 | m2 | 9500 | 133000
H | Ditto, honey comb | 24 | m2 | 9500 | 228000
| To Collection |  |  |  | 548000
5.2
| SUBSTRUCTURE | Qty | Unit | Rate | Amount
COLLECTION
Page Nos.
| 5.1 |  |  |  | 131850
| 5.2 |  |  |  | 548000
| To Summary |  |  |  | 679850
5.3
| ROOF | Qty | Unit | Rate | Amount
ROOFING
TRAFFIC GREEN CHROMADECK IBR
A | 28 gauge Chromadeck IBR roofing sheets fixed on softwood purlins
accordance with the manufacturer's specifications and
| recommendations | 12 | m2 | 12500 | 150000
B | 450mm girth Ridges |  | m1 | 4000 | 0
C | Ridge Closures |  | m1 | 3500 | 0
CARPENTRY
Unframed
D | 50 x 75mm Rafters/Sprockets | 12 | m1 | 1000 | 12000
E | 50 x 75mm Treated battens/purlins | 18 | m1 | 1000 | 18000
F | 50 x 85mm ditto | 4 | m1 | 1150 | 4600
G | 50 x 150mm Purlins | 24 | m1 | 2000 | 48000
Treated wrot softwood
H | 30 x 250mm Softwood fascia/barge boards | 18 | m1 | 3000 | 54000
Sundries
I | Two strand 4mm Diameter high tensile steel wire tie 1500mm
girth with one end built into block wall and other end around
| roof timber | 8 | No | 985 | 7880
PAINTING AND DECORATING
Prepare, knot, stop, prime and apply one undercoat
and two finishing coats of gloss paint on
J | Timber general surfaces | 10 | m2 | 2400 | 24000
K | Ditto, 200 to 300mm girth | 24 | m1 | 720 | 17280
| To Summary |  |  |  | 335760
5.4
| EXTERNAL AND INTERNAL WALLS | Qty | Unit | Rate | Amount
BLOCKWORK
Stabilised soil blocks bedded and jointed in
gauged mortar (1:10)
A | 140mm Thick block wall in stretcher bond and reinforced with
| one layer of "blockforce" reinforcement every fifth course | 4 | m2 | 10500 | 42000
B | Fair splay cutting | 2 | m1 | 1500 | 3000
C | Extra over block wall for strengthened
| stabilised soil blocks | 8 | m2 | 12000 | 96000
D | 140mm x 290mm girth block wall in stretcher bond and
reinforced with one layer of "blockforce" reinforcement
| every fifth course | 12 | m1 | 1500 | 18000
Selected stabilised soil blocks bedded and jointed
in gauged mortar (1:1:6) - pointing measured
separately
E | 140mm Thick block wall in stretcher bond and reinforced with
| one layer of "blockforce" reinforcement every fifth course | 28 | m2 | 10500 | 294000
F | Fair splay cutting | 2 | m1 | 1500 | 3000
Sundries
G | Form a hole size 600 x 450mm through 140mm block wall
including forming rough arch over and plastering around
| internally in cement mortar (1:4) and make good | 2 | No | 850 | 1700
Damp proof course
H | 3 Ply malthoid damp proof course, over 140mm wide, laid
| under blockwork | 18 | m1 | 250 | 4500
| To Summary |  |  | K | 462200
5.5
| WINDOWS AND DOORS | Qty | Unit | Rate | Amount
CONCRETEWORK
Precast vibrated concrete (Class 21N/mm2/10mm)
bedded, jointed and pointed in cement mortar (1:3)
A | 140 x 150 x 1050mm long lintel, two edges chamfered finished
fair on all exposed surfaces and reinforced with and including
| 6kg of mild steel rod reinforcement and built into blockwork | 2 | No | 2000 | 4000
Doors
Framed, ledged, braced and battened doors shall be
constructed having 45 x 100mm stiles top, centre,
bottom rail and bracing, grooved, morticed, tenoned
and glued together clad one side with 25 x 100mm
tongued and grooved "v" jointed boarding
B | 920 x 2050mm High framed, braced and battened door | 2 | No | 85000 | 170000
Door frames
Rates shall include for lugs welded to back, building into
blockwork and filling cavity with cement and sand (1;3)
Prior to delivery on site, the whole to be treated at works
with one coat red oxide primer
C | Standard metal door frame, size 1000 x 2110mm overall,
suitable for 140mm blockwall, complete with one pair of
| butts | 2 | No | 60000 | 120000
(Accessible to Physical Challnged)
PAINTING AND DECORATING
Prepare, knot, stop, prime and apply one undercoat
and two finishing coats of gloss enamel on
D | Timber framed, ledged, braced and battened doors
| (measured overall) | 4 | m2 | 2400 | 9600
Prepare, prime and apply one undercoat and two
finishing coats of gloss enamel on
E | General surfaces, exceeding 200mm and not exceeding
| 300mm girth | 10 | m1 | 720 | 7200
| To Summary |  |  | K | 310800
5.6
| IRONMONGERY | Qty | Unit | Rate | Amount
Unless otherwise stated, fixing is to timber
Doors
A | "Union AL643-24-77" 3 lever lockset and furniture set | 2 | No | 12500 | 25000
B | "Union AL 8730" rubber door stop, fixed to floor screed | 2 | No | 2000 | 4000
C | "Union AL 8722" rubber tipped hat and coat hook | 2 | No | 2000 | 4000
| To Summary |  |  | K | 33000
5.7
| WALL FINISHES | Qty | Unit | Rate | Amount
INTERNAL
PLASTERWORK
15mm Rendering (1:4) cement and sand, finished
with a wood float
A | Block/concrete wall | 28 | m2 | 1800 | 50400
B | Ditto, ditto | 2 | m2 | 1800 | 3600
PAINTING AND DECORATING
Prepare and apply one water thinned coat and
two coats of internal quality wash "n" wear silk
white on
C | Rendered walls | 32 | m2 | 1800 | 57600
EXTERNAL
BLOCKWORK
D | Point in cement and sand mortar (1:4) recessed joints
| of blockwork | 26 | m2 | 1500 | 39000
PLASTERWORK
15mm Rendering (1:4) cement and sand, finished
with a wood float
E | Block/concrete walls (provisional) | 10 | m2 | 1800 | 18000
F | Block/concrete walls | 1 | m2 | 1800 | 1800
PAINTING AND DECORATING
Prepare and apply two coats styrene acrylic
emulsion clear sealer on
G | Fairface block walls | 36 | m2 | 1500 | 54000
PAINTING AND DECORATING
Prepare and apply two coats of black bituminous
paint on
H | Rendered walls (provisional) | 10 | m2 | 1500 | 15000
Prepare, prime and two coats of external quality
wash "n" wear silk white on
I | Rendered walls | 1 | m2 | 1800 | 1800
| To Summary |  |  | K | 241200
5.8
| FLOOR FINISHES | Qty | Unit | Rate | Amount
PLASTERWORK
1:3 Cement and sand screed finished with a steel
trowel
A | 100mm High skirting with small cove at bottom and
| "V" joint to junction of rendering | 10 | m1 | 350 | 3500
PAINTING AND DECORATING
Washdown, clean and apply two coats of wax
polish on
B | Steel trowelled slabs | 4 | m2 | 900 | 3600
| To Summary |  |  | K | 7100
5.9
| SOIL, WASTE AND VENT SERVICES | Qty | Unit | Rate | Amount
(ALL PROVISIONAL)
This section has been measured from fittings up to
gulley or first manhole
Pipework and fittings
Soil system shall be "Key Terrain 100" PVC to BS 4514
Waste system shall be "Key Terrain 200" UPVC
Diameters stated are outside in accordance with the
manufacturers metric catalogues
Generally joints are solvent welded
Fixing to walls, slabs etc shall be with standard pipe, clips
plugged and screwed
A | 110mm Diameter pipe fixed to brick/concrete wall | 5 | m1 | 1650 | 8250
B | Extra over 150.4 vent cowl | 1 | No | 6500 | 6500
Testing
C | Allow to test the foregoing soil, waste and vent pipework
| installation | 1 | item | 30000 | 30000
D | Form sleeved opening through iron sheets for 110mm diameter
| pipe | 1 | No | 850 | 850
| To Summary |  |  | K | 45600
5.1
SUMMARY
Pages No.
| SUBSTRUCTURE | 5.3 |  |  | 679850
| ROOF | 5.4 |  |  | 335760
| EXTERNAL AND INTERNAL WALLS | 5.5 |  |  | 462200
| WINDOwS AND DOORS | 5.6 |  |  | 310800
| IRONMONGERY | 5.7 |  |  | 33000
| WALL FINISHES | 5.8 |  |  | 241200
| FLOOR FINISHES | 5.9 |  |  | 7100
| SOIL, WASTE AND VENT SERVICES (ALL PROVISIONAL) | 5.1 |  |  | 45600
| To Final Summary |  |  | K | 2115510
5.11

## Material schedule
1 HOLE PIT LATRINE BLOCK - MATERIAL SCHEDULE
|  | Qty | Unit | Rate | Amount
1 | Graded stone filling as filter media, backfilled around chamber. | 9 | tons | 7000 | 63000
2 | 50mm Bed of sand on hardcore rolled to receive DPM. | 1 | ton | 0 | 0
3 | 250mm Micros (1000 gauge) polythene damp proof membrane. | 2 | m2 | 1000 | 2000
4 | Approved ant repellant for hardcore and top of block walls. | 2 | ltr | 900 | 1800
5 | 50mm precast concrete "Sanplat" cover slab size 600x600mm. | 1 | No | 5500 | 5500
6 | 75mm concrete slab size 3320x1360mm with 100mm dia. Hole. | 2 | No | 30000 | 60000
7 | 50mm thick precast concrete slabs, general size 600 x 600mm. | 8 | m2 | 5000 | 40000
8 | Cement for foundations. | 5 | pkts | 7500 | 37500
9 | Sand for foundations. | 1 | ton | 0 | 0
10 | Stone for foundations. | 2 | ton | 15000 | 30000
11 | 140mm thick hollow precast cement and sand blocks. | 300 | no | 750 | 225000
12 | 28 gauge galvanised corrugated iron roofing sheets. | 12 | m2 | 8500 | 102000
13 | 50 x 75mm timber for Rafters/Sprockets/battens and purlins. | 30 | m1 | 1000 | 30000
14 | 50 x 85mm timber for battens/purlins. | 4 | m1 | 1200 | 4800
15 | 50 x 150mm Purlins. | 24 | m1 | 2000 | 48000
16 | 30 x 250mm Softwood fascia/barge boards. | 12 | m1 | 3000 | 36000
17 | 4mm Diameter high tensile steel wire for ties. | 24 | m | 800 | 19200
18 | Roofing nails. | 1.5 | kg | 2000 | 3000
19 | 4" Wire nails. | 2 | kg | 1800 | 3600
20 | 6" Wire nails. | 3 | Kg | 1800 | 5400
21 | Undercoat for roof timbers. | 2 | ltrs | 8500 | 17000
22 | Gloss Paint for roof timbers. | 3 | ltrs | 12000 | 36000
23 | Bricks for toilet superstructure. | 3200 | no | 0 | 0
24 | Cement for toilet superstructure. | 9 | pkts | 7500 | 67500
25 | Sand for toilet superstructure. | 2 | tons | 0 | 0
26 | Brickforce wire. | 4 | rolls | 850 | 3400
27 | 3 Ply malthoid damp proof course, 115mm wide. | 1 | roll | 4950 | 4950
28 | 115 x 150 x 1050mm long precast concrete lintel over door frame. | 1 | No | 2000 | 2000
29 | Mild steel rod reinforcement (Y10) in the lintol. | 6 | kg | 860 | 5160
30 | 920x2050mm High framed, ledged and braced and battened door | 1 | No | 50000 | 50000
31 | Standard metal door frame, size 1000 x 2110mm overall, | 1 | No | 33000 | 33000
32 | Undercoat for door and frame. | 0.5 | ltrs | 8500 | 4250
33 | Gloss Paint for door and frame. | 1 | ltrs | 12000 | 12000
34 | "Union AL643-24-77" 2 lever lockset and furniture set. | 1 | No | 6500 | 6500
35 | "Union AL 8730" rubber door stop, fixed to floor screed. | 1 | No | 1200 | 1200
36 | "Union AL 8722" rubber tipped hat and coat hook. | 1 | No | 1500 | 1500
37 | Cement for plastering, pointing and floor. | 4 | pkts | 7500 | 30000
38 | Sand for plastering, pointing and floor. | 1 | tons | 0 | 0
39 | Interior quality PVA white for plastered walls. | 1 | 5ltrs | 40000 | 40000
40 | Black Bituminous Paint for external plastered plinth. | 1 | ltr | 8000 | 8000
41 | 110mm Diameter pipe fixed to brick/concrete wall. | 3 | m1 | 1000 | 3000
42 | 150.4 vent cowl | 1 | No | 650 | 650
| Sub-Total |  |  |  | 1042910
| Add : 25% Labour charges |  |  |  | 260727.5
Add: 12.5% Admnistration Charges,
| Transport and Supervision |  |  |  | 130363.75
| Grand Total |  |  | MK | 1434001.25

## Sheet1
| MATERIAL SCHEDULE FOR |  |  |  |  | Quantities for 20 Pit Latrines
|  | Qty | Unit | Rate | Amount | Qty | Unit | Rate | Amount
1 | Graded stone filling as filter media, backfilled around chamber. | 9 | tons | 7000 | 63000 | 360 | tons | 7000 | 2520000
2 | 50mm Bed of sand on hardcore rolled to receive DPM. | 1 | ton | 0 | 0 | 20 | ton | 0 | 0
3 | 250mm Micros (1000 gauge) polythene damp proof membrane. | 2 | m2 | 1000 | 2000 | 40 | m2 | 1000 | 40000
4 | Approved ant repellant for hardcore and top of block walls. | 2 | ltr | 900 | 1800 | 40 | ltr | 900 | 36000
5 | 50mm precast concrete "Sanplat" cover slab size 600x600mm. | 1 | No | 5500 | 5500 | 40 | No | 5500 | 220000
6 | 75mm concrete slab size 3320x1360mm with 100mm dia. Hole. | 2 | No | 30000 | 60000 | 80 | No | 30000 | 2400000
7 | 50mm thick precast concrete slabs, general size 600 x 600mm. | 8 | m2 | 5000 | 40000 | 160 | m2 | 5000 | 800000
8 | Cement for foundations. | 5 | pkts | 7500 | 37500 | 100 | pkts | 7500 | 750000
9 | Sand for foundations. | 1 | ton | 0 | 0 | 20 | ton | 0 | 0
10 | Stone for foundations. | 2 | ton | 15000 | 30000 | 40 | ton | 15000 | 600000
11 | 140mm thick hollow precast cement and sand blocks. | 300 | no | 750 | 225000 | 6000 | no | 750 | 4500000
12 | 28 gauge galvanised corrugated iron roofing sheets. | 12 | m2 | 8500 | 102000 | 270 | m2 | 8500 | 2295000
13 | 50 x 75mm timber for Rafters/Sprockets/battens and purlins. | 30 | m1 | 1000 | 30000 | 600 | m1 | 1000 | 600000
14 | 50 x 85mm timber for battens/purlins. | 4 | m1 | 1200 | 4800 | 80 | m1 | 1200 | 96000
15 | 50 x 150mm Purlins. | 24 | m1 | 2000 | 48000 | 480 | m1 | 2000 | 960000
16 | 30 x 250mm Softwood fascia/barge boards. | 12 | m1 | 3000 | 36000 | 240 | m1 | 3000 | 720000
17 | 4mm Diameter high tensile steel wire for ties. | 24 | m | 800 | 19200 | 480 | m | 800 | 384000
18 | Roofing nails. | 1.5 | kg | 2000 | 3000 | 30 | kg | 2000 | 60000
19 | 4" Wire nails. | 2 | kg | 1800 | 3600 | 40 | kg | 1800 | 72000
20 | 6" Wire nails. | 3 | Kg | 1800 | 5400 | 120 | Kg | 1800 | 216000
21 | Undercoat for roof timbers. | 2 | ltrs | 8500 | 17000 | 40 | ltrs | 8500 | 340000
22 | Gloss Paint for roof timbers. | 3 | ltrs | 12000 | 36000 | 100 | ltrs | 12000 | 1200000
23 | Bricks for toilet superstructure. | 3200 | no | 0 | 0 | 64000 | no | 0 | 0
24 | Cement for toilet superstructure. | 9 | pkts | 7500 | 67500 | 260 | pkts | 7500 | 1950000
25 | Sand for toilet superstructure. | 2 | tons | 0 | 0 | 40 | tons | 0 | 0
26 | Brickforce wire. | 4 | rolls | 850 | 3400 | 80 | rolls | 850 | 68000
27 | 3 Ply malthoid damp proof course, 115mm wide. | 1 | roll | 4950 | 4950 | 20 | roll | 4950 | 99000
28 | 115 x 150 x 1050mm long precast concrete lintel over door frame. | 1 | No | 2000 | 2000 | 20 | No | 2000 | 40000
29 | Mild steel rod reinforcement (Y10) in the lintol. | 6 | kg | 860 | 5160 | 120 | kg | 860 | 103200
30 | 920x2050mm High framed, ledged and braced and battened door | 1 | No | 50000 | 50000 | 40 | No | 50000 | 2000000
31 | Standard metal door frame, size 1000 x 2110mm overall, | 1 | No | 33000 | 33000 | 20 | No | 33000 | 660000
32 | Undercoat for door and frame. | 0.5 | ltrs | 8500 | 4250 | 10 | ltrs | 8500 | 85000
33 | Gloss Paint for door and frame. | 1 | ltrs | 12000 | 12000 | 20 | ltrs | 12000 | 240000
34 | "Union AL643-24-77" 2 lever lockset and furniture set. | 1 | No | 6500 | 6500 | 20 | No | 6500 | 130000
35 | "Union AL 8730" rubber door stop, fixed to floor screed. | 1 | No | 1200 | 1200 | 20 | No | 1200 | 24000
36 | "Union AL 8722" rubber tipped hat and coat hook. | 1 | No | 1500 | 1500 | 20 | No | 1500 | 30000
37 | Cement for plastering, pointing and floor. | 4 | pkts | 7500 | 30000 | 120 | pkts | 7500 | 900000
38 | Sand for plastering, pointing and floor. | 1 | tons | 0 | 0 | 20 | tons | 0 | 0
39 | Interior quality PVA white for plastered walls. | 1 | 5ltrs | 40000 | 40000 | 20 | 5ltrs | 40000 | 800000
40 | Black Bituminous Paint for external plastered plinth. | 1 | ltr | 8000 | 8000 | 20 | ltr | 8000 | 160000
41 | 110mm Diameter pipe fixed to brick/concrete wall. | 3 | m1 | 1000 | 3000 | 60 | m1 | 1000 | 60000
42 | 150.4 vent cowl | 1 | No | 650 | 650 | 20 | No | 650 | 13000
| Sub-Total |  |  |  | 1042910 |  |  |  | 26171200
| Add : 25% Labour charges |  |  |  | 260727.5 |  |  |  | 6542800
Add: 12.5% Admnistration Charges,
| Transport and Supervision |  |  |  | 130363.75 |  |  |  | 3271400
| Grand Total |  |  | MK | 1434001.25 |  |  |  | 35985400