# Project Submission Form

# May, 2019

# KAPANDE FOUNDATION

# Improve Sanitary Health for Women and Girls

# Project Proposal

Project Title: 	Improve Sanitary Health for Women and Girls.

Region: 				Sub Saharan Africa

#### Sector:				Health and Education Sector

Country: 				South Africa

Estimated start date:			01/07/2019

Estimated end date:			20/12/2019

Executing Agency:			KAPANDE FOUNDATION

##### Sector:	Sanitary Health

Sub-sectors:	Capacity-building, Literacy program drug control, environment, gender, HIV/AIDS, human rights,

Estimated budget	Year One: ZAR 72 000

Total: ZAR 72 000 (USD 5 000)

OVERVIEW

Since attaining independence from the Apartheid regime, South Africa`s majority of township and rural communities are still struggling to access proper health care and education. The gap between rich and poor has its roots in cultural, ethnic and religious communities underpinned by sovereignty, political and economic issues. In the post-apartheid South Africa of today, unemployment figures have skyrocketed particularly amongst the unskilled and less skilled populace. A lack of health awareness programs, education and skills training still remains as one of the greatest challenges facing South Africa.

The available empirical evidence clearly suggests that South Africa faces a situation of widespread lack of resources to fund procurement of basic sanitary hygiene kits for the less fortunate. The highest number of poor families are either illiterate or unskilled and unemployed, especially in the rural areas, among women, men and marginalized groups. The illiteracy rate is estimated to be above 90 percent or even more, one of the highest in Africa. It has been found that there is a latent demand for education among the poor, especially women and girls, who not only realize the value of health education, but want to attend schools and literacy classes in order to lead a better life. They acknowledge the empowering role of education; it will help to alleviate the poverty that the majority of South Africans live in. They will in turn be able to afford basic hygiene kits for themselves and their families.

In this context, literacy and non-formal education should serve socially constructive purposes to prepare South African citizens to actively participate in the process of health, social, cultural and economic development.  It should contribute positively towards bridging the wealth gap and building a culture of solidarity and tolerance within a framework of multi-ethnicity and cultural and linguistic diversity.  Policy makers and international organizations need to rethink the role of health, literacy and non-formal adult education so that they impart not only knowledge and skills, but more importantly, social inclusion.

The prime objective of this project, is to help the whole nation to establish a framework that reaches out to needy women and girls in the country and enable them to easily access sanitary pads; secondly, to teach these women and girls about sexual health and prevention of infectious diseases through non-formal education. The focus of the project will be to assist the local community leaders in training and developing a provincial body of education, health planners and trainers who will be in charge of implementing an ambitious community health programs, with learning objectives for each province and eventually, each town and rural area.

This proposed project aims at harnessing strong political support from intellectuals, politicians, civil society, NGOs, and the international community. It will also require strong communication and information media involvement in order to disseminate social inclusion values to all sectors.

Through various survey-based activities, it is expected that the proposed project would provide the much-needed relief in curbing the shortage of sanitary hygiene kits for the less fortunate. The project will examine programs designed specially to meet the needs of adolescent girls, and of women. This project will particularly look into ways these programs reinforce formal health education, creating thus a more favorable learning environment conducive to full participation and better achievement.

OBJECTIVES

The overall objective of the project is to provide the basis for creating a channel for alleviating and providing relief to women and girls by providing sanitary wear. Enforcing a culture of health awareness in institutional capacities at local, provincial and national levels in policy design, implementation, monitoring and evaluation of a good sanitary health program.

Specific objectives are:

- To provide, in a short period of time, the knowledge-base required for designing and implementing large scale, effective sanitary wear distribution programs based on community mobilization.

- To support innovative projects and programs with a view to reducing the alarming lack of sanitary pads rate in the country and promote “Sanitary health”.

- To monitor projects and programs leading to a national sanitary pad ease of access system and health education program.

# ACTIVITIES

The overall objective of the project is to provide the basis for creating a channel for alleviating and providing relief to women and girls by providing sanitary wear. Enforcing a culture of health awareness in institutional capacities at local, provincial and national levels in policy design, implementation, monitoring and evaluation of a good sanitary health program.

Specific objectives are:

- To provide, in a short period of time, the knowledge base required for designing and implementing large scale, effective sanitary wear distribution programs based on community mobilization.

- To support innovative projects and programs with a view to reducing the alarming lack of sanitary pads rate in the country and promote “Sanitary health”.

- To monitor projects and programs leading to a national sanitary pad ease of access system and health education program.

KAPANDE FOUNDATION will provide technical support and assist the provincial health department in reviewing past experiences and on-going models of sanitary pads distribution and health education including those in use by the local communities. It will help the Department in identifying and training a core group of volunteers, health planners and promoters with a view to first undertake a country-wide sanitary health survey and then assess implementation strategies on making the system work particularly for out-of-school girls and women. Another critical activity which is foreseen in this project is to explore ways and means for intensive advocacy to persuade political leaders, policy-makers and administrators to reform the system. The core group of health planners and promoters, in close cooperation with provincial decision makers and, will be in charge of conducting the survey, undertake advocacy activities and plan the implementation of the first phase of the sanitary health programme.

Based on the success of Community Learning Centers in the KwaZulu Natal province KAPANDE FOUNDATION will facilitate networking for promoting better policy dialogue and more cooperative and collaborative approaches. These will be channeled in efforts aimed at eradicating poverty and reducing ignorance and lack of sanitary and sexual health awareness. Having greater impact on the government’s decisions at the local community and provincial levels with a focused attention to the re-insertion of girls and women into a health educational life.

We would want to establish framework that promotes Self-reliance initiatives such as small-scale reusable/washable sanitary pads production. We would also want to donate machinery to the community such that they can implement a project of this nature.

The project will thus consist of a provincial planning meeting, technical expert meetings, provincial training workshops, case studies and at a later stage a provincial follow-up and evaluation meeting. In summary, KAPANDE FOUNDATION`s contribution will include:

- Technical assistance for training and monitoring;

- Development and distribution of prototype training/learning materials;

- Establishment of provincial and sub-provincial networks;

- Helping with the creation of a favourable environment conducive to poverty alleviation; promotion of informal and community-based approaches capitalizing on capacities of the rural poor and aiming at self-reliance;

- Assistance in the development of a holistic community information system to enable “one-step” access to relevant data and information;

- Encouragement of bottom-up, people-centred community initiatives, alternative modes of education (e.g. multi-purpose comprehensive community learning centres), and social support services;

- Harnessing the support of media such as radio, for the support and development of sanitary pads distribution and health education activities, by paying full attention to the ethnic diversity of the country; and

- Networking and sharing among government and non-government institutions and community-based organizations.

Specific Activities:

  - Provincial Planning Meeting on the planning and management of sanitary pads distribution and sanitary health education, programmers and activities will be organized to (i) clarify the main issues and conceptual/operational framework of the project; (ii) share the national experience and review the state-of-the-art of and progress made in the policies, approaches and strategies for planning and implementing sanitary pads distribution and sanitary health education programmers and activities (frequency, quality and reliability data collection and analysis; and (iii) initiating networking among NGOs and other health stakeholders.

  - Identification and training a core group of health planners, trainers and promoters to undertake a rapid survey i) on sanitary health levels (random- survey and other techniques), if possible, in all communities and of the province, ii) available teacher potential, iii) available local facilities, and iv) enlisting local support from elders and village leaders for sanitary health programmers. The work results of these sanitary health promoters and pioneers, especially their advocacy achievements, will be crucial for the further success of the sanitary health programmed.

  - Scanning Exercise of already existing sanitary health programmers will be undertaken to identify projects and programmes with potential for scaling up or for dissemination of lessons learnt. Based on the scanning exercise, some selected projects will be subject to an in-depth analysis for providing inspiration and models for “how to do it”. The results of the survey and the scanning exercise will both be used for assisting the provincial authorities with developing a realistic provincial sanitary health plan, with short- and medium-term objectives.

  - Technical Workshop will involve the development of a set of “guiding materials” for training health personnel and community development agents in the planning and management of integrated sanitary pads distribution and sanitary health education programmers as the key strategy for value creation. Furthermore, it is for promoting democratic social cohesion, building a culture of peace, solidarity and tolerance within a framework of multi-ethnicity and cultural diversity and for poverty alleviation.

  - Implementation of Sanitary pads distribution and Sanitary health education Programmes will begin from an early stage through support to existing innovative programmes that are willing to work within the parameters described above, including communication promoting social cohesion, peace-building, health etc, and linkage to media such as radio programmes, and with a community-based approach.  The provincial programme will subsequently be developed based on policy criteria developed by the Department of Women.

  - NFE Data Collection and Analysis mechanisms will be set up as the project develops, but only after the initial phase of the first survey and first sanitary health activities have been undertaken and concluded; it is planned to identify and train a core group of planners, statisticians and data collectors, so as to lay the foundations for a comprehensive sanitary health system, enabling the provincial health planners and administrators at a later stage, to collect, assimilate, analyse and report systematically both the quantitative and qualitative information for the planning of sanitary health follow-up activities at various levels of administrative hierarchy.

An indicative time frame for the activities to be implemented during the project is shown below.

June 2019	Provincial Planning Meeting;

Training of core group of health planners, trainers and promoters, and beginning of provincial-wide survey;

Beginning of advocacy work for sanitary health in provincial capitals, joint meetings with village and tribal elders;

Establishing of Sanitary health committees and centers in provincial capitals.

July - August 2019	Technical expert meeting for strengthening (Assessment of hardware, software furniture, stationery and other logistic support), designing/redesigning the provincial sanitary health framework, materials production and for developing teaching-learning resources for CLCs.

Sept 2019 	Trial of innovative approaches in selected CLCs and other health centers, as identified in first survey; focus will be to multiply these centers as much as possible.

October 2019	Building national capacity of health planners, administrators, teachers/volunteers/facilitators and community leaders.

Nov 2019 – Dec 2019	Design/redesign the provincial sanitary health framework and develop teaching-learning resources for CLCs.

Evaluation and synthesis of project activities during the first six months. Launch of provincial sanitary pads distribution and sanitary health education programs, under the auspices of the Department of Health, Department of Women and Department of Education.

| Item | Description | Amount |
| --- | --- | --- |
| 1 | Training of core group of health and education planners/trainers | $ 70 |
| 2 | Provincial survey and advocacy | $ 10 |
| 3 | Establishing community sanitary health centers | $ 100 |
| 4 | Review of framework on sanitary health program at the district levels | $ 20 |
| 5 | Procurement of sewing and overlocking machinery | $ 3000 |
| 6 | Procurement of fabric and textile material | $ 1000 |
| 7 | Manufacturing and distribution of Sanitary pads | $ 300 |
| 8 | Transport and logistics | $ 500 |
|  |  | $ 5 000,00 |

- Total (1 year) USD 5 000 (ZAR 72 000)

# OUTPUTS

The proposed project is a modest effort in manufacturing and distributing reusable/washable sanitary pads to women and girls as well as educating them of sanitary health issues and creating awareness of the same. We also intend to train Self Reliance skills in the process and to analyze and identify critical issues and problems related to the health and education of millions of children, youth and adults. Particularly girls and women, who are not or have not been beneficiaries of the health and skills training system. The project intends to provide a first-hand account of issues and challenges related to planning and management of sanitary health, identifying projects that work and can be easily scaled up and disseminated. In particular the results and outcomes of this undertaking, linking both upstream and immediate implementation, will include:

- The preparation of large-scale project and program proposals which are likely to attract and mobilize sufficient funds and which will be based on (i) a more detailed needs analysis; (ii) analysis of existing sanitary health mechanisms - what works in sanitary health programs in South Africa; and (iii) as assessment of the capacities of South African governmental and non-governmental organizations, provincial and local capacities and needs.

- An in-depth analysis of problems and issues related to access and quality of girls and women health education and innovative initiatives to be taken for their integration in the mainstream of schooling and social life;

- A reference document for consultation with the national planners and policy-makers, selected academia, NGOs, private bodies, UN and other bilateral development partners for raising and seeking technical and financial commitments;

- Multimedia sanitary health/training materials developed, specially by involving radio and developing existing projects.

- Provincial/district networks strengthened;

- Holistic information/data collected on sanitary pads distribution and sanitary health education experiences and development opportunities; locally specific development needs of the poor assessed; and

- Local and provincial facilitators of community-based sanitary health programmers trained and retrained;

- Consolidation of on-going sanitary health programmes and initiating of innovative pilot projects and a provincial sanitary health programmes.

.

Beneficiaries

- Basic health and education planners, administrators, and project managers, practitioners, trainers and facilitators at all levels.

- Key policy decision-makers, trainers, leaders of NGOs and village elders and /or tribal leaders who are involved in designing and implementing, monitoring and evaluating sanitary health programs

- Rural and urban poor, the orphaned and vulnerable, especially adolescent girls and women.