**State of Construction Bogoya School**

The construction of the school of Bogoya began in 17 March 2019 with the launching of the first one with the participation of the population and the representatives of the administrative and customary authorities of the locality.

In a month and a half, the school's construction activities are satisfactory and we note that the objectives set at the beginning are largely achieved.

Details of achievements   :

1. Drilling with Volonta system   : 100% with water analysis ready for use and billed sale
2. School with 3 classes + store and office   is at 49, 45 % of achievement
3. Latrines   0%
4. Equipment is 0%

Confer table of realization below updated following the payment ( 1   950   000 FCFA)   of Mr XXXX of May 16 , 2019

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **No.** | **Topics** | **Total amount**  **project** | **3% discount** | **Grand total** | **Completed** | **Completion rate** | **Miss to win** |
| AT | Construction 3 classes + Store + office | 15   754,995 | 472,650 | 15   282,345 | 7   600   849 | 49, 45 | 7   681496 |
| B | Drilling will | 5   805   000 | 174 150 | 5   630,850 | 5   630,850 | 100% | 0 |
| C | Latrines | 1   832,580 | 54,977 | 1   777,603 | 0 | 0% | 1   777,603 |
| D | Class benches tables | 1   607,425 | 48,222 | 1   559,203 | 0 | 0% | 1   559,203 |
| **TOTAL** | | **25**  **000,000** | **750,000** | **24**  **250,000** | **13**  **23** **1** **699** | **54, 56** **%** | **11**  **018 301** |

-          Continue the work quickly before the rainy season because the aggregates (sand, pebble, water) will be difficult to collect by the population that will be working in the camps