Strategic Plan &

Resource Mobilization Strategy

2019

Prepared by the:

Secretariat

Kilombero Organization for community Development (KOCD)

P.O. Box 624

Ifakara Morogoro

1.6

Contents

Introduction	3

1.1 Vision:	3

1.2 Mission Statement	3

1.3 Core Values:	3

1.4 Key Focus Areas:	3

1.5 Strategic Goals:	3

1.6 Strategic Objectives:	4

1.7 KOCD five strategic Community programs/Projects set to be implemented this year 2019	4

1.8   Approach and Methodology	6

1.9   Situational Analysis	7

1.10   SWOC Analysis	7

1.11        Strategic Actions, KPIs, Timeline and Responsible Person	11

1.12        Implementation Plan	13

1.13    Costing the Strategy	15

2       Resource Mobilization Strategy	17

2.1  Need for a Resource Mobilization Strategy	17

2.2   Resource Mobilization Approach and Methodology	17

2.3   Resource Mobilization Vision	18

2.4 Resource Mobilization SWOC Analysis	18

2.5    KOCD Resource Mobilization Strategy Framework	20

2.6    Income Generating Activities Evaluation	24

2.7    Risks and Mitigation Plan	26

PLAN FOR 2019

# Introduction

For easiness of implementing the Strategic Plan of KOCD, Management in collaboration with Board of directors and members managed to develop strategic activities in yearly basis. This document is the plan drawn from Strategic Plan to implement Strategic activities for year 2019 in order to attain the goal of Strategic Plan   (2017-2021)

## 1.1 Vision:

” Our vision is “To be a standard of excellence in community service provision to women and children in Tanzania.”

1.2 Mission Statement:

Our mission is “to collaborate with government, communities, development partners, and like-minded organizations to improve women and children’s living standards through education and training, health services, and advocacy.”

## 1.3 Core Values:

In delivering our strategy we will  be guided by the following principles:

| Value | Description |
| --- | --- |
| Teamwork | Our team is supportive of each other and loyal to one another |
| Good governance | We shall adopt the best possible process for making and implementing decisions |
| Respect | We treat our team members and all stakeholders with mutual respect |
| Accountability | We accept responsibility for our actions |

## 1.4 Key Focus Areas:

We identified 4 KFAs: resource mobilization, increase organizational governance, efficiency in service delivery, and stakeholders’ management.

.

## 1.5 Strategic Goals:

This strategy responds to 4 strategic goals that include:

- Establish sustainable resources for KOCD

- Improved decision making and quality service delivery

- Quality education, health services and advocacy rendered to woman and children in Tanzania

- Improved relationship and collaboration with stakeholders

## 1.6 Strategic Objectives:

To ensure that our strategic goals are achieved, the following strategic objectives were identified:

- Developed and improved organization polices by May, 2019

- Delivered 5 community programs that cater to women and children by 2019

- Developed a Stakeholders Management Strategy by June 2019

- Mobilized 5 key stakeholders (LGA, donor, community, CSOs, private companies)

- Established   and  continuously run 4 IGAs   2019

## 1.7 KOCD five strategic Community programs/Projects set to be implemented this year 2019

- Improving Agricultural Service Delivery through Social accountability monitoring to local villagers in kilombero District.

Under this  Project KOCD  aims to mobilize, empower and impart knowledge to communities, farmers’ cooperative societies, media, and other stakeholders and hence form a task force to influence Local Government Authority to be transparent and accountable and uphold rule of law and procedures in all issues of public resources.

The project goal is to contribute in improved good governance at government and its outcome is Local Government Authorities (LGAs) deliver improved quality services.

To achieve the above outcome and goal, beneficiaries, duty bearers including councilors as well as other stakeholders such as farmers’ cooperative societies, media and members from CSO networks will be empowered through training and capacity building on Social Accountability Monitoring (SAM) and mostly on their roles and responsibilities. Project will still be conducted in the wards of kalengakelu, Ching’anda, Chisano Mchombe, Mkula and Sanje. The period  of the project will be  twelve months duration and expected to start on June, 2019.

Direct beneficiaries of the project will be   355 (Male 172 , Female 183),villagers 48 government officials and 32 Community leaders while Indirect beneficiaries will be more than 22,000 people whereas 13500 are men and 8500 women who will benefit from this project indirectly from those five wards.

Project will be implemented in a participatory approach between villagers, government officials; public leaders, SAM team, Media, agriculture sector stakeholders, youths, women, farmers associations and others are involved with Kilombero Organization for Community Development (KOCD) in the systematic organized strategies and activities so as to achieve the set goal.

- Water, Sanitation and Hygiene    Project for 3 kilombero District primary schools.

Under this Programme KOCD intends to build 3 furnished sanitary facilities for 3 selected primary schools in kilombero, Tanzania and save 2000 pupils from sanitary related diseases such as diarrhea, urinary transmission infection and cholera. In addition to the construction of sanitary facilities, the pupils from these schools will get knowledge on   personal hygiene and safe extra disposal to maintain healthy environment.

Reduce maternal anemia and childhood stunting by providing Nutritional Education to Pregnant and lactating women in kilombero District.

The Program goal is to improve the nutritional status of children, pregnant and lactating women in Tanzania in reducing maternal anemia and child stunting by 20% in Morogoro region. In its focus of reducing childhood stunting and maternal anemia, KOCD will implement the following Intermediate results (IR)

IR1:  Increased investment in Agriculture and Nutrition related activities                                                  IR2:  Improved access to diverse and quality food

IR3:  Improved Related Nutrition Behavior                                                                                                      IR4:  Improvements in provision of Maternal and Child Health Services                                                                 IR5:  Improved Enabling Policy Environment for both Agriculture and Nutrition

- Empowering   at risk women and youth through Horticulture, beekeeping and SILC Education in kilombero District.

In an effort to boost households income for poor families in kilombero District   KOCD plans to   conduct training on Horticulture, beekeeping and SILC education to the community with the benefiaries being poor households. About 200 women and 100 men will benefit from this endeavor.

- Mobilization of tree planting to the community and schools in kilombero District.

In order to respond to negative climatic changes and preserve the environment, KOCD plans to launch campaign and mobilize the community of kilombero district to plant trees to households, and Schools .Students and the community will be educated on the impacts of climatic changes resulting from human activities and will be distributed with various trees to plant in selected schools and to community.

## 1.8   Approach and Methodology

An 8-step strategic thinking and planning process was incorporated to develop KOCD’s 2019  Strategic Plan.

Strategic thinking and planning are distinct but interrelated and complementary thoughtprocesses, therefore all 8-steps shown in Figure 1were addressed in order to develop a new successful strategic plan. A description of each step is provided below:

- Built a shared understanding of strategy and the strategy making process

Before delving into the development of a new strategic plan,it was important for KOCD management and key personnel staff to first have certain fundamental strategic knowledge; namely a shared understanding of what a strategy is and the strategy making process. This involveddifferentiating between strategic thinking, strategic planning, and strategic management, understanding the importance of strategic formulation and execution, andunderstanding the barriers to an effective strategy execution.

- Clarified the core purpose and principles of the organization (vision, mission and core values)

To ensure that ourorganizational aspirations are addressed in the strategic plan, we developed avision (that states where we want our organization to be in the future) and a mission statement(thatstates why our organization exists and our key services). We also developed core values that highlight our organizations moral standard of behavior.

- Assessed both internal and external factors with strategic relevance to KOCD

We analyzed the internal and external factors that affect KOCD’s success and growth using a SWOC analysis. A SWOC analysis refers to the organizations strengths, weaknesses, opportunities and challenges, with the strengths and weaknesses focusing on the internal capabilities and the opportunities and challenges focusing on external factors that affect the organizations operations.

- Identified strategic issues (key focus areas) and formulated strategic responses (strategic goals and objectives)

We identified 4 key focus areas that are crucial to KOCD’s strategic success, and then formulated strategic goals and objectives. The strategic goals and objectives are statements of key priorities for the organization and should be the basis for everything the organization does.

- Developed strategic actions and performance targets and indicators

We developed strategic actions, which are the path that KOCD will follow to achieve its strategic goals and objectives. We then set performance targets (KPIs) to evaluate the success of KOCD in meeting the set strategic goals and objectives.

- Costed the strategy to determine an indicative budget for the strategic actions identified

We discussed and analyzed the various costs necessary to ensure effective implementation of key action items within our strategy. It should be noted that a more detailed budget is provided in the work-plan, not the strategic plan.

- Developed an implementation plan

In the implementation plan we set yearly targets for the strategic actions and assigned appropriate members of staff to take responsibility for each strategic action

- Identified risks and developed a mitigation plan

We identified potential risks and the level of impact that they could have on our strategy (high, medium or low). We also developed mitigating measures for each identified risk, and appointed an appropriate member of staff in regards to accountability. It should be noted that we developed a comprehensive risk and mitigation plan, combining both the strategic plan and resource mobilization strategy.

# 1.9   Situational Analysis

SWOC analysis is a strategic planning method used to research external and internal factors which affect an organizations success and growth

## 1.10   SWOC Analysis

We provided a brief definition of what a SWOC analysis is in the Approach and Methodology section of this report, howeverSWOC can be furtherdefined as follows:

- Strengths – Conditions that we can build/maintain/leverage upon to facilitate successful execution of our strategy. Strengths are also internal, positive factors that can leverage opportunities presented to KOCD.

- Weaknesses – Our current negative characteristics that need to be remedied, stopped or improved upon for successful execution of the strategy.

- Opportunities – Elements in the external environment that an organization can take advantage of. Opportunities need to be prioritized and optimized towards effective execution of the strategy.

- Challenges – External negative factors that could prevent/limit the execution of our strategy

The results of our SWOC analysis are shown in the table below:

| Strengths | Opportunities |
| --- | --- |
| Capacity to deliver Programs to the community Qualified staff | Existence of government policies that support our work Presence of development partners Increasing need for KOCD services, particularly amongst women and children |
| Weaknesses | Challenges |
| Donor dependency Policy implementation is poor Poor organizational governance | Interference of politics in social development Community conflicts |

The table below outlines the actions that need to be pursued, maintained, or improved in regards to each point identified in the SWOC analysis:

| Strengths |
| --- |
| Strength | Details | Actions to maintain | Under threat |
| Capacity to deliver Programsl to the community | KOCD have professional staff, adequate office equipment (secretarial tools, generator etc.), and motorcycles for field activities | Maintain good condition of all office equipment and motorcycles |  |
| Qualified staff | KOCD has capable and experienced staff to implement its core activities. When extra need arises, we outsource professional expertise within our collaboration network | Maintain good relationships with experts in our collaboration network |  |
| Weaknesses |
| Weakness | Details | Action to improve | Impact |
| Donor dependency | The institutional capacity of KOCD is not yet sustainable given the fact that our organization is almost entirely dependent on donor funding. | Need to diversify our sources of income by assessing our IGAs |  |
| Policy implementation is poor | KOCD are struggling to ensure that all polices are implemented, furthermore our documented polices are outdated | Need to establish new policies for the period -2019 and ensure they are all implemented |  |
| Poor organizational governance | KOCD currently have a poor organizational structure in regards to effective decision making | Need to establish strong and effective communication between the different organizational organs |  |
| Opportunities |
| Opportunity | Details | Needed actions | Impact |
| Existence of government policies that support our work | The Tanzanian government has been implementing liberalizing policies that have facilitated a relaxation of government control over the freedom to associate | KOCD need to closely communicate with government leaders to enhance good corporation |  |
| Presence of development partners | There are local and international development partners who are willing to support KOCS programs | Engage in strategic discussion with potential partners |  |
| Increasing need for KOCD services, particularly amongst women and children | There is a growing demand for KOCD services in the Morogoro region particularly amongst women and children | Continue offering programs and activities that cater to this particular target audience |  |
| Challenges |
| Challenge | Details | Action to improve | Impact |
| Interference of politics in social development | NGOS and CSOs are governed by the Societies Ordinance 1954 which gives the Registrar the power to deregister any NGO/CSO whenever they deem fit | KOCD need to make sure that their work does not involve political related activity that could be deemed as a threat to government |  |
| Community conflicts | Fighting between communities occasionally takes place which hinders our operations, as we aim to involve all community members | Hold community meetings whereby community conflicts can be resolved in a timely and diplomatic manner |  |

| 1.11 Strategic Actions, KPIs, Timeline and Responsible Person |  |
| --- | --- |
|  |  | Key Performance Indicators (KPI) |  |  |
| Strategic Objective | Strategic Action |  |  | Responsible |
|  |  |  | 2019 |  |
| SO2. Established and continuously run 4 IGAs up to Dec ,2019 | Allocate required resources (e.g. man power, money etc.,) | Resources allocated |  | Board member, Program Manager and Resource Mobilisation officer ,finance officer |
|  | Identify and generate income 4 IGAs per annum | 4 IGAs identified and income generated for year 2019 | 4 | Program Manager, Resource Mobilisation officer ,finance officer ,Board member |
| SO3. Developed and improved organization polices by June 2017 | Carry out a needs assessment to establish which old policies to keep, and which new policies to include | Policy assessment done | 1 |  |
|  | Document all policies that shall be incorporated in KOCD going foreword | Policies drafted | 1 |  |
|  | Have new policy document authorised | Official KOCD policies developed | 1 | Board member, Finance Officer, Secretariat |
| SO4. Improved the coordination and effectiveness between board members and the secretariat by 2021 | Congregate board members and the secretariat to establish communication lines between the two departments | Official communication channels between the two departments developed |  | Board members and Secretariat |
|  |  | M&E of the board and secretariat bi-annually done | 2 | Organisation Chairman |
|  | Monitor and evaluate the board and secretariat on policy implementation |  |  |  |

Table 3: implementation actions

| Strategic Objective |  | Key Performance Indicators (KPI) |  |  |
| --- | --- | --- | --- | --- |
|  | Strategic Action |  | 2019 | Responsible |
| SO6. Delivered 5 community programs that cater to women and children by 2019 |  |  | 5 | Board Member ,Program manager ,finance Officer ,executive Director |
|  | Assess, discuss and develop programs that cater to women and children | Program Assessment Done |  |  |
|  |  | 5 programs implemented by 2019 | 5 |  |
|  | Implement identified programs |  |  |  |
| SO7. Developed a Stakeholders Management Strategy by may 2019 | Identify 5 stakeholders that KOCD would like to manage their relationship with | 5 stakeholders identified | 5 | Program Manger ,M&E officer |
|  | Draft stakeholders management strategy | Draft completed | 1 | Program Manger ,M&E officer |
|  | Have stake holder management reviewed and approved | Stakeholders management strategy implemented | 1 | Board members |
|  | Monitoring and evaluating stakeholders strategy | M&E done bi-annually | 1 | M&E |
| SO8. Mobilized 5 key stakeholders (LGA, donor, community, CSOs, private companies etc.) | Networking with at stakeholders | Communication strengthened with at least 5 stakeholders | 5 | Program Manger ,M&E officer |
|  | Incorporate 5 stakeholders in organization programs by 2019 | At least 5 stakeholders directly involved in organization programs by 2019 | 5 | Program Manger ,M&E officer |
| 1.12 Implementation Plan |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Monthly Targets year 2019 |  |
| Strategic Objective | Strategic Action |  | Responsible |
|  |  | JAN | FEB | MARCH | APRIL | MAY | JUNE | JULY | AUG | SEPT | OCT | NOV | DEC |  |
| SO2. Established and continuously run 4 IGAs up to Dec,2019 | Allocate required resources (e.g. man power, money etc.,) | XXXX | XXXX | XXXX | XXXX | XXXX |  |  |  |  |  |  |  | Board member, Program Manager and Resource Mobilisation officer ,finance officer |
|  | Identify and generate income 4 IGAs per annum |  |  |  |  |  | XXX | XXX | XXX | XXX | XXX | XXX | XXX | Program Manager, Resource Mobilisation officer ,finance officer |
| SO3. Developed and improved organization polices by June 2017 | Carry out a needs assessment to establish which old policies to keep, and which new policies to include | XXX | XXXX | XXXX | XXXX | XXXX |  |  |  |  |  |  |  |  |
|  | Document all policies that shall be incorporated in KOCD going foreword |  |  |  |  | XXX |  |  |  |  |  |  |  |  |
|  | Have new policy document authorised |  |  |  |  | XXXX |  |  |  |  |  |  |  | Board member, Finance Officer, Secretariat |
| SO4. Improved the coordination and effectiveness between board members and the secretariat by Dec,20 19 | Congregate board members and the secretariat to establish communication lines between the two departments | XXXX | XXXX | XXXX | XXXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | XXXX | Board members and Secretariat |
|  |  |  |  |  |  |  |  |  |  |  |  |  | XXXX | Organisation Chairman |
|  | Monitor and evaluate the board and secretariat on policy implementation |  |  |  |  |  | XXXX |  |  |  |  |  |  |  |
| Strategic Objective |  | Yearly Targets 2019 |  |
|  | Strategic Action | JAN | FEB | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPT | OCT | NOV | DEC | Responsible |
| SO6. Delivered 5 community programs that cater to women and children by 2021 |  | XXXX | XXXX | XXXX | XXXXX | XXXX |  |  |  |  |  |  |  |  |
|  | Assess, discuss and develop programs that cater to women and children |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | XXXX | XXXX | XXXXX | XXXXX | XXXX | XXXX | XXXX | Board Member ,Program manager ,finance Officer ,executive Director |
|  | Implement identified programs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SO7. Developed a Stakeholders Management Strategy by June 2019 | Identify 5 stakeholders that KOCD would like to manage their relationship with |  |  |  |  | XXXX |  |  |  |  |  |  |  | Program Manger ,M&E officer |
|  | Draft stakeholders management strategy |  |  |  |  | XXXXX |  |  |  |  |  |  |  | Program Manger ,M&E officer |
|  | Have stake holder management reviewed and approved |  |  |  |  | XXXXX | XXXX |  |  |  |  |  |  | Board member |
|  | Monitoring and evaluating stakeholders strategy |  |  |  |  |  | XXXX | XXX | XXXX | XXXXX | XXXX | XXXX | XXXX | M&E |
| SO8. Mobilized 5 key stakeholders (LGA, donor, community, CSOs, private companies etc.) | Networking with stakeholders |  |  |  |  | XXXX | XXXXX | XXXX |  |  |  |  |  | Program Manger ,M&E officer |
|  | Incorporate 5 stakeholders in organization programs by Dec,2019 |  |  |  |  |  | XXXX | XXXX | XXXXX | XXXX | XXXXX | XXXX | XXXX |  |

## 1.13    Costing the Strategy

| Strategic Objective | Strategic Action | Budget (TZS) |
| --- | --- | --- |
| SO2. Established and continuously run 4 IGAs up to Dec,2019 | Allocate required resources (e.g. man power, money etc.,) | 0 |
|  | Identify and generate income from 4 IGAs | 22,850,000 |
| SO3. Developed and improved organization polices by May 2019 | Carry out a needs assessment to establish which old policies to keep, and which new policies to include | 0 |
|  | Document all policies that shall be incorporated in KOCD going foreword | 0 |
|  | Have new policy document authorised | 0 |
| SO4. Improved the coordination and effectiveness between board members and the secretariat by Dec, 2019 | Congregate board members and the secretariat to establish communication lines between the two departments | 0 |
|  | Monitor and evaluate the board and secretariat on policy implementation | 0 |
| SO6. Delivered 5 community programs that cater to women and children by Dec ,2019 | Assess, discuss and develop programs that cater to women and children | 32,000,000 |
|  | Implement identified programs | 552,439,078 |
| SO7. Developed a Stakeholders Management Strategy by june 2019 | Identify 5 stakeholders that KOCD would like to manage their relationship with | 300,000 |
|  | Draft stakeholders management strategy | 300,000 |
|  | Have stake holder management reviewed and approved | 300,000 |
|  | Monitoring and evaluating stakeholders strategy | 1,000,000 |
| SO8. Mobilized 5 key stakeholders (LGA, donor, community, CSOs, private companies etc.) | Networking with at stakeholders | 1,000,000 |
|  | Incorporate 5 stakeholders in organization programs by 2019 | 2,000,000 |
| Total Estimated Cost | 612,189,078 |
| Estimated Overhead Cost (30% of estimated cost) | 183,656,723 |
| Total Estimated Cost | 795,845,801 |

Table 4:costing strategy

# 2       Resource Mobilization Strategy

## 2.1  Need for a Resource Mobilization Strategy

Resource mobilization refers to all activities involved in securing new and additional resources for an organization, and also involves maximizing and making better use of existing resources. We recognise the importance of an RM strategy in order to ensue sustainability of our services, thus we shall therefore develop a RM plan alongside our 2017-2021

## 2.2   Resource Mobilization Approach and Methodology

A 6-step approach was used to develop KOCD’s Resource Mobilization Strategy.

A 6-step approach similar to the Strategic thinking and planning process used in the Strategic Plan was used to develop our resource mobilization strategy. A description of each step is provided below:

- Built a shared understanding of a resource mobilization strategy

Before delving into the development of a resource mobilization strategy, it was important for KOCD management and key personnel staff to understand why it is key to develop a RM strategy to support our 2017-2021 Strategic Plan.

- Clarified the vision of KOCD in regards to resource mobilization

We developed a vision for KOCD, addressing our future desired state in regards to resource mobilization.

- Assessed the internal and external factors that affect KOCD in being able to implement the RM plan

The internal and external factors that affect KOCD’s ability tosuccessfully implement a resource mobilization strategy were assessed via a SWOC analysis (strengths, weaknesses, opportunities and challenges).

- Developed a resource mobilization strategy framework

We developed a RM framework that includes key focus areas, strategic objective and actions, key activities, key performance measures (KPIs) a budget and assigned appropriate members of staff to take responsibility for each strategic action.

- Identified and evaluated Income Generating Activities (IGAs)

We conducted a comprehensive analysis of Income Generating Activities (IGAs) to ensure that the Resource Mobilization Strategy effectively supports our sustainability. We also examined the level of risk presented by each IGA.

- Developed a Financing Strategy for the identified IGAs

We determined sources of income to finance the identified IGAs

## 2.3   Resource Mobilization Vision

RM Vision

Our vision is “to be a self-reliant organization in Tanzania”

## 2.4 Resource Mobilization SWOC Analysis

We provided a definition of what a SWOC analysis is in our Strategic Plan; the same definition shall be applied to our RM strategy. The results of our SWOC Analysis are shown in the table below:

| Strengths | Opportunities |
| --- | --- |
| Capacity to execute organization programs sufficiently | Good relationship with government office Networking opportunities with local CSO networks and other organizations |
| Weaknesses | Challenges |
| High donor dependency Staff lack skills on resource mobilization techniques | Unanticipated donor policy changes Government policies and laws |

| 2.5 KOCD Resource Mobilization Strategy Framework |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Strategic Objective | Strategic Action |  | Key Performance Measures (KPI) | Budget (TZS) | Responsible | 2019 |
| Key Focus Areas |  |  |  |  |  |  |  |
|  |  |  | Activities |  |  |  |  |
|  |  |  | Update organization website to include information about fundraising events | Website updated | 500,000 |  | 100M |
|  |  | Hold fundraising events to raise TZS 100 million | Invite volunteers to fundraising events/cloud funding | 100 volunteers invited/donors | 2,500,000 | Resource Mobilization officer ,Financial Officer and Program Officer |  |
|  | SO2. Accumulated TZS 200 million from volunteers by Dec,2019 |  | Collect contributions from volunteers/cloud funding | TZS 100 million collected from volunteers/cloud funding | - |  |  |
| Quality Service |  |  | Identify suitable volunteers | 100 volunteers identified | 750,000 |  | 100M |
|  |  | Incorporate volunteers in KOCD activities to raise TZS 100 million | Incorporate volunteers in KOCD activities | 50 volunteers allocated and incorporated in activities | 1,000,000 | Resource Mobilisation Officer,ProgramOfficer,Financial officer |  |
|  |  |  | Save money | TZS 100 million saved | - |  |  |
|  |  |  | Identify potential donors | 20 donors identified | 1,250,000 |  |  |
|  |  | Raise TZS 300 million from existing donors | Write proposals to donors | 20 proposals written | 2,000,000 | Resource Mobilisation office & secretariet | 300 M |
|  |  |  |  |  | 500,000 |  |  |
|  |  |  | Implement and monitor programs | 20 programs established and monitored |  |  |  |
| Increase Income | SO3. Increased income to TZS 550 Million from existing sources by 2021 |  |  |  |  |  |  |
|  |  | Collect TZS 250 million from membership fees | Review current membership fee rate | New membership fee established | 50,000 |  |  |
|  |  |  | Increase number of members | 150 new members joined | 50,000 | Organization Chair, executive Director, Financial Officer | 250 M |
|  |  |  | Collect membership fees | TZS 250 million collected | 50,000 |  |  |
|  |  | Improve current vocational training and raise TZS 20 million from it | Review current vocational training programs | 2 programs reviewed | 1,000,000 |  |  |
|  |  |  | Implement the improved vocational program | 2 courses implemented | 5,000,000 | Program Manager,Secretariet | 20M |
|  |  |  |  | 20 million collected from new trainees |  |  |  |
|  |  |  | Admit new trainees |  |  |  |  |
|  | SO4. 45 Million revenue collected from new sources by 2019 |  | Setupa beekeeping farm | 1 bee keeping farms setup | 2,000,000 |  |  |
|  |  | Engage in beekeeping to raise TZS 5 million | Monitor, harvest and package honey | 720 liters of honey produced annually | 1,000,000 | Program Manager, Procurement Officer ,financial manager | 5 M |
|  |  |  | Sell honey products to customers | TZS 5 million collected from selling honey products | 500,000 |  |  |
|  |  |  | Setup a shop | 1 shop setup | 2,000,000 | Program manager |  |
|  |  | Engage in shop business to raise TZS 5.845 million | Monitoring and establishment of Business shop | TZS 5 million collected from selling products | 1,200,000 | Procurement Officer, financial officer | 5.845 M |
|  |  |  | Identify customers | 14,000 customers identified | 1,000,000 | Program manager Procurement Officer, financial officer |  |
|  |  | Sell packaging materials to raise TZS 15million |  |  |  |  | 15 M |
|  |  |  | Order packaging materials from manufacturers | 70,000 packets ordered | 200,000 |  |  |
|  |  |  | Sell packaging materials to customers | TZS 15 million collected from packaging material | 300,000 |  |  |
| Budget Total TZS 22,850,000/= |
| Revenue Generated Total TZS 795,845,801 |

Table 9: KOCD’s Resource Mobilization Strategy Framework

## 2.6    Income Generating Activities Evaluation

We assessed10 potential Gas to ensure that they lead to financial sustainability, and narrowed this down to 4 (as highlighted in the table below). The level of risk presented by each IGA has also been highlighted to provide focus on which IGAs will be our most viable projects to implement in order to obtain new resources. The higher the final score an IGA has compared to another, the more favorable and profitable the project is expected to be. The full IGA assessment is outlined in the tables below:

| IGA | Final Score | Link to mission | Size of the value | Required Capital | Required Capability | Complexity | Risk |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Low 1, med 2, high 3 | Low 1, Med 2 High 3 | Low 3, Med 2, High 1 | Low 3, Med 2, High 1 | Low 3, Med 2, High 1 | Low 3, Med 2, High 1 |
| Bee Keeping | 17 | 3 | 3 | 3 | 2 | 3 | 3 |
| Fish Pond | 12 | 3 | 3 | 2 | 2 | 1 | 1 |
| Brick Making | 12 | 2 | 3 | 2 | 3 | 1 | 1 |
| Catering Services | 12 | 1 | 2 | 2 | 2 | 2 | 3 |
| Vocational Training majoring in Tailoring | 16 | 3 | 3 | 2 | 2 | 3 | 3 |
| Day Care | 12 | 3 | 3 | 1 | 1 | 2 | 2 |
| Sun Flower Growing | 13 | 2 | 2 | 3 | 2 | 2 | 2 |
| Poultry & Rabbit farming | 13 | 3 | 3 | 2 | 2 | 2 | 1 |
| Selling Products from business | 16 | 3 | 3 | 2 | 2 | 3 | 3 |
| Packaging Materials | 16 | 3 | 2 | 2 | 3 | 3 | 3 |

| Strategy | Person Responsible | Expected Revenue (TZS) | Complexity (Challenges) | Required capability |
| --- | --- | --- | --- | --- |
| Bee Keeping | Fundraising Officer | 5 Million | Pests and diseases Thieves Quality Control | Land Bee hives Skilled Laborers |
| Key activities | Required capital (TZS) | RISK: |
| Land survey for beekeeping Procurement of land Purchase of Bee Hives- | 3,500,000 | MEDIUM |
|  | Risk Management |
|  | Ensure production of quality products Construction of good beehives with locks Frequent surveillance |

| Strategy | Person Responsible | Expected return (TZS) | Complexity (Challenges) | Required capability |
| --- | --- | --- | --- | --- |
| Selling packaging materials | Fundraising Officer | 15 Million | Business Competitors Order delays | Storage space |
| Key activities | Required capital (TZS) | RISK: |
| Identify manufacturers Order packaging materials from selected manufactures Store packaging materials Sell packaging materials | 1,500,000 | LOW |
|  | Risk Management |
|  | Offer competitive prices Keep a track record of packaging materials, so that orders can be placed to manufacturers before inventory is finished |

| Strategy | Person Responsible | Expected return (TZS) | Complexity (Challenges) | Required capability |
| --- | --- | --- | --- | --- |
| Selling of products from KOCD shop | Fundraising Officer | 5 Million | Price fluctuation Faithfulness shop attendant | Laborers |
| Key activities | Required capital (TZS) | RISK: |
| Obtain room Equiping the shop with products Selling of products | 3,200,000, | LOW |
|  | Risk Management |
|  | Will look for cheaper suppliers We will hire a faithful shop attendant |

| Strategy | Person Responsible | Expected return (TZS) | Complexity (Challenges) | Required capability |
| --- | --- | --- | --- | --- |
| Vocational training | Fundraising Officer | 20,000,000 | Competition from other CSOs and NGOs | Skilled training staff Adequate equipment |
| Key activities | Required capital (TZS) | RISK: |
|  | 6,000,000 | LOW |
|  | Risk Management |
|  | Offer competitive training fee prices |

## 2.7    Risks and Mitigation Plan

We identified potential risks and the level of impact that they could have on our strategy (high, medium or low). We also developed mitigating measures for each identified risk, and appointed an appropriate member of staff in regards to accountability. It should be noted that we developed a comprehensive risk and mitigation plan, combining both the strategic plan and resource mobilization strategy.

| RISK MITIGATION PLAN |
| --- |
|  | Level of Impact(High ,Medium ,Low) | Probability of Occurrence(High,Medium,Low) | Mitigating Measure | Action Owner |
| Risk Description |  |  |  |  |
| Political Interference | Medium | Low | Remain unpolitical | Board members, Secretariat |
|  |  |  | Coordinate the project with government stakeholders |  |
| Competition from other CSOs/NGOs | Medium | High | Offer competitive prices | Coordinator, Fundraising Officer |
|  |  |  | Create unique programs |  |
| Donors withdrawal | High | Medium | Exit Strategy Plan | Board Member, Secretariat, Financing Officer |
|  |  |  | Implement Resource Mobilization Plan |  |
|  |  |  | Compliance with funding regulations |  |
| Donor policy change | Medium | Low | Organization Flexibility | Board members, Secretariat |

# Text boxes

Future/External

Current/Internal

Table 1: KOCD SWOC Analysis

Table 2: SWOC Analysis Actions

Table 8: KOCD’s RM SWOC Analysis

Table 10: IGA Assessment

Table 11: IGA Evaluation Construction of an Information Resource Centre

Table 12: IGA Evaluation

Table 13: IGA Evaluation

Table 11: Risks and Mitigation Plan