**Report from April 2022 to July 2022**

**Therapeutics and Educational Intervention Programme for the Children with Disabilities and community mobilization through CBR Project .**

The 2nd Year for Support from ReJenga started from 1st April 2022 to 31st March 2023. Previous year we faced lots of Challenges to run the project as per plan activities due to COVID pandemic and Lockdown. This year we began with new hope of normal life and we also took COVID precaution. All the staff Members of the Centre is fully Vaccinated with 3rd Precaution dose of Vaccine and all the parents is vaccinated with double dose. Still we follow the COVID protocols such as use mask in movement and washing hand properly. The Community Rehabilitation Centre is functioning normally and the children visit with their mothers regularly. During this period we provide rehabilitation services to 45 Children. They received 394Therapeutic sessions and 172 Special Educational Session.

We organized two parents training programme and observe the Bengali New Year’s and World Autism Day. One training programme for the ICDS workers of Panskura Block was also organized on 19th May where 65 ICDS workers participated. The programme was organized to promote Identification of Disables children in early stages through the ICDS workers and refer them as per their needs. We organized one parents training programme on various Law on Disability and Child Rights on 28th June. We received support from two Law students to conduct the programme for the parents of our Panskura Community Rehabilitation Center. 28 parents were participated in that programme and understand the Laws about their children benefits in present and future.

With the Support of Asha Bhavan Centre Orthopedic Workshop Department we organize a camp where 15 children received 24 no of aids and appliances which include Knee Gaiters, Special Chair, Crutch and also take the measurement and casting of 18 children who will receive the require assistive devices such as AFO, Splint, Special Chair, Gaiter etc.

In this Quarter (from April 2022 to July2022) we achieved the bellow mention activities.-

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Male** | **Female** | **Total** |
| No of Children enrolled | 33 | 12 | **45** |
| **Age Wise Break Up** | | |  |
| 0 - 3 years | 04 | 02 | **06** |
| 3 – 8 Years | 18 | 08 | **26** |
| 8 12 Years | 08 | 02 | **10** |
| 12 years above | 03 | 00 | **03** |

|  |  |  |  |
| --- | --- | --- | --- |
| **No of Therapeutic session conducted** | **No of Special education session Conducted** | **No of ADL Training session Conducted** | **No of Speech Therapy Session Conducted** |
| **263** | **172** | **46** | **85** |

|  |  |  |  |
| --- | --- | --- | --- |
| **Statement of expenditure for Therapeutics and Educational Intervention programme for the Children with Disabilities and community mobilization through CBR for the period of 01.04.2022 to 31.07.2022.** | | | |
| RUN BY: **Asha Bhavan Centre** | | | |
| IN COLLABORATION WITH **ReJenga, USA** | | | |
| Area: Asha Bhavan Centre, Balidangri, Panskura, PurbaMidnapore, West Bengal, India. | | | |
| **Sl No.** | **Financial details** | **Details** | **Amount (INR)** |
|  | **Honorarium to Rehabilitation Therapist** | 9500 X 4 months | **38000.00** |
|  | **Honorarium to Special Educator** | 8000 X 4 months | **32000.00** |
|  | **Honorarium to Field programme officer** | 6500 X 4 months | **26000.00** |
|  | **Honorarium to Project manager** | 4000 X 4 months | **16000.00** |
|  | **Travelling for Project staff** | - | **-** |
|  | **Rehabilitation and Teaching Learning materials** | - | **-** |
|  | **Cleaning and hygiene of the centre** | - | **320.00** |
|  | **Cost of Electricity** | - | **620.00** |
|  | **Telephone and communication expenses** | - | **459.00** |
|  | **Contingency (distribution of sweet on on Bengoli New year and celebration of Autism day )** | - | **10500.00** |
|  | **Administrative expenses** | - | **501.00** |
| **TOTAL** | |  | **124400.00** |

**A Glimpse of Activities**













