Project Title: Improving quality production of Shea Butter to increase income of women shea butter producers.

Duration:  2009-2011

## LOGICAL FRAMEWORK

| Summary description | Measurable Indicator | Source | Challenges |
| --- | --- | --- | --- |
| Objectives : Improvement of the standard of living for women shea butter producers | - At least 50% of shea butter producers have increased their income by 100% | - Activity reports Site Visits Interviews with women | - Obtaining accurate data |
| Improvement of the techniques of transport and storage of shea butter | - More than 75% of trainees have effective means of transportation | Activity reports Site Visits | - Oversight and use of new techniques |
| Production of high quality shea butter | - More than 75% of trainees are proficient in producing high quality shea butter | Testing samples of shea butter Interviews with women | Accessing a well-equipped lab for testing Ensuring proficiency of women in new production methods |

| Expected results | Measurable Indicator | Source | Challenges |
| --- | --- | --- | --- |
| Improving transportation of shea nuts | - At least 50% of shea producers have increased the amount of shea nuts they collect and transport by 30% | Site Visits | Ensuring that women use to mull drawn carts - |
| Year round shea butter production | - More than 30% of women in the villages of joined the co-op to ensure high output of production | Site Visits | Equipping the co-op with millet grinders and tools to increase production Establishing proper storage of raw shea butter |
| Reducing the use of wood for heating during the production of shea | - At least 50% of trainee women use ameliorated stoves to heat the shea and converse wood | Site Visits | Community reliance on wood and coal for fuel |

| Phase 1 Data Collection/Organizing | Phase 2 Project Implementation |
| --- | --- |
| 1 month | 3 years |

SHEA YEELEN Project  Activity Plan in DIO

Plan is divided in two phases

Phase 1: Data Collection/Organizing

| Stage 1: Meeting with local authorities and women | Activity | Description | Period |
| --- | --- | --- | --- |
|  | Meeting with Local authorities | - Introducing project goals to the local authorities, traditional and religious leaders of Kati and Koulikoro - Meeting with local leaders in Dio. | Completed 2005 |
| Stage 2: Organizing Co-ops | Meeting with women in 7 villages of Dio | Assessing needs Developing a set of techniques for A grade shea butter production in Dio | Completed 2006 |
|  | Getting a Peace Corps Volunteer into Dio | -Submitting request to Peace Corps Mali | Completed 2007 |

Phase 2: Project IMPLEMENTATION:

These three stages will all be part of any of the alternatives available in Phase 1.

| Stage 3: Training | Activity | Description | Period |
| --- | --- | --- | --- |
|  | Co-op management Shea butter production Responsibility: | - Trainings will be provided to establish process and procedures | Training is ongoing but some provided in 2006 |
| Stage 4: Production | Production Responsibility: | - Establishing Central Location for women to produce shea butter. - Building of production facility | 2010 |
| Stage 5: Follow-up & Evaluation | Follow-up and quality assurance. Responsibility: | - Technical inspection (follow–up) to ensure that techniques learned are applied | 2011 |

TRAINING FOR SHEA BUTTER PRODUCTION IN MALI

SCHEDULE OF SESSIONS

| DAILY PROGRAMS | MORNING | AFTERNOON | PROJECTED RESULTS |
| --- | --- | --- | --- |
| DAY ONE | INTRODUCTION TO SHEA BUTTER MAKING QUALITY CONTROL ISSUES QUESTIONS AND ANSWERS | PLANNING SELECTION OF RAW MATERIALS EXPLANATION OF MATERIALS TO BE USED, EQUIPMENT ETC | AT END OF THE TRAINING THE WOMEN SHOULD BE ABLE TO: PRODUCE GOOD QUALITY SHEA BUTTER FOR INTERNATIONAL AND LOCAL MARKETS. PACKAGE THEIR SHEA BUTTER FOR SPECIFIC MARKETS. CREATE THEIR OWN MARKETING PLANS |
| DAY TWO | SORTING NUTS |  |
| DAY THREE | CRACKING AND ROASTING |  |
| DAY FOUR | GRINDING |  |
| DAY FIVE | KNEADING AND CLARIFICATION |  |
| DAY SIX | FILTERING AND STERRING | QUESTIONS AND ANSWERS |  |
| DAY SEVEN | INTRODUCTION TO MARKETING . MARKETING TECHNIQUES FOR THE INTERNATIONAL MARKET. | QUESTIONS AND ANSWERS |  |
| DAY EIGHT | PACKAGING AND LABELLING |  |
| Trainer: Eugenia Akuete |  |

TRAINING BUDGET

| Designation | Quantity | Unit Price (FCFA) | Total Cost. (FCFA) | Total cost (US$) |
| --- | --- | --- | --- | --- |
| Travel for Eugenia and her assistant | 1 | 305,160 | 610,320 | $1,200 |
| Kneading machine | 1 | 508,600 | 508,600 | $1,017 |
| Nut Cracker | 1 | 152,580 | 152,580 | 306 |
| Nut Grinder | 1 | 152,580 | 152,580 | 306 |
| Transport for Women | 20 | 1,000 | 20,000 | $40 |
| Pier Diem | 20 | 7,000 | $140,000 | $280 |
| Food | 25 | 2,000 | 50,000 | 100 |
| GENERAL TOTAL | 1,634,080 | $3,249 |

# Text boxes

Stage 1:

###### Meeting with local authorities & women

# Stage 3:

Training

Stage 2:

Organizing

Stage 4:

Production

Stage 5:

## Evaluation/Follow-up