# St. Leonard Health & Research Foundation

# NEYANG HEALTH ACADEMY

iNTRODUCTION AND oVERVIEW:

Neyang Health Academy Distance Learning

Table of Contents

Executive Summary	5

Overview of St. Leonard Health & Research Foundation:	6

Background	8

The Problem	8

Cameroon	9

Neyang Health Academy Distance Learning	11

Purpose	11

Embedding New Nurses in the Communities They Serve	12

Education	12

Distance Education:  Leveraging e-Learning	12

Student-Centered Blended Learning Platforms	13

Partnerships & Collaboration	13

Network of Community Health Professionals	13

Paid, Professional Nursing Educators	14

Governments and Ministries of Health	14

National and Global Partnerships	14

Who We Are and How We Started	15

Humanitarians Without Borders	17

THE NEXT STEP:  Neyang Health Academy Distance Learning	18

The Plan:   Implementation Phases of Growth	19

Organization	22

Acknowledgements	22

References	23

Appendix	25

Appendix - Hope for the Most Remote	26

Appendix - Presentation of the NGO	29

Appendix - Community Brochure (Historic)	31

Appendix - Images	33

# Executive Summary

Delivery of primary healthcare to rural, developing communities is unsustainable due to lack of infrastructure, especially transportation.  St. Leonard Health & Research Foundation has developed medical education, delivery, and research programs centralized in Limbe, Cameroon to address coverage gaps.  Recognizing that the decentralized delivery of medical education and resources are the only way to bring about sustainable healthcare in remote communities, St. Leonard is on the brink of establishing an online professional nursing education delivery platform.  This is the planned Neyang Health Academy Distance Learning that will take advantage of our ongoing experience Neyang Health Academy in Limbe, Cameroon, while broadening it to suit a distributed audience.  Neyang Health Academy and Neyang Health Academy Distance Learning train healthcare professionals who, after completing their education, provide services to their local communities.  The impact of this initiative will make lasting change and save lives.

# Overview of St. Leonard Health & Research Foundation:

Centralized Services

- Provided in facilities in Limbe, Cameroon.

  - Medical Education

    - Neyang Health Academy

      - Urban nursing school in Limbe, Cameroon.

  - Medical Delivery

    - Outpatient Health Clinic

      - Urban provider of primary healthcare.

  - Medical Research

    - Center for Biomedical Research:

      - Researching ways to combat current, emerging and re-emerging infections, especially MRSA/HIV/AIDS/Co-infections and Malaria.

Decentralized Services:  Humanitarians Without Borders

- Sustainably empowering rural individuals and communities through education, healthcare, and development.

  - Medical Education

    - DEVELOPING:  Neyang Health Academy Distance Learning

      - Educating the next generation of healthcare professionals living in remote communities.

  - Medical Delivery

    - FORMERLY:  Mobile Health Partners

      - Project-based medical care to rural communities during outreach events.

    - DEVELOPING:  Rural Primary Health Partners

      - Embeds healthcare professionals within the communities they serve.

  - Other Resources

    - Remote Community Development & Social Outreach

      - Birth Certificate Rural Access

        - Without a Birth Certificate, a child cannot graduate primary school, which contributes to maleducation and continues the cycle of poverty.

      - Female & Junior Youth Empowerment Programs

        - Fostering the skills, attitudes, and qualities of character necessary for lives dedicated to building a peaceful, just, and inclusive society.

      - Gender Equality Education

        - Harmful attitudes towards women impede peace by perpetuating injustice against half the population, and creating a climate for gender violence.

Illness is universal but access to healthcare is not (Panjabi, 2017).

# Background

More than half of the world’s population cannot obtain essential health services (WHO, 2017).  Primary healthcare is notoriously hard to obtain in developing nations and it is even more difficult for those living in rural areas.  For decades there have been multiple attempts to solve this problem.  Traditional international healthcare aid models have proven to be less effective than once predicted: often temporary, inefficient, and disempowering to the very people they were intended to assist.  This model fails because it treats the symptoms of this health crises, not its cause:  a lack of healthcare infrastructure.  The two main areas in need of improvement are education and transportation. When nurses are educated where they live and reside in the communities they service, the logistical and financial challenges of housing and transportation are circumvented.

It is necessary to create a sustainable primary healthcare delivery system in which trained healthcare providers are embedded within remote communities where the need is greatest.  In order to improve healthcare access and move away from the temporary, one-off interventions and project-based approaches of the past, Neyang Health Academy Distance Learning seeks to provide permanent improvement to healthcare infrastructure.

# The Problem

Worldwide, over a billion people will never see a health worker during their lifetime (WHO, 2017).  Today, more than 60% of the African population live in rural areas far removed from healthcare providers (Amzat & Razum, 2018).  People living in remote places in Africa face considerable challenges receiving even basic health care. Obstacles confronting those living in remote areas include:

- Difficulties traveling to the nearest health facility

- Lack of trained healthcare professionals

- High cost of treatment and transportation

- Stigma associated with disease itself

All these issues make it difficult, if not impossible, for people in rural communities to access lifesaving services.

The combined effects of distance and poverty means that many die needlessly from preventable or treatable diseases.  Infectious diseases, such as tuberculosis, HIV/AIDS, hepatitis B and C, pneumonia, diarrhea, and malaria spread unchecked.  Chronic diseases, such as hypertension, diabetes, malnutrition, and cancer remain untreated with devastating consequences.  Complications during childbirth destroy lives, families, and communities.

# Cameroon

Cameroon is located in Sub-Saharan Africa, a region that carries about one third of the world’s disease burden (Njinji, 2012). More than 25 million people live in Cameroon and, although it is the 24th largest country by land mass, it is one of the least densely populated countries in the world (World Population Review, 2019).  “Out of the entire population, 24% live in poverty, and 55% of those in poverty live in rural communities. [There] are two causes of poverty in Cameroon and reasons for the gap between rural and urban poverty are a lack of infrastructure and an education system that fails to develop alongside shifting labor needs” (Borgen, 2018).

About 7.2 million Cameroonians live more than an hour’s walk from the nearest health facility, and many live greater than 21 kilometers (13 miles) from one.  Impediments to healthcare access are further exacerbated when coupled with those internally displaced during periods of civil unrest, and the influx of refugees from neighboring countries due to armed conflict.

In recent years, information communications technology (ICT) in Cameroon has made greater achievements than in other countries in Central and West Africa (Achidi, 2019).  It is expected that during 2020, the entire country will have enhanced Wi-Fi, reliability, speed, and network coverage to support increasing demand (Achidi, 2019).  As the national ICT capacities grow, even remote villages will be Wi-Fi connected.

# Neyang Health Academy Distance Learning

Empowering the Next Generation of Healthcare Professionals

Living in Remote Communities

## Purpose

Everyone Should be Able to Access a Nursing Education, No Matter How Far Away They Live

The purpose of the academy is to deliver comprehensive, high quality nursing education that is accessible to students where they live:  in remote communities.  There is a desire for more accessible nursing education in Cameroon (Maboh, 2016).  Without an organization such as Neyang Health Academy Distance Learning, the only choice available to rural nursing students is to move into the city in order to attend school.  Citing the financial hardship of living in the city, many promising students in Neyang Health Academy are forced to drop out before graduation.  We believe that ensuring the affordability of a nursing education for rural students is the first step towards closing the healthcare gap in Cameroon for good.

## Embedding New Nurses in the Communities They Serve

After graduation from Neyang Health Academy Distance Learning, these new nurses will provide primary healthcare to serve people, hospitals, and their neighbor in rural communities.  These nurses will understand their communities better and be better equipped than those from outside the area who come in sporadically during outreach initiatives.  Mobile Health Partners, the medical outreach branch of Humanitarians Without Borders, has been providing intermittent care for many years, but cannot realistically grow to address the needs of remote communities.

By linking new rural nurses with the improved version of Mobile Health Partners, now known as Rural Primary Health Partners, there are no longer any geographic limits to the expansion of healthcare. Rural Primary Health Partners embeds healthcare professionals within the communities they serve.  This infrastructure strategically places healthcare providers at the right time and place to address a multiplicity of health issues, including current, emerging and re-emerging infections.

## Education

### Distance Education:  Leveraging e-Learning

21st century education calls for new ways of developing the knowledge and skills necessary for students to become successful healthcare professionals.  Our approach blends traditional and web-based environments.  Faculty are skilled educators and nursing professionals who develop and deliver the unique curriculum, courses, and lessons necessary to train competent rural community health nurses in a learner-centered context.

Technology and internet connectivity allow us to deliver educational content and engage students no matter where they live, so long as there is accessible Wi-Fi or a network with reliable speed and coverage.  Students are provided with laptops and cell phones - the new tools for connecting students and faculty with course materials and providing opportunities for meaningful interaction.  Utilizing the wealth of resources available through the web, faculty engage students beyond the limitations of traditional lecture-style formats.  As information communication technology (ICT) expands, the locations where students can connect will increase to encompass even more remote areas.

### Student-Centered Blended Learning Platforms

Blended learning takes the best of traditional nursing education and expands the possible ways educators connect students with new knowledge by combining online educational content and interaction with face-to-face place-based classroom methods.  Creating opportunities for students, faculty, mentors, and preceptors to connect in person will be necessary at a variety of locations including, but not limited to, clinics and hospitals, at the local and regional level.

The development of clinical skills is essential to any nursing education program.   Simulation opportunities provide a safe learning environment. Clinical competency, interpersonal skills, and interprofessional collaboration are essential components of nursing education.  Students will be partnered with local and regional clinics, as well Neyang Health Academy in Limbe, to develop important clinical competencies and skills, as well professional mentoring relationships.

## Partnerships & Collaboration

### Network of Community Health Professionals

Drawing on international best practices and the lessons learned with Humanitarians Without Borders’ remote community outreach in Cameroon, the Neyang Health Academy Distance Learning will educate a network of community health professionals.  These new professionals can then be deployed through Rural Primary Health Partners as paid healthcare providers to remote communities in Cameroon, and eventually scaling throughout Africa.

### Paid, Professional Nursing Educators

In order for Neyang Health Academy Distance Learning to be sustainable and deliver high quality nursing education, the faculty of nurse educators, including clinical nurse educators, must be paid professionals (Aeta, et al., 2011).

### Governments and Ministries of Health

Partnerships with governments and Ministries of Health offer the ability to integrate the public sector health infrastructure to support sustainable continuation and expansion of Neyang Health Academy Distance Learning and Rural Primary Health Partners.  We will provide assistance based on lessons learned to governments, beginning in Cameroon and expanding into Central and Western Africa, where education programs will be implemented to bring Neyang Health Academy Distance Learning and Rural Primary Health Partners to nationwide and regional scales.

### National and Global Partnerships

Recognizing the importance of partnerships, collaboration, and collective impact to bring about transformative change, we will advocate on both the national and global stage for investment in solutions to the broader health and development needs of underserved, poor, and remote communities in Africa.

# Who We Are and How We Started

Dr. Kouemou Sinda Leontine, founded St. Leonard in 2010 to address the growing concerns for the health and wellbeing of patients she encountered as a new healthcare provider in Limbe, Cameroon.  The health needs in Cameroon were so great and the situation seemed to be worsening rather than improving.  For example, between 1980 and 2012, the maternal mortality rate almost doubled from 500 to 900 deaths per 100,000 (Njinji, 2012).  Dr. Sinda noticed a corresponding increase in the poverty resulting in declining health.  As Njinji points out, “a healthy population is obviously more productive and vice versa” (2012).  With as few as one doctor to 30,000 inhabitants in norther Cameroon, those living in the most remote areas were experiencing the greatest health and poverty challenges (Njinji, 2012).

Based on the premise that healthcare is a human right, St. Leonard began the Outpatient Medical Clinic to provide primary healthcare locally, in Limbe, Cameroon. Next, the Neyang Health Academy was created to provide a stream of trained human resources by educating the next generation of healthcare professional in Limbe.  All the while, Dr. Sinda continued to focus on the future to generate new knowledge through research to combat current, emerging and re-emerging infections, especially focused on MRSA/HIV/AIDS/Co-infections and Malaria while working towards a second PhD in Microbiology. In December 2019, the Center for Biomedical Research is scheduled to open a renovated research branch of St. Leonard.

Figure: Centralized structure of St. Leonard Health & Research in Limbe, Cameroon

As the number of outreach activities to remote communities became more frequent and the scope of the need became more apparent, Humanitarians Without Borders was created to be the remote community outreach branch of St. Leonard.  Humanitarians Without Borders has been a beacon of solace and hope for many rural communities and those displaced during civil conflict, and isolated refugees from neighboring countries by providing medical care and community development initiatives targeting education access, building youth capacity, and promoting gender equality.

# Humanitarians Without Borders

Humanitarians Without Borders continues to evolve and expand to address the multifaceted issues confronting people living in remote communities.  Our mission is to serve as a catalyst for a peaceful, just, and inclusive society which respects the dignity of all people.  Our focus is on sustainably empowering rural individuals and communities through education, healthcare, and development.

Figure: Transition from Centralized structure to a Decentralized & Sustainable structure

In order to address the urgent need in rural communities in Africa, Humanitarians Without Borders is dedicated to creating sustainable solutions to address the urgent need of bringing healthcare to everyone, everywhere. Because we believe that “no one should die because they live too far from a doctor, not in the 21st century” (Panjabi, 2017).

Humanitarians Without Borders is pleased to introduce our newest initiative empowering the next generation of healthcare professionals living in remote communities:

# THE NEXT STEP:  Neyang Health Academy Distance Learning

Neyang Health Academy Distance Learning is uniquely positioned in Cameroon to combine its expertise in nursing education with robust and expanding access to information technology and communication networks. This union transforms both professional training and healthcare delivery for the nation’s rural population, as it is not limited by infrastructure and physical accessibility.

St. Leonard is a transparent organization dedicated to continuously learning; drawing on experience, evidence, and best practices; constantly assessing, re-evaluating, and strategically improving processes and approaches to most effectively serve vulnerable populations; implementing the most efficacious initiatives promoting well-being and autonomy; and honoring human dignity and worth within their cultural context.

## The Plan:   Implementation Phases of Growth

St. Leonard Health & Research Foundation, Inc. is an apolitical, non-governmental organization headquartered in Cameroon’s Bobende, Limbe II Subdivision, Fako Division, South West Region.  Due to a generous donation of the current building and property, St. Leonard has been providing a multiplicity of services, including a;

- Primary medical clinic,

- Biomedical research laboratory, and a

- Center of education/training for:

  - Research specialists and assistants,

  - Medical assistants,

  - Phlebotomists,

  - Nurses, certified nursing aids and nursing aids.

New Model, New Needs:

As St. Leonard moves from an entirely centralized model to encompass a new decentralized model, new issues emerge along with new needs.  Its initial phase is perhaps the most critical; without meeting these needs, Neyang Health Academy Distance Learning may not be able to become reality.

Phase I:  Developing the course and obtaining the necessary technology and supports.

- Administrative Supports

  - CEO

  - Faculty/staff for school

  - Administration/Accounting/Finance

  - Information Communication Technology Support person (or agency)

- Paid Faculty /  Nursing Educators

  - Curriculum and Program Design

  - Course Development with Lesson Plans for the entire program

- Web-based educational platform

  - Identify and obtain an adequate remote e-learning platform

  - Input all curricular/program elements, courses and lesson plans into the educational platform

- Technology

  - Internet Network /access fees

  - Web-based educational platform

  - Need based on estimated class size per cohort

    - (50 students per class + ~10 faculty and administrators = 60)

    - Hardware

      - Cell phones

      - Computers (laptop or tablet)

      - Solar chargers

      - Power bank compatible with aforementioned electronics

      - Charger cables

    - Cloud storage and remote back up

    - Software to support learning/teaching/communications

Phase II:  Enhancing health and safety at headquarters.

- Facility improvement

  - As Neyang Health Academy at St. Leonard’s is the epicenter for all organizational undertakings, including onboarding new students and clinical competency evaluations, ensuring the campus’ facilities are adequate to support current and future expansion is critical

    - Water

      - Bore-hole/well to supply enough clean water for patients, faculty/administrators and students

        - NOTE:  St. Leonard is committed to donating part of the property for community access to water from a well/pump

    - Sanitation

      - Expanding toilet/shower facilities for increased facility usage

    - Temporary Dormitory

      - Tents within a compound (below) will serve as a temporary dormitory accommodations for students while they are attending training or events at the headquarters facility.

      - An exterior, walled compound to surround the tents in order for remote students to remain safe

Phase III:   Beginning first nursing class and working to improving facility physical

infrastructure to accommodate the next class of students.

- First class of nursing students begins

- Paid nursing faculty

  - Nursing educators

  - Nursing clinical educators

- Continued Facility Improvement

  - Building permanent dormitory spaces for students

Phase IV: Enhancing research capacities for infectious diseases and increasing global

partnerships and capacity.

- Creating a biomedical laboratory in Yaounde (the national capital)

  - Drawing on academic resources

- Increased International collaboration, partnerships and collective impact

# Organization

Founder/CEO:

Kouemou Sinda Leontine, PA, MS, PhD, Limbe, Cameroon.

Dr. Sinda is on the faculty of Bengono Toure University, holds a PhD. in Infectious Diseases from the Faculty of Medicine and Biomedical Sciences, is a licensed Physician Assistant, has a Masters in International Cooperation and Humanitarian Action, and has recently completed work towards another PhD in Microbiology.

Partners:

The Baare Tchamba Foundation, Cameroon.

The American University of St. Vincent School of Medicine

Volunteer 4 Africa

Elected board members on the 19th Mars 2019

| No | NAME | FUNCTION | PROFESSION | CONTACT |
| --- | --- | --- | --- | --- |
| 01 | Sokem Ngale Mborh | Director | Magistrate | 677690665 |
| 02 | Kouemou Sinda Leontine | Member | Infectious diseases specialist/humanitarian | 677442654 |
| 03 | Medong Adele Noel | Member | Economist | 00447438353877 |
| 04 | Mbimenyuy Bomki Cynthia | Member | Clinical researcher | 690691523 |
| 05 | Sara-Ana Rodriguez | Member | Lecturer/humanitarian | + 34600721557 |
| 06 | Fokoue Fabrice | Member | Medical doctor | 697669170 |
| 07 | Kathleen Russell | Member | Senior nurse | + 011 4404340142 |

International Collaborators:

Sara A. Dominguez Rodríguez, BA, Honors Humanities, Barcelona, Spain.

Ms. Dominguez Rodriguez holds a Diploma in European Studies, Advanced Certificate in TEFL, and Curs de Qualifcació Pedagògica Anglès.

Makebabcn2018@gmail.com

Kathleen Russell, BS, RN, Cleveland, Ohio, USA.

Ms. Russell anticipated Masters of Science in Nursing Education (MSN Ed) December 2019. Kathleen.Russell99@gmail.com

# Acknowledgements

Thanks to all who assisted in bringing Neyang Health Academy Distance Learning from vision closer to reality:

Pr. Koulla Shiro Sinata, Twamba Charles, Dr. Sinda Freud Taylor, the entire St. Leonard Team, Ariel Russell, Michael Russell, Morgan Russell

Special thanks to the Community Health Academy for the opportunity to participate in the first Leadership Training for Strengthening Community Worker Programs (Last Mile Health, 2019).

# References

Achidi, J. (2019).  Cameroon: "Through Cooperation with Huawei We're Sure to Break the Digital Divide".  Cameroon Tribune (Yaoundé), 7 March, 2019.  Retrieved from https://allafrica.com/stories/201903080423.html

Aeta, V., Atanga, M., Atashili, J., & Cruz, G. (2011).  Nurses and Challenges Faced as Clinical Educators: A Survey of a Group of Nurses in Cameroon.  Pan African Medical Journal: African Field Epidemiology Network; 8: 28.  Retrieve from https://www.ncbi.nlm.nih.gov/pmc/articles/PMC3201592/

Amzat, J. & Razum, O. (2018). Towards a Sociology of Health Discourse in Africa, Rural Health in Africa, pp 109-124.  Retrieved from  https://link.springer.com/chapter/10.1007/978-3-319-61672-8_8   and available on google books: https://scholar.google.com/scholar?q=towards+a+sociology+of+health+discourse+in+africa&hl=en&as_sdt=0&as_vis=1&oi=scholart

Borgen Project. (2018).  Understanding the Causes of Poverty in Cameroon.  Retrieved from https://borgenproject.org/causes-of-poverty-in-cameroon/

Cameroon (2019).  Retrieved from https://en.wikipedia.org/wiki/File:Cameroon_-_Location_Map_(2013)_-_CMR_-_UNOCHA.svg

Delves-Yates, C. (2014). A Matter of Curses:  Nursing in Cameroon.  Retrieved from https://www.nursingtimes.net/opinion/a-matter-of-curses-nursing-in-cameroon/5077811.article

Eduardo, A. (2019). Hope for the Most Remote:  Providing Rural Community Aid in Cameroon.  Retrieved June 6, 2019 from https://www.idealist.org/en/days/providing-rural-community-aid-in-cameroon

Last Mile Health (2019).  Community Health Academy Leadership Development:  Strengthening Community Health Worker Programs.  Retrieved from:  https://www.edx.org/course/strengthening-community-health-worker-programs-to-deliver-primary-health-care

Maboh, M. N. (2016). Nurse Education in Cameroon - A Grounded Analysis on Seizing the Opportunity of the Moment. PhD thesis, University of Essex.  Retrieved from http://repository.essex.ac.uk/19970/

Map of Cameroon (2019).  Retrieved from https://www.ezilon.com/maps/africa/cameroon-physical-maps.html

Njinji, R. (2012). The Need is so Great. D+C E+Z.  Retrieved from https://www.dandc.eu/en/article/cameroon-too-many-nurses-and-doctors-lack-perspective

Panjabi, R. (2018). How Community Health Workers Could Save 30 Million Lives By 2030. Time Magazine.  Retrieved from http://time.com/5305122/how-community-health-workers-could-save-30-million-lives-by-2030/

Tanywema, A. (2014).  The realities of evidence-based nursing in Cameroon. International Journal of Evidence Based Healthcare.  Retrieved from  https://journals.lww.com/ijebh/Abstract/2014/09000/The_realities_of_evidence_based_nursing_in.74.aspx

World Health Organization. (2017).  World Bank and WHO: Half the world lacks access to essential health services, 100 million still pushed into extreme poverty because of health expenses.  Retrieved from https://www.who.int/news-room/detail/13-12-2017-world-bank-and-who-half-the-world-lacks-access-to-essential-health-services-100-million-still-pushed-into-extreme-poverty-because-of-health-expenses

World Population Review (2019). Cameroon Population 2019.  Retrieved from http://worldpopulationreview.com/countries/cameroon-population/

# Appendix

- Hope for the Most Remote

- Presentation of the NGO

- Community Brochure (Historic)

- NGO Charter

## Appendix - Hope for the Most Remote

Hope for the Most Remote: Providing Rural Community Aid in Cameroon

https://www.idealist.org/en/days/providing-rural-community-aid-in-cameroon

by Angel Eduardo      June 6, 2019

When she was a young girl, Leontine Sinda suffered a bout with malaria that nearly killed her. She spent her time off from school in Ehuet, a village in the mountains of Cameroon, with her grandmother. Ehuet was incredibly remote; getting fresh water for daily meals meant a trek down the mountain with a pail. If anyone fell ill, the nearest medical facility was 50 kilometers away—a trip that required three hours on foot before reaching a truck to drive the rest of the way. Sinda’s malaria caused her to go into shock and, with the paucity of medical treatment options, she barely survived. It became clear to her then just how lucky she had been to make it through her ordeal, and how few others shared her good fortune. “It was horrible,” Sinda recalls, “and though I was a child, I wondered, Why is it that this community is different? Why is it that they don’t have the facilities that you find in the city?” These questions burned within her and became the spark for her life’s work. “I had the thought, you know, We can do something for this community. And that was my main motivation to go and do medicine.”

After losing her grandmother to a mistreated case of pneumococcus, Sinda decided to specialize in the treatment and prevention of infectious diseases. She also started to think about the scope of her humanitarian goals. In 2006 she began the association Peer Educators Actions in Cameroon, traveling to remote villages and instructing young people on the dangers of unsafe sex, and on preventing the spread of diseases such as HIV and AIDS. However, Sinda soon found her position of strictly raising awareness too limiting. “While working with the association,” she said, “I found that there were so many communities having the same problems.” These issues—lack of access to clothing, education, and medical treatment; domestic violence and female oppression; and no knowledge of disease prevention—required something on a larger scale. “For me to solve the problems that I’m seeing,” she said, “I must come up with something bigger.”

“I had the thought, you know, We can do something for this community. And that was my main motivation to go and do medicine.”

In 2010, Sinda founded the St. Leonard Health and Research Foundation, a non-governmental organization dedicated to promoting and providing education, socio/economic inclusion, primary health care, human rights, and preventive approaches to infectious diseases and cancers, as well as reinforcing capacity building for healthcare workers in rural health centers in Cameroon and Africa. Three of St. Leonard’s branches—an Education branch, where a new generation of healthcare professionals are trained; a Medical Care branch, providing treatment to people from an outpatient medical clinic in Limbe; and a Research branch, which focuses on HIV/AIDS and tuberculosis treatment and prevention, malaria vaccines, and the treatment of other infectious diseases—allowed Sinda to fund and propel the Foundation’s fourth branch, the charity organization Humanitarians Without Borders.

Humanitarians Without Borders provides community outreach to remote and underserved populations in Cameroon. Through this organization, Sinda and her colleagues focus on empowering rural students to become healthcare professionals by integrating education, technology, and clinical opportunities. They also instituted a program to register birth certificates to children in rural communities—a requirement for secondary school admission, and a critical step toward breaking the cycle of poverty by eliminating illiteracy. Humanitarians Without Borders also established programs to promote and educate on gender equality, noting that harmful attitudes towards women impede peace by perpetuating injustice against half the population. The Foundation has ambitious goals, but Sinda is not discouraged. “Africa has so many challenges, but I don’t see those challenges as a hindrance to my mission. I see them as opportunities to bring the change that I want to see happen in my community.” Through her work, Sinda is realizing the desire that sparked in her as a little girl, to reach out to her community and make a difference.

“I must do something,” she emphasizes. “You don’t wait for people to come, you start and people can follow if they wish. You don’t force people.” She channels a well-known call to action, “We are the ones we are looking for. We bring the change that we want to see. You don’t wait for people from somewhere else to come and bring this change in your community when you have not done anything.”

“Africa has so many challenges, but I don’t see those challenges as a hindrance to my mission. I see them as opportunities to bring the change that I want to see happen in my community.”

On September 9th, 2017, decades-long tensions between the English- and French-speaking regions of Cameroon erupted into full-on warfare—a conflict called the Anglophone Crisis (also known as the Ambazonia War). The resulting strife threw an already struggling nation into further disarray, and the people most affected were those in remote and rural villages. Many people were internally displaced, and refugees from Central Africa and beyond were also flooding in due to catastrophic issues in their own countries. The crisis also directly hindered Sinda’s mission. Due to safety concerns, St. Leonard’s medical clinic in Limbe, which was initially available to patients 24 hours a day, now had to be closed at 6 PM. The crisis also caused most of Sinda’s medical trainees to flee, severely impacting her ability to do her work with Humanitarians Without Borders.

During a particularly dark moment, in July of 2018, everyone was forced to stay indoors. Locked in and lonely, Sinda was growing depressed. It was then that she happened upon something that would not only lift her spirits but also reignite what had sparked in her when she was just a little girl in Ehuet. “One day I have my tablet and I saw a post that said, Your friend has clicked ‘like’ to this group, the Idealist group. I said, Wow, let me see why this friend of mine has posted in this group.” After registering the St. Leonard Health and Research Foundation to the Idealist network, she came upon the description of Idealist’s mission. “The mission was going along the same lines of what I had in mind,” she remembers. “Doing good. Love. Generosity. Mutual respect. Your mission was in line with what I am doing.”

When Sinda discovered Idealist Days and the worldwide community that joined together to do good in the world, it reminded her why she began her mission all those years ago. “Idealist Day is like a catalyst in me to bring out the best of what I’ve been doing,” she says. “I’m doing it with so much passion, so much excitement. I’m so happy that day because it is a day that is reminding me, This is your mission. So you have to take it over. Continue and continue and continue. I’m happy that I’ve found a family—an Idealist family, which is accompanying me.”

Emboldened by this sense of global community, Sinda began planning her own Idealist Day activities. On 7/7 she organized a seminar called On the Eradication of Neglected Tropical Diseases Through Prevention at St. Leonard’s headquarters in Limbe, instructing children on methods for avoiding dangerous parasites and diseases. On 8/8, Sinda and her colleagues educated women on reproductive health, infectious diseases, and domestic violence at their clinic. They also held free screenings for women to test for diabetes, hypertension, and HIV.

On 9/9, exactly one year after the Anglophone Crisis began, Sinda gathered a group on Wabane Bridge in Southwest Cameroon. The Idealist Call to Action for September was to hold meetups on bridges, and for Sinda this bridge meeting was especially meaningful. Wabane bridge, which Sinda called the Bridge for Peace, symbolized a desire for connection and community between the peoples of Cameroon torn apart by tribal conflict. What’s more, the lush greenery of medicinal plants surrounding the bridge highlighted not only Sinda’s particular mission as a clinician and researcher, but also the ways that medical outreach and the pursuit of peace go hand-in-hand. “The healing nature of these plants is to remind us that we cannot preach peace to people who are sick,” she says. “They need to be healed in their mind, body, and soul.”

Sinda continues her clinical and humanitarian work, planning educational events and medical screenings as well as clothing, medicine, and treatment drives on Idealist Days in even the most remote villages of Cameroon. “When I’m doing my humanitarian action,” she says, “I do it with all my mind, all my soul, I do it with all the passion that I can do it.” And though reaching some of these villages can be treacherous, Sinda remains undeterred. “I am not afraid. If I have to take a bike on a road and fall ten times before arriving, I go. Or if the bike slows me down, I will even go by foot up the mountain to give treatment to people. I don’t care. I go because I know that those people there, they have no hope. They have nothing.”

“But,” she adds, “even if there is one person that I can help, it means that I have found my purpose. I arrive in those communities, and I always tell them, there is hope. There is hope for a better tomorrow.”

## Appendix - Presentation of the NGO

PRESENTATION OF THE NGO

By Dr. Dinga Jerome Nyhalah  (PhD in Bch)

Saint Leonard Health and Research Foundation, Inc. is headquartered at Bobende Limbe II Sub-division, Fako Division, South West Region, Cameroon. Created in 2010, is a non-governmental and apolitical organization composed of professionals from different background and volunteers who work together for social and economic inclusion of young girls and women and to bring education and primary healthcare closer to the underserved populations in rural zones and refugees camps in Cameroon and Africa.

Our VISION:

Our vision is on sustainably empowering rural individuals and communities through education, healthcare, peace and development and on reinforcing capacity building of healthcare workers in rural health centers in Cameroon and Africa.

Our MISSION:

Our mission is to serve as a catalyst for a peaceful, just, and inclusive society which respects the dignity of all people.

GENERAL OBJECTIVE:

Educate and bring primary health care closer to the underserved communities and less privileged especially women and children in non-accessible rural zones in Cameroon, Africa and refugees camps, and fight against socio/economic exclusion and gender-based violence.

SPECIFIC OBJECTIVES:

To develop mobile strategies to reach more women and children with education, primary health care and essential drugs so as to reach rural women with Ante Natal Care and emergency care in case of complications in non-accessible rural zones in Cameroon, Africa and refugees camps.

- To reinforce human resources in quantity and in quality in non-accessible rural zones through training workshops, seminars and conferences for better management of diseases in children.

- To sensitize the rural communities on the benefit of education, the protection of environment, hygiene and sanitation.

- To reinforce IEC activities on behavioral change and create awareness on diabetes, cardiovascular diseases, STIs, HIV/AIDS, cancers, unwanted pregnancies and abortion.

TARGET POPULATIONS

- Target Public 1: vulnerable children in rural zones

- Target Public 2: vulnerable women and young girls in rural zones and refugee camps.

- Target Public 3: villages in Cameroon and Africa.

- Target Public 4: local participants trained for the implementation of projects on health,

education, water, hygiene and sanitation.

Our staff is made of professional doctors, nurses, nurse aids, guest speakers, and volunteers; who work endlessly to foster our vision.

Humanitarians without Borders is the charity branch of The Saint Leonard Health and Research Foundation that empower community through health and education. Our projects range from basic research in our labs to field trips across the regions of Cameroon. We engage the rural populations and local authorities during free health campaigns into sensitization, vaccination, human rights, environmental campaigns and education programs and more.

OUR ACTIVITIES

We have been working on the following areas:

Health campaigns, sensitization, women and young girls’ empowerment, skills acquisition and entrepreneurship in underserved, non-accessible rural zones

## Appendix - Community Brochure (Historic)

## Appendix - Images

Appendix - NGO Charter

SAINT LEONARD HEALTH AND RESEARCH FOUNDATION ASSOCIATION

(updated 10 August 2019)

BYELAWS,

PREAMBLE:

We, members of the Saint Leonard Health and Research Foundation Association, are mindful of the Universal Declaration of Human Rights of 1948 on the right to health and healthy living to which Cameroon is a signatory.

Mindful of the constitution of the Republic of Cameroon [18/01/96] which attaches great importance to health.

Conscious of the increase rate of diseases in general and infectious diseases in particular, coupled with the poor socio-economic standards in our local communities on some health facilities and treatment, culminating in a high rate of morbidity and mortality.

Bearing in mind the dire need to increase awareness among the population in general and those of the local communities in particular on HIV/AIDS, STDs, STIs and related diseases.

We have proceeded to form this non-governmental and apolitical organization in conformity with law no 90/053 of 19/12/90 relating to the formation of associations in the Republic of Cameroon for the purposes and objectives outlined here below by which we bind ourselves for the higher interests of the community and the public good.

PART I- PRELIMINARIES

CHAPTER ONE: NAME, MOTTO AND SEAT

Article 1- NAME:

The name of the Association is SAINT LEONARD HEALTH AND RESEARCH FOUNDATION ASSOCIATION with the acronym SLHERF

Article 2- The Motto:

Prevention, Care and Health for all [A stitch in time saves nine]

Article 3- The Seat

The headquarter of the Association is at Bobende, Limbe II sub-division Fako Division, South West Region.  Email: slhef22@gmail.com

CHAPTER TWO: GENERAL PROVISIONS

Article 4- Scope of Activities (OBJECTIVES)

The Saint Leonard Health and Research Foundation Association shall be involved in the following:

- Health care services and delivery

- Community health education and awareness

- Outreach programmes in surrounding villages

- Research and medical training programmes in the local communities

- Publication of a periodic bulletin/newsletter

Article 5 – Vision – Mission – Strategies

(1) The Vision:

- Educate and motivate the community to adopt practical pre-emptive health measures for the purpose of saving lives within the framework of the Ministry of Public Health.

- Implement guidelines and measures to support organizations, donors and partners for the purpose of saving lives and for healthy living as approved by the Ministry of Public Health.

(2) The Mission:

- To provide primary health care facilities to the local communities such as consultations, prescriptions and low-priced / free drugs.

- Increase awareness on infectious diseases among the local population and measures of prevention with the view to saving lives in line with the objectives of the St Leonard Health Association.

(3)  Strategies:

(a) Carryout mobilization and sensitization campaigns in the local communities.

(b) Organize training workshops and seminars as the need may arise to raise awareness on basic health issues and infectious diseases in the local communities.

(c) collaborate with and be a link between the Ministry of Public Health, support organizations, partners, donors on the one hand and the local population on the other hand on issues of infectious diseases and preventive measures.

(d) Attend training workshops, seminars, open debates and round table conferences organized by the Ministry of Public Health and other approved organizations.

PART II- STRUCTURAL ORGANISATION AND FUNTIONING:

ARTICLE 6: The organs of the Association shall be as follows:

- The General Assembly

- The Executive Bureau

ARTICLE 7- Functioning

- The organs and offices shall function as follows:

- The General Assembly

- Shall be the most important and most powerful organ of the Association in terms of its attributions.

- It shall comprise of all registered members

- It shall elect the members of the executive Bureau

- It shall meet at least once a year

- It shall elect the executive Bureau

- It shall direct and control the activities of the Executive Bureau

- It shall vote the budget of the Association

- The quorum shall be 35% of regular members

- The Executive Bureau shall comprise of the following officers:

- The president

- The vice president

- The secretary

- The technical adviser

- The treasurer

- Financial secretary

- The Executive Bureau shall under the direction of the president meet at least once a year

- The executive Bureau shall implement the objectives of the Association with the aim of achieving success

- The executive Bureau shall fixe the remuneration of allowances of        its members.

- A member shall be entitled to one post only unless otherwise approved

by 2/3 vote of the members.

- THE PRESIDENT

Shall:

- Preside over the General Assembly meetings.

- Convene meetings of the General Assembly.

- Convene Extra-ordinary sessions of the General Assembly when necessary.

- Be the Chief Executive Officer of SLHERF in all public matters.

- Be the president / CEO of all SLHERF branches, sub branches and Clinics.

- Be the principal signatory of all SLHERF bank accounts and one of the signatories of all bank accounts of branches and sub branches of Saint Leonard Health and Research Foundation (SLHERF).

- THE VICE PRESIDENT

Shall:

- Replace the president in his absence.

- Carry out any function assigned by the president

- THE SECRETARY

Shall:

- Write and keep minutes of all meetings.

- Co-ordinate the various activities of SAINT LEONARD HEALTH AND RESEARCH FOUNDATION ASSOCIATION including branches, sub branches and Clinics.

- Give an annual report of the activities of SAINT LEONARD

HEALTH and RESEARCH FOUNDATION ASSOCIATION including branches, sub branches and Clinics.

- THE TREASURER

Shall:

- Keep an internal cash book signed by the president.

- Be a co-signatory to all accounts of SLHERF.

- FINANCIAL SECRETARY

Shall:

- Control the financial management of SLHERF and give a quarterly audit report to the president / CEO.  External Auditors shall be appointed when the need arises.

ARTICLE 8: FINANCIAL PROCEDURES

An account shall be opened in the name of SLHERF Cameroun. Signatory to such an account shall be the President, and the Treasurer. Internal regulations shall define the signatories for different operations under a project.

ARTICLE 9: ELECTIONS

- All the members of the Executive shall be elected by the General Assembly.

- Only regular members may vote or be elected.

- The quorum shall be 2/3 of majority and voting may be done by proxy.

- Election shall hold every two years with each Executive member being eligible for re-election.

- In case of resignation or death of an Executive member, a meeting of the General Assembly shall take place within 60days following resignation or death.

- The mandate of Executive members can be shortened on the grounds or demand at least 2/3 of the General Assembly. In such a case voting by proxy shall not be allowed.

ARTICLE 10: OWNERSHIP OF PROPERTY

SLHERF may own movable and no movable properties or have such other assets as may be likely to enhance its objectives.

In the event of dissolution such property shall be sold and proceeds distributed amongst SAINT LEONARD creditors and the rest deposited in any social home to be decided at that time.

ARTICLE 11: DISSOLUTION

SAINT LEONARD HEALTH AND RESEARCH FOUNDATION ASSOCIATION may be dissolved by a unanimous vote of General Assembly taken in an Extra-ordinary General Assembly concerned for the purpose.

APPENDIX A

FORMATION AND RESOLUTIONS

MINUTES OF THE CONSTITUENT MEETING

Meeting of the 10/9/2011 held at Bobende, Limbe II by its founding members aimed at creating St Leonard Health Association a non-governmental organization, non-tribal and apolitical was conceived with the resolve:

a) That the name of the non-governmental organization shall be SAINT LEONARD HEALTH and RESEARCH FOUNDATION ASSOCIATION.

b) That the main objectives shall be;

i) To empower local communities with basic and approved health facilities,

ii) Network with similar organizations to provide quality medical care,

iii) Research and medical training programmes in the local communities and

iv) To transform and save lives through the power of the word of God and medical care with the conviction that Man treats but God heals.

Elected board members on the 19th Mars 2019

| No | NAME | FUNCTION | PROFESSION | CONTACT |
| --- | --- | --- | --- | --- |
| 01 | Sokem Ngale Mborh | Director | Magistrate | 677690665 |
| 02 | Kouemou Sinda Leontine | Member | Infectious diseases specialist/humanitarian | 677442654 |
| 03 | Medong Adele Noel | Member | Economist | 00447438353877 |
| 04 | Mbimenyuy Bomki Cynthia | Member | Clinical researcher | 690691523 |
| 05 | Sara-Ana Rodriguez | Member | Lecturer/humanitarian | + 34600721557 |
| 06 | Fokoue Fabrice | Member | Medical doctor | 697669170 |
| 07 | Kathleen Russell | Member | Senior nurse | + 4404340142 |

Executive bureau elected on 11th Mars 2015

| No | NAME | FUNCTION | PROFESSION | CONTACT |
| --- | --- | --- | --- | --- |
| 01 | Kouemou Sinda Leontine | President | Infectiologist | 677442654 |
| 02 | Kamnang Bienvenu | Vice president | DIRECTOR SOREDI | 674122276 |
| 03 | Tonfack Sandrine | General secretary | PLEG | 670020759 |
| 04 | Sinda foumou Freud Tailor | Financial secretary | Radiologist | 675541311 |
| 05 | Fambalang Odilia | Vice secretary general | Physician assistant | 698259901 |
| 06 | Dinga Jerome Nyhala | Treasurer | Immunologist | 679820704 |
| 07 | Nkana Catherine | Member | Physician assistant | 699598934 |
| 08 | Bih Adig | Member | Assistant nurse | 674295657 |
| 09 | Doumbe Irene Christelle | Member | Assistant nurse | 676 56 23 34 |
| 10 | Ajong Rose | Member | Physician assistant | 695439577 |
| 11 | William Ebaye | Member | Medical microbiologist | 675042610 |
| 12 | Doh Gilbert | Member | Bacteriologist | 676168011 |
| 13 | Epopa NgomePatrick Stephane | Member | Immunologist | 675436101 |
| 14 | Minlo Frank | Member | Nutritionist | 675931651 |
| 15 | Limunga Hannah | Member | Physician assistant | 698259901 |
| 16 | Asick Ebanga | Member | Physician assistant | 679417756 |
| 17 | Chendjou Thimothe | Member | Physician assistant | 699148938 |
| 18 | Anyiagwa Esemoh | Member | Physician assistant | 677237728 |
| 19 | Mbeng Berenger | Member | Physician assistant | 695076354 |
| 20 | Tchountza Menda Landry | Member | Medical Bacteriologist | 695472913 |
| 21 | Ngah Meka | Member | Nurse Aid | 682675140 |

APPENDIX B

ASSISTANT LABORATORY TECHNICIANS PROGRAM

- Medical psycholology and sociology

- Human anatomy and physiology

- Human body in health and disease

- Pharmacology

- Primary healthcare and community health practice

- Nursing science

- Ethic law and religion

- Basic sciences (mathematics, physics and chemistry)

- Information Education and Communication Technology

- Hematology and transfusion science

- Parasitology

- Biochemistry

- Microbiology and bacteriology

- Virology and mycology

- Basic laboratory techniques

- Immunology

- Research project

- Language

- Sport

- Manual labor

APPENDIX C

NURSING ASSISTANTS PROGRAM

- Human anatomy and physiology

- Human body in health and pathologies

- Pharmacology

- Nursing science

- Pediatrics

- Obstetrical and gynecological nursing

- Basic science, mathematics, physics, chemistry

- Laboratory techniques

- Dietetics and nutrition

- Information Education and Communication Technology

- Primary health care and community health practice

- Ethics, law and religion

- Medical nursing

- Surgical nursing

- Nursing procedures

- Medical psychology and sociology

- Emergency nursing

- Language

- Sport

- Manual labor