## Monthly Progress Report: Child Protection in Yemen

Reporting Period: January 1 – April 20, 2026

### 1. Project Overview

- Project Title: Protecting Children in Yemen from Violence Amidst Conflicts and Crises.

- Implementing Partner: Sanid Organization for Relief and Development (SORD).

- Location: Yemen.

- Report Preparer: Shaif Ahmed Ali Ezz El-Din

      - Phone number	0096701231744

      - Current job	Project Manager

      - e-mail	Programs.officer@sanid.org

      - Mobile number	00967778515109

### 2. Humanitarian Context

Children in Yemen have faced severe hardships since 2015 due to ongoing conflict. The current situation includes critical challenges:

- Protection Risks: High vulnerability to violence, exploitation, and forced recruitment.

- Displacement: Ongoing forced displacement, with many children living in inadequate camp conditions and lacking basic services.

- Health & Nutrition: High rates of acute malnutrition and limited access to healthcare, clean water, and sanitation.

- Education & Psychosocial Needs: Severe disruption to the education system and widespread psychological trauma among children.

### 3. Strategic Objectives

The project aims to provide safety and resilience through:

- Essential Protection: Establishing Safe Spaces and providing psychosocial support (PSS).

- Awareness & Advocacy: Educating parents and communities on child rights and the harmful effects of exploitation.

- Capacity Building: Training staff and volunteers in professional child protection standards.

- Protection Networks: Strengthening local and national networks to ensure a coordinated response.

### 4. Key Achievements (Jan - Apr 2026)

Despite limited funding, SORD has focused on high-impact protection activities:

- Safe Space Operations: Sustained a Child-Friendly Space (CFS) providing a secure environment for displaced and conflict-affected children until July 2026.

- Psychosocial & Educational Support:

  - Conducted 30 awareness sessions led by female specialists.

  - Provided psychosocial support sessions for 50 children.

  - Engaged 80+ children in ongoing literacy and art activities (reading, writing, and drawing).

- Material Assistance:

  - Distributed winter clothing to 50 children during the cold season.

  - Provided general clothing to 30 additional children.

  - Supplied 80 children with light nutritional meals during CFS activities.

- Health & Nutrition Awareness: Facilitated access to primary healthcare and vaccinations while promoting healthy nutrition programs to combat malnutrition.

### 5. Visual Documentation

- Winterization: Distribution of winter clothing to vulnerable children.

- Recreational Activities: Children participating in physical and intelligence-building games at the CFS.

- Educational Support: Group awareness sessions and literacy/drawing workshops.

- Nutrition: Provision of light meals during project activities.

### 6. Contact Information

- Address: Al-Habari, Shu'ub District, Amanat Al-Asimah, Yemen.

- Phone: 00967 01231744

- Email: Programs.officer@sanid.org.

SANID ORGANIZATION FOR RELIEF AND DEVELOPMENT (SORD) Sana'a - Al-Hasba - Shu'ub District - Al-Hasba Al-Jamahiriya Street -Alhabari Round-behind Aljedri Station https://sanid.org www.facebook.com/sanid.org https://twitter.com/sanid_org https://www.instagram.com/sanidorganization

Tel : +9671231744 Mob:+967775433335 Email : info.sord@sanid.org