## work plan
PRESENTATION OF WOMEN EMPOWERMENT PROGRAM TRHOUGH MICRO FINANCE 2018 -2019
Objective of the project: Empowering around 80 vulnerable women and youth living in poor suburbs of kenya by helping them to start, run and improve their small businesses
Methodology: Through micro loans ($5 to $3000) ,bi-annual business training and also by an individual follow up
Scope - target = 80 widows, single mothers or HIV postive women in poor suburbs of kenya : Makadara , Kariobangi, buruburu and Taita
METHODOLOGY
STEPS | CONTENT | Details
1 | Find new members | Get in touch with local partner, church, members friends etc. Focus on vulnerable women : widows, single mother, HIV positive
2 | Individual interview | One hour individual evaluation = skills and motivation evaluation + terms and condition of the microfinances agreement
3 | Forming small groups of 5 plus electing the chairlady | We advice the members to form a group of 5 to create fellowship, helping each other, and for an easier folow up for Tumani staff
4 | Business plan creation and validation | Tumaini helps the member to create her plan in order to evaluate the needs and the sustainability of the project. And be used by Tumaini staff to follow the member up | x
5 | Capital to start the projects | Through micro loans between $5 to $3000 and according to their business plan (the average is $50)
6 | Business Management training | 2 days twice a year by the local partner "Kenya Institute of Business Training (KIBT)" | x
7 | Follow up/monitoring | 10 women per week are called or visited to their shop to check if everything is alright, if she needs help or just someone to listen to her | x
8 | Monthly meeting for HIV positive women | Create fellowship, support and a space to be listened and helped we share our testmonies every month about a different topic (eg. Depression, how to behave with customer, book keeping etc.) | !
9 | Tumaini continuous improvement | Every 3 months Tumaini's activities, behaviour, budget and effciency are evaluated in order to improve ourself | x
10 | Annual General Meeting | Meeting for everyone yearly in order to celebrate our hardwork with everyone and create special moment together | x

## budget for 1 year - 50 women
MICROFINANCE AND WOMEN EMPOWERMENT PROGRAM - BUDGET FOR 80 WOMEN FOR 1 YEAR-
STEPS | CONTENT | budget
|  | Cost/units ($) |  | number |  | duration |  | Total Cost ($)
EXPENSES | Business Management training (per group)
| Business Management training (by proffessional facilitator) | 5 | $/pers/day | 80 | pers | 3 | days | 1200
| Meeting room renting | 25 | $/room/day | 8 | room | 3 | days | 600
| Subtotal | [6 empty] | 1800
Capital to start the projects
| Capital (micro loans) | 50 | $/pers (average) | 80 | pers |  |  | 4000
| Subtotal | [6 empty] | 4000
Follow up/monitoring
| Transport for Tumaini staff in field | 10 | $/staff/month | 2 | staff | 12 | months | 240
| Subtotal | [6 empty] | 240
Annual General Meeting Award
| Drinks and snack | 5 | $/pers/day | 200 | pers | 1 | days | 1000
| Meeting room renting | 50 | $/room/day | 1 | room | 1 | days | 50
| Humble decoration | 30 | $/room | 1 | room | 1 | days | 30
| Subtotal | [6 empty] | 1050
Other related costs
| Tea and snacks for Hiv montlhy meeting | 1 | $/pers | 30 | pers | 12 | months | 360
| Book keeping and stationneries for business running | 5 | $/pers | 80 | pers |  |  | 400
| Subtotal | [6 empty] | 760
Administration and operating Expenses
| Stationary/ Communication i.e internet, postage, airtime, paper, ink, etc | 40 | $/month (average) |  |  | 12 | months | 480
| Office stationnary renewing (chair, printer, etc) | 100 | $/office/year | 1 | office | 1 | year | 100
| Subtotal | [6 empty] | 580
TOTAL OF EXPENSES | [7 empty] | 8430
INCOMES | fixed cost for micro loans appyling
| Processing fees | 2 | $/pers | 80 | pers |  |  | 160
| Office maintenance | 1 | $/pers/month | 80 | pers | 12 | months | 960
| Subtotal | [6 empty] | 960
loan and interest repayment
| Loan repayment | 50 | $/pers (average) | 80 | pers |  |  | 4000
| Interest (15%) | 7.5 | $/loans (average) | 80 | pers |  |  | 600
| Subtotal | [6 empty] | 4600
TOTAL OF INCOMES | [7 empty] | 5560
DIFFERENCE BETWEEN INCOME AND EXPENSES | [7 empty] | -2870 | $/years
$12 000 will help to run the Tumaini women empowernment program for four years

## Sheet1
MICROFINANCE AND WOMEN EMPOWERMENT PROGRAM - BUDGET FOR 50 WOMEN FOR 1 YEAR-
STEPS | CONTENT | budget
|  | Cost/units ($) |  | number |  | duration |  | Total Cost ($)
EXPENSES | Business Management training (per group)
| Business Management training (by proffessional facilitator) | 5 | $/pers/day | 15 | pers | 3 | days | 225
| Meeting room renting | 25 | $/room/day | 1 | room | 3 | days | 75
| Subtotal | [6 empty] | 300
Capital to start the projects
| Capital (micro loans) | 100 | $/pers (average) | 50 | pers |  |  | 5000
| Subtotal | [6 empty] | 5000
Follow up/monitoring
| Transport for Tumaini staff in field | 5 | $/staff/month | 2 | staff | 12 | months | 120
| Subtotal | [6 empty] | 120
Annual General Meeting Award
| Drinks and snack | 3 | $/pers/day | 200 | pers | 1 | days | 600
| Meeting room renting | 50 | $/room/day | 1 | room | 1 | days | 50
| Humble decoration | 20 | $/room | 1 | room | 1 | days | 20
| Subtotal | [6 empty] | 650
Other related costs
| Tea and snacks for montlhy meeting | 0.5 | $/pers | 50 | pieces | 12 | months | 300
| Book keeping and stationneries for business running | 5 | $/pers | 10 | pers |  |  | 50
| Subtotal | [6 empty] | 350
Administration and operating Expenses
| Stationary/ Communication i.e internet, postage, airtime, paper, ink, etc | 20 | $/month (average) |  |  | 12 | months | 240
| Office stationnary renewing (chair, printer, etc) | 50 | $/office/year | 1 | office | 1 | year | 50
| Subtotal | [6 empty] | 290
TOTAL OF EXPENSES | [7 empty] | 6710
INCOMES | fixed cost for micro loans appyling
| Processing fees | 2 | $/pers | 50 | pers |  |  | 100
| Office maintenance | 1 | $/pers/month | 50 | pers | 12 | months | 600
| Subtotal | [6 empty] | 600
loan and interest repayment
| Loan repayment | 100 | $/pers (average) | 50 | pers |  |  | 5000
| Interest (15%) | 15 | $/loans (average) | 50 | pers |  |  | 750
| Subtotal | [6 empty] | 5750
TOTAL OF EXPENSES | [7 empty] | 6350
DIFFERENCE BETWEEN INCOME AND EXPENSES | [7 empty] | -360 | $/years
Note on B4: Tumaini: Two hours training per week for each group => Kenya Institute of Business Training
Note on B8: Tumaini: according to the validated business plan
Note on B11: Tumaini: the first six weeks individual follow up,then afterwards montly follow up =>Tumaini staff + professional facilitator (at the beginning)
Note on B14: Tumaini: Two hours training per week for each group => Kenya Institute of Business Training