# Title: Save the lives of 492,140 school going pupils at Road crossing point when going to school and when coming back from school in Sierra Leone.

Project Implementation Location: Bo, Bonthe, Moyamba and Pujehun

Project Beneficiaries:  School Children, Youths and Aged Population.

Total Budget:

Implementing Partners:   Ministry of Education, Sierra Leone Road Safety Authority, Sierra Leone Police and the District Councils

Executive Summary:

Concern Mothers Movement for women’s Participation in Development Sierra Leone has been working with disadvantage children, Youths and women since 1998.

We are currently working with over 200 hundred schools, 250 school teachers and 300 hundred youth Lollipop ladies and Gents in Bo, Moyamba, Pujehun and Bonthe Districts of Sierra Leone with the Aim of saving the lives school going pupils when going to school and coming back from school at road crossing points in the towns and city in the Southern region of Sierra Leone.

This project is to be implemented in partnership with the Sierra Leone Police (SLP) Ministry of Health and Sanitation, Ministry of Basic and Senior Secondary Education, Sierra Leone Road Safety Authority and the District Councils.

The overall goal of this project is to reduce the accident rate in the country especially for schools pupils who find it difficult to cross the road when going to school in an urgent mode and about to get late.

It is an on-going project with the first Phase of two years with a well-structured management team and Monitoring and Evaluation team. The total cost of the project is U$$ 50,000 for two years.

Problem Statement

The road safety situation in Sierra Leone is serious and has deteriorated over the last years, mainly due to the growing vehicle population and ineffective implementation of the road safety interventions, Economic growth including rehabilitation of roads and increased vehicle growth will increase road safety challenges in the country.

SLP statistics show that 2,204 road traffic accidents (RTA) were reported during 2017, 165 of these were fatal crashes in which 216 persons were killed. Corresponding frequencies for 2018 are 2,501 RTAs, 232 fatal crashes and 322 fatalities; and for 2019 the numbers are 1,574 RTAs, 158 fatal crashes and 182 fatalities.

However, this is likely to reach at by 2020. It was estimated that over 55% of Road traffic Accident  occur in Southern region of Sierra Leone, even though it account for only 32% of total motor vehicle fleet, which involves 65% of pedestrians and 45% of school children. Child pedestrian injury, an important cause of morbidity and mortality remains one of the leading causes of death in Sierra Leone. Each year in Sierra Leone approximately 850 children under the age of 15 years are killed & another 30,000 are injured in pedestrian collisions. During last decades injuries due to Road Safety Accident have risen by 150% in Sierra Leone in contrast to 30-40% in the Southern Province. The chances of Road traffic Accident can be averted to a large extent, if school children who are going to be adults of tomorrow are made aware of road safety measures, Help them cross the road when going to school and after school will help save Sierra Leone Future Leaders and Development specialists. Hence this Project is focussed on school children to help reduce the risk the faced when going to school.

Justification

In Sierra Leone According to Research conducted by CMMWPD-SL a Forty percept (40%) of students lacked correct knowledge of traffic safety rules. In particular, knowledge of correct speed limit was lacking in 67.3% of the respondents. Girls were more aware of traffic rules to be followed at traffic lights (63%) and while crossing zebra lines (41.2%), whereas boys were more versed with rules for pedestrians (49.8%). Around 60% of school children had correct knowledge of risk factors. The awareness was almost same in both government & private Schools as well as in males & female students. Results of this study were similar to that done in other regions of the Country.

The Ministry of Education who is responsible for policy formulation, laws, regulations and strategies within education and training, The Ministry’s role in road safety was seen as currently minimal as there is no child road safety training in schools at elementary and tertiary level. There is need to develop, approve and implement school curricula and training programmes on child road safety training. CMMWPD-SL plans to involve the Ministry of  Education officials in this task.

Relevance of the project

Road traffic injuries and deaths have a terrible impact on individuals, communities and the country. They involve massive costs to often overburdened health care systems, occupy scarce hospital beds, consume resources and result in significant losses of productivity and prosperity, with deep social and economic repercussions.

The numbers speak for themselves: this is a public health and development crisis that is expected to worsen unless action is taken to help save our future generation.

Activities:

- Stakeholders consultative meeting on Road Safety Management

- Training of schools teachers to include road safety management in their lesson plan

- Training of Lollipop ladies and Gents on Road safety during emergency case/ accident

- Daily manding of the Zebra crossing point by Lollipop ladies and gents

- Procurement of Reflectors, First Aid Kits and Uniforms for Gents and Ladies

- Monitoring of Volunteers during duty

- School sensitization on road management

- Review meetings

- Report writing

- Evaluation

Objectives:

Sustainability:

The project will ensure that the community maintains the operations of the groups when funding stops. The organization will from the start ensure participation of all stakeholders, including beneficiaries in project planning, implementation, monitoring and evaluation. Awareness creation will be conducted throughout the life of the project to help in changing negative community attitudes, cultures and perceptions towards citizens. This will involve creation, printing and dissemination of IEC materials, sensitisation meetings and radio talk shows. CMMWPD-SL will continue to work closely with government departments and advocate for the inclusion of citizens issues and the poor community in the district and local governments plans and budgets.

Monitoring and Evaluation

CMMWPD-SL carries out planning of its activities at the beginning of each year. Participants include; staff, management, representatives of the board, stakeholders and grass root community members. After six months a review/ reflection of the plans is conducted and necessary adjustments made.

CMMWPD-SL is taking monitoring and evaluation as well as linking and learning as important for improving organizational relevance and achievement of results. It will also optimize the use of resources, beneficiary involvement to promote beneficiary satisfaction and maximize the impact of organizational contribution to the community.

CMMWPD-SL has adopted various tools to monitor its activities based on daily, weekly, monthly, quarterly and specific activities. Monitoring is carried out on weekly, monthly, and quarterly basis. The people involved in the monitoring include; the board of directors, management, staff, representatives of the organisations and the community..

PROJECT RISKS

- Continued flocking to the streets by organisations that might make the work quite overwhelming.

- Fluctuating prices and increasing inflation that might affect the budget of the project.

- Change in government policy on citizens which do not favour this proposal

Activity Plan

| Activities | Months |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| Stakeholders consultative meeting on Road Safety Management |  | x |  |  |  |  |  |  |  |  |  |  |
| Training of schools teachers to include road safety management in their lesson plan |  | x |  |  |  |  |  |  |  |  |  |  |
| Training of Lollipop ladies and Gents on Road safety during emergency case/ accident |  | x |  |  |  |  |  |  |  |  |  |  |
| Daily manding of the Zebra crossing point by Lollipop ladies and gents | x | x | x | x | x | x | x | x | x | X | x | x |
| Procurement of Reflectors , Fist Aid Kits And Uniforms for Gents and Ladies | x |  |  |  |  |  |  |  |  |  |  |  |
| School sensitization on road management | x | x | x | x | x | x | x | x | x | X | x | x |
| Monitoring of Volunteers during duty | x | x | x | x | x | x | x | x | x | X | x | x |
| Review meetings |  |  | x |  |  | x |  |  | x |  |  | x |
| Report writing | x | x | x | x | x | x | x | x | x | X | x | x |
| Evaluation |  |  |  |  |  | X |  |  |  |  |  | x |

| Budget for Save the lives of 492, 140 school going pupils in sierra leone |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Activity | Qty. | Unit cost | Frequency | Total cost | Exchage rate( U$$ 1= 9700 |
| 1 day Training of Teachers on Road Safety management in Schools For Bo, Bonthe Moyamba and Pujehun |  |  |  |  |  |
| Refreshment | 45 | 50,000 | 1 | 2,250,000.00 |  |
| Hall Rental | 1 | 500,000 | 1 | 500,000.00 |  |
| Stationaries | lump sum | 500,000 | 1 | 500,000.00 |  |
| Internal transport | 45 | 100,000 | 1 | 4,500,000.00 |  |
| Facilitators Fee | 3 | 250,000 | 1 | 750,000.00 |  |
| Books | 10 | 50,000 | 1 | 500,000.00 |  |
| Pens | 4 | 25,000 | 1 | 100,000.00 |  |
| Sub-total |  |  |  | 9,100,000.00 | $ 938.00 |
| Training on Road safety management of lollipop Ladies and Gents on Emmergency Cases in Bo, Pujehun, Bonthe and Moyamba |  |  |  |  |  |
| Refreshment | 75 | 30,000 | 1 | 2,250,000.00 |  |
| Hall Rental | 1 | 500,000 | 1 | 500,000.00 |  |
| Stationaries | 1 | 500,000 | 1 | 500,000.00 |  |
| Internal transport refund | 70 | 100,000 | 1 | 7,000,000.00 |  |
| Printing of Banner | 1 | 500,000 | 1 | 500,000.00 |  |
| Facilitators Fee | 2 | 250,000 | 1 | 500,000.00 |  |
| Books | 20 | 30,000 | 1 | 600,000.00 |  |
| Pens | 5 | 20,000 | 1 | 100,000.00 |  |
| Sub-total |  |  |  | 11,950,000.00 | $ 1,231.00 |
| Sensitazation and Media Engagement on Road safety Management |  |  |  |  |  |
| Radio Airtime | 2 | 500,000 | 6 | 6,000,000.00 |  |
| Pannellist | 3 | 30,000 | 6 | 540,000.00 |  |
| Moderator | 1 | 50,000 | 6 | 300,000.00 |  |
| Television Hour | 1 | 1,000,000 | 6 | 6,000,000.00 |  |
| Sub-total |  |  |  | 12,840,000.00 | $ 1,323.71 |
| Procurement |  |  |  |  |  |
| First Aid Kits | 4 | 1,000,000 | 4 | 16,000,000.00 |  |
| Uniform | 70 | 100,000 | 1 | 7,000,000.00 |  |
| Reflectors | 100 | 40,000 | 1 | 4,000,000.00 |  |
| Road Safety Management Sign Board | 50 | 100,000 | 1 | 5,000,000.00 |  |
| Road Safety Management IEC materials | 100 | 10,000 | 1 | 1,000,000.00 |  |
| Painting of the Zebra crossing points | 50 | 125,000 | 1 | 6,250,000.00 |  |
| Procurement of Motor bite for Monitoring | 2 | 7,500,000 | 1 | 15,000,000.00 |  |
| Sub-total |  |  |  | 38,250,000.00 | $ 3,943.00 |
| Administrative Cost |  |  |  |  |  |
| Stationaries | Lump sum | 500,000 | 6 | 3,000,000.00 |  |
| Utility Bills | Lump sum | 100,000 | 6 | 600,000.00 |  |
| Internet Connection | Lump sum | 500,000 | 6 | 3,000,000.00 |  |
| Office rent | 1 | 7,000,000.00 | 1 | 7,000,000.00 |  |
| Evaluation | 1 | 1,000,000.00 | 2 | 2,000,000.00 |  |
| Review Meetings | 4 | 3,000,000.00 |  | 12,000,000.00 |  |
| Sub-total |  |  |  | 27,600,000.00 | $ 2,845.36 |
| Personnel Cost |  |  |  |  |  |
| Executive Director | 1 | 3,000,000 | 6 | 18,000,000.00 |  |
| Program Manager | 1 | 2,000,000 | 6 | 12,000,000.00 |  |
| Admin/Finance Officer | 1 | 1,200,000 | 6 | 7,200,000.00 |  |
| Road Safety Cordinators | 2 | 1,000,000 | 6 | 12,000,000.00 |  |
| Monitoring and Evaluation Officer | 1 | 1,300,000 | 6 | 7,800,000.00 |  |
| Secretary | 1 | 800,000 | 6 | 4,800,000.00 |  |
| Project officer | 1 | 1,200,000 | 6 | 7,200,000.00 |  |
| Stipend for Lollipop Ladies and Gents | 70 | 500,000 | 6 | 210,000,000.00 |  |
| Stipend for Teachers | 20 | 200,000 | 6 | 24,000,000.00 |  |
| Sub-total |  |  |  | 303,000,000.00 | U$$ 31,237 |
| GRAND TOTAL (LE) |  |  |  | 485,000,000.00 | $ 41,518.08 |