PROGRAM REPORT

Date of submission: October 2, 2020

| Grant No. | #45194 |
| --- | --- |
| Grant receiving organization | Public Organization “Gurdofarid” |
| Project coordinator | Majidova Rahbar |
| Reporting period | July 20, 2020 – September 30, 2020 |
| Please describe how the goals of the program were met | Project “Vocational Education for 500 women in villages” in Bobojon Gafurov continued its second period from July 20, 2020. The main goal of the project is to provide education for girls and women on sewing, cooking, electric, driving and computer skills. Furthermore, another our goal is to improve the lifestyle of women and girls. In order to reach the goal of the project we created daily activity plan and conducted all events according that plan. We created 5 groups and conducted lessons on cooking, sewing and knitting. |
| Please provide statistical data, number of events, number of participants, geographical coverage | Event 1 –During the second period, we conducted 5 courses for 100 women. Women were from B. Gafurov town and Guliston town, Isfisor, Chorrukh-darron villages. (Sugd region). Each group covered 20 women. Two groups on Cooking course and three groups on Sewing and Knitting courses. Each group conducted the lessons for two months. All the courses started on July 25, 2020 and finished September 25, 2020. We conducted sessions three times a week and each lesson lasted for three hours, every group had 72 hours of instruction. - Cooking course in Gafurov – started on July 25, 2020 (20 women) - Cooking course in Chorukh-darron – started on July 25, 2020 (20 women) - Sewing course in Chorukh-darron – started on July 25, 2020 (20 women) - Sewing course in Gafurov – started on July 25, 2020 (20 women) - Knitting course in Isfisor – started on July 25, 2020 (20 women) |
| Please describe the kind of events organized; the issues discussed; the number of publications; the new contacts made | We conducted cooking, sewing, knitting, courses. We planned to hold several events like product sales, Job fair and show of clothes made by our dressmakers, but unfortunately due to the pandemic COVID -19 we were not able to implement our plans. Courses were conducted 3 days a week with a small number of groups for 3 hours. Generally in a month 36 hours and during the course 72 hours. |
| Immediate output results: Please describe the impact the grant has had on your organization and the participants in the program activities, including evidence of change of attitude or knowledge, and public reaction – | During the First period of project implementation, we organized courses for 30 women all these participants got certificates. Now we covered 100 women and they got their certificates on September 30, 2020. They have improved their level of sewing, cooking and knitting skills and life skills and now they will be able to work in different centers. The project helps to continue the activities that the organization is dedicated to. The project is the realization of organization’s main goal and priorities in education of local citizens and creating opportunities for them for positive change. In addition, the project helps to make positive impact in the local community and open future perspectives for the organization. |
| Long-term impact/performance: Please describe the likely future impact of the program and what new plans or projects were conceived | In 12 more months we plan to educate 320 more women and girls Sewing, Cooking and Computer, Driving and Electrician courses . |
| Any problems encountered and how they were solved | Yes, there were problems with COVID -19 and therefore our trainers had to conduct lessons not 6 times a week, but 3 times in a week and divided the participants into small groups. |
| Please indicate any address or telephone/fax changes. | All the address and phones the same |

All photos of events are attached in separate files to the financial statements.