BENIN EDUCATION FUND-ONG (BEF-ONG)                                                               BP: 676- Natitingou-Bénin;                                                         Tél: +22996168199/97986226                                                        E-mail : benineducationfundong@gmail.com                                   Sis Qtier Boriyouré, Logements sociaux                                  Enregistré sous le n°2004/P-SG-STCCD-DCD-ONG                                                                   du 17 février 2004

BENIN EDUCATION FUND-ONG (BEF-ONG)                                                               BP: 676- Natitingou-Bénin;                                                         Tél: +22996168199/97986226                                                        E-mail : benineducationfundong@gmail.com                                   Sis Qtier Boriyouré, Logements sociaux                                  Enregistré sous le n°2004/P-SG-STCCD-DCD-ONG                                                                   du 17 février 2004

BENIN EDUCATION FUND ONG

RAPPORT DU NIVEAU D’EXECUTION A MI-PARCOURS DES ACTIVITES DE L4ANNEE ACADEMIQUE 2020-2021

Juin  2018

Juin  2018

Janvier 2021

| RUBRIQUE |  | STATISTIQUES | Estimated Budget | Expenses | % of Budget | Not paid yet |
| --- | --- | --- | --- | --- | --- | --- |
| ELEVES | SCOLARITES ELEVES | 51 Secondary School Students (24 girls and 27 boys) | 2 407 000 | 1 435 000 | 59,62% | 972 000 |
|  | FOURNITURES BENEFICIAIRES | School supplies | 415 000 | 0 | 0,00% | 415 000 |
|  | SUIVI - SENSIBILISATIONS ET BESOINS EN SANTE BENEFICIAIRES | Health Insurance for students | 625 000 | 0 | 0,00% | 625 000 |
|  | SOUS-TOTAL 1 |  | 3 807 000 | 1 435 000 | 37,69% | 2 372 000 |
| ETUDIANTS | BOURSES ETUDIANTS (SCOLARITES COMPRIS) | 54 students | 7 177 200 | 1 550 000 | 21,60% | 5 627 200 |
| FOYERS BEF | FOYERS ETUDIANTS | BEF Housing Facilities rentals for university students | 2 277 000 | 1 763 000 | 77,43% | 514 000 |
|  | FOYERS ELEVES | Housing facilities for secondary school students. | 360 000 | 144 000 | 40,00% | 216 000 |
|  | SOUS-TOTAL 2 |  | 9 814 200 | 3 457 000 | 35,22% | 6 357 200 |
|  | TOTAL |  | 13 621 200 | 4 892 000 | 35,91% | 8 729 200 |
| USD Totals |  |  | $28,000 | $9,784 | 35.91% | $18,000 |

TABLEAU RECAPITULATIF DES PREVISIONS ET DU NIVEAU D’EXECUTION DU BUDGET

BEF highlight of key accomplishments thus far for School Year 2020 - 2021

- For the current school year, the Benin Education Fund, in addition to scholarships, rented three (3) additional community houses for the students that recently graduated from secondary school and moved to the university. In Total, for the current school year, 2020 – 2021, we are providing housing for 50 university students, including 15 female students.

- Our housing budget has significantly increased compared to previous years.

- Since 2018, a special program, BEF has created a new special program aimed recruiting our past drop out former beneficiaries and enrolling them in vocational schools, including engineering on renewable power energy, and information technology. For this year alone, 4 students are enrolled in such schools.

- Our program has focused more STEM, including mechanical, engineering (civil and electrical) fields.

- BEF also provided relief to 50 households economically affected by the COVID-19 pandemic by supplying food and cash transfers.