**ANNUAL WORK PLAN 2019/2020: FEED EDUCATE EMPOWER WOMEN AND GIRLS OF ACHOLI PROJECT**

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **CODE** | **ACTIVITIES** | **TIMELINE 2018/2019** | | | | | | | | | | | | **TARGET GROUP/BENEFICIARIES** | **RESPONSIBLE PERSON** |
| 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 |
|  | Identification of beneficiaries |  |  |  |  |  |  |  |  |  |  |  |  | 34 Vulnerable girls and 55 CNS/households in the target area | Coordinator |
|  | Payment of school fees |  |  |  |  |  |  |  |  |  |  |  |  | 20 Vulnerable girls | Treasurer and Chairperson Programs Committee |
|  | Provision of scholastic and sanitary materials |  |  |  |  |  |  |  |  |  |  |  |  | 12 vulnerable girls | Treasurer and Chairperson Programs Committee |
|  | Life skills training |  |  |  |  |  |  |  |  |  |  |  |  | 12 vulnerable girls(school) | Chairperson Programs Committee |
|  | Training in soap making |  |  |  |  |  |  |  |  |  |  |  |  | 7 girls O’ level leavers | Coordinator |
|  | Supply of food and nonfood items to Children/household with Nodding Syndrome - CNS |  |  |  |  |  |  |  |  |  |  |  |  | 34 CNS/households | Treasurer/Coordinator |
|  | Home care and counselling visits to CNS |  |  |  |  |  |  |  |  |  |  |  |  | 55 CNS/households | Coordinator/Group Team leader |
|  | Poultry production (eggs/meat) |  |  |  |  |  |  |  |  |  |  |  |  | 20 vulnerable girls/households and 55 CNS/households | Secretary and coordinator |
|  | Monitoring and Evaluation |  |  |  |  |  |  |  |  |  |  |  |  | Board /members and donor |  |