FRIENDS OF CANON GIDEON FOUNDATION

(FOCAGIFO)

24 MONTH WORK PLAN MAY 2014- JULY 2016

“Together AchievingMuch More”

In

The Global Race to S.A.V.E Lives from HIV & AIDS and other Life –reducing, life –taking and Life washing Realities that are both Preventable and Controllable.

PHYSICALADDRESS

Located 6 Miles off Bombo road, Adjacent Bishop Samuel

Chapel JinjaKalori, LC1 , above Katooke Police Station, Wamala Parish,

Nabweru Sub County, Wakiso District

P.O.Box 37270 Kampala

Tel: +256-414577201

Email.info@focagifo.org

Website: www.focagifo.org

CONTACT ADDRESS

1.      Right Rev Bishop Samuel B.Ssekkadde

Chairman Board of Trustees

Mobile Phone: + 256 77 2 500 494

2.  Rev Canon Prof.Gideon Byamugisha

Executive Director& Convener Global Working Group on Faith,

SSDDIM & HIV

Tel +256-782, 869102

Email. gideon_byamugisha @yahoo.co.uk

3. Assoc.Prof Grace MuwanguziKyeyune

Hope University Planning Rector

Tel.+256-713695219

Email.mgkyeyune@yahoo.com

4. Mrs Ruth NinsiimaMbalinda

Hope Institute Principal

Tel.+256 -782-925198

Email.runinsiima@yahoo.com

5. James Claude Mutyaba

Global Working Group on Faith, HIV

Secretariat Coordinator

Tel.+256- 782-732352

Email.jamesclaude@focagifo.org

| TABLE OF CONTENTS |  |
| --- | --- |
|  | Page |
| Acronyms |  |
| Forward Executive Summary |  |
| 1.0. Programme Overview..................................................................................................6 |  |
| 1.2. Vision, Goal and Specific objectives...........................................................................6 2.0. Planned Activities........................................................................................................7 3.0 Results Chain...............................................................................................................16 5.0 Appendices..................................................................................................................37 5.1 Appendix 1.Executive Board Members......................................................................37 5.2Appendix 2.Staff Members..........................................................................................38 |  |

ACRONYMS

ECSA: 	Eastern, Central & Southern Africa

DIT:                     Directorate of Industrial Training

EHAIA:		Ecumenical HIV & AIDS Initiative in Africa

FBOs:		Faith Based Organisation

FOCAGIFO: 	Friends of Canon Gideon Foundation

GWG:		Global Working Group on Faith, SSDDIM and HIV

HI-TLD:		Hope Institute for Transformational Leadership and Development

HUS:                    Hope University Semuto

IEC:		Information, Education and Communication

IRCU:		Inter-Religious Council of Uganda

NAFOPHANU: National Forum of People Living with HIV/AIDS Network in Uganda.

OVCs:		Orphans and other Vulnerable Children

OVIs:		Objectively verifiable indicators

SSDDIM		Stigma, Shame, Denial, Discrimination, Inaction and Mis-action

SAVE		Safe Practices; Access to treatment and nutrition; Voluntary and Routine stigma free Testing and 			Counselling and Empowerment of Children, Youth, Men, Women, Families and Communities

Most at risk of, Most –vulnerable to and most challenged by HIV and AIDS

TB		Tuberculosis

UBTEB                   Uganda Business Technical Examination Board

UGAPRIV              Uganda Association of Private Vocational Institution

# EXECUTIVE SUMMARY.

This Work Plan  is developed by Friends of Canon Gideon Foundation (FOCAGIFO)   a faith based  Non Governmental  Organization dully registered by National NGO Board ,Ministry of Internal Affairs with Reg No  S.5914/4347 .FOCAGIFO

FOCAGIFO’s origin is traced way back in 1992 when Rev Gideon Byamugisha (now Rev Canon Prof) who was the first Priest in Africa to publicly declare that he was living with HIV, came on a forefront together with others to reduce further spread of HIV infections especially among faith based communities. Since then ,FOCAGIFO has been responsible for  the  formation of UNERELA+  Uganda  Network for Religious Leaders Living with or personally affected by AIDS, ANERELA+1 (  African Network for Religious Leaders Living with or personally affected by AIDS) which later translated into INERELA+ International   Network for Religious Leaders Living with or personally affected by AIDS) which boasts of 10,000 members  in 48 countries , been   among  the founder members of NAFOPHANU ( National Forum of People Living With HIV &AIDS Networks in Uganda ), and the  Global Working Group on Faith, SSDDIM and HIV  an integration and ecumenical movement  of  people and leaders working for accelerated  HIV & AIDS  Competence at congregational and at National level .

FOCAGIFO also started the Hope Institute Transformational Leadership and Development which has supported, trained  and  graduated over 900 youth ( Orphans and  Other Vulnerable Children and Youths )  in various vocational courses and helping them to become productively employed, gainfully skilled, HIV and AIDS competent, social justice sensitive, spiritually empowered and environmental aware  leaders in their families and communities.

At present, FOCAGIFO has now embraced a big vision of establishing Hope University Semuto which will engage students, lectures and researchers in holistic education and integrated training for accelerated HIV & AIDS prevention, management and governance.

The Work plan 2014/2015 therefore is going to concentrate more on strengthening FOCAGIFO programmes  like The Hope Institute for Transformation Leadership & Development to make sure that all the 5 schools become fully operational, put in place infrastructures and lobby resources for the construction of Hope University Semuto and at the same time   lobby  support  of national organizations which are stronger, grounded, with a bigger population size and resources like IRCU and NAFOPHANU  to adopt and advocate for SSDIM Reduction and SAVE Multiplication strategy as a  more comprehensive Strategy for HIV Prevention, Care, Treatment and Impact Mitigation in Uganda .

In this Work Plan, FOCAGIFO will supplement and support both the local and central government’s efforts’ in the OVC empowerment in implementation and attainment of Vision 2040 for Uganda through skilling young people and in carrying out HIV & AIDS prevention and advocacy interventions

The WorkPlan will be implemented for a period of 24 months starting from May 2014 to June 2016 and it is budgeted to cost US$ 211,379 which is equivalent to Ugshs 528,447,950

- Programme Overview

This section presents the strategic framework and direction for Friends of Canon Gideon Foundation for the period of 24 months (May 2014-June 2016)

1.1 Vision, Goal and Specific Objectives (SO)

Vision:

“A world in which HIV and AIDS have been defeated”

Mission:

To reduce the vulnerability of individuals, families and communities and nations vulnerable to HIV & AIDS infections, illness and deaths and mitigate the impact of the epidemic using the anti- SSDDIM and Pro SAVE approach.

Goal:

To improve the capacity of individuals, families and communities and nations vulnerable to HIV & AIDS infections, illnesses and deaths and mitigate the impact of the epidemic using the anti-SSDDIM and Pro-SAVE approach.

FOCAGIFO Objectives.

- To advocate for the reduction of HIV and AIDS related SSDDIM and the Multiplication of SAVE at Individual, family, community and Institutional level.

- To strengthen the Capacity of Orphans and Vulnerable Children (OVC) to become HIV & AIDS Competent, gainfully skilled, productively employed, spiritually empowered, and social justice sensitive.

- To promote HIV and AIDS competence working through the faith sector communities.

- To enhance the Institutional Capacity of FOCAGIFO for effective programme implementation.

  - OBJECTIVES &PLANNED  ACTIVITIES FOR 2014/2016

PLANNED ACTIVITIES 2014- 2016

SO1. To advocate for the reduction of HIV and AIDS related SSDDIM and the Multiplication of SAVE at Individual, family, community and Institutional level.

Specific objective 1.1.To enhance Leadership Lobbying, Advocacy and Concretization  for the type of HIV Governance, AIDS Management and Societal Legislation needed to achieve and sustain zero new HIV infections, zero stigma and discrimination and zero AIDS related deaths in Uganda.

- Facilitate establishment of vibrant National Policy Dialogue and Action Forums on HIV and AIDS governance.

- Facilitate  National Working Group (NWG)  monthly  meetings

- Conduct conferences, workshops and seminars to promote policy dialogue among policy makers, researchers, civil society on good governance and leadership

- Hold roundtable dialogues with Parliamentary HIV and AIDS Committees, National AIDS Commissions, religious leaders, and other key policy makers to support and adopt theSSDDIM reductionand SAVEmultiplication approach.

- Hold advocacy talk shows on TV and Radio

- Facilitate SSDDIM Reduction  and SAVE Multiplication Solidarity Enhancement Days of Petitioning & Prayer (SEDOPP)

- Enhance the FOCAGIFO’s capacity in policy analysis and advocacy

- Facilitate key staff to attend GWG conferences and seminars at Global and  regional  level on SSDDIM reduction  and SAVE multiplication  approach

Strategic Objective 2.To strengthen the Capacity of Orphans and Vulnerable Children (OVC) to become HIV & AIDS Competent, gainfully skilled, productively employed, spiritually empowered, and social justice sensitive

Objective 2.1. To strengthen FOCAGIFO Hope Institute to deliver OVC Empowerment services.

Specific objective 2.1.1 Tomobilize Children (OVC) to attend FOCAGIFO Hope Institute.

- Carry out advertisement ventures on TV and Radio  to  mobilisation   students  (OVC)

- Print out advertisement  brochures and flyers

- Carry out  field visits  to identify in communities

- Print out sign posts

- Carry out DJ slots on radios

- Conduct Radio programmes

- Conduct OVC selection committee meetings

- Conduct  Caregivers orientation meetings for the new OVC

Specific objective 2.1.2.To facilitate the departments of FOCAGIFO Hope Institute.

- Facilitate Fashion and Design Department

- Facilitate Motor Vehicle Department

- Facilitate Beauty and Cosmetology Department

- Facilitate Carpentry and Joinery Department

- Facilitate Electrical Installation Department

- Facilitate the welfare department

Specific objective 2.1.3.To expand the provision &access of vocational skills to OVC at Hope Institute.

- Construct toilet facility

- Plastering , flooring  and fixing of windows for Canon Ernest Building

- Registration of Hope Institute  and Hope University Semuto with bodies

- Conduct OVC graduation ceremony

- Conduct OVC caregivers meetings for phase out

Objective 2.1. To strengthen FOCAGIFO Hope Institute to deliver OVC Empowerment services.

Specific objective 2.1.4 To strengthen the spiritual, psychosocial and  HIV&AIDS  competencies of  OVC at the Institute

- Conduct play /games therapy session for OVC

- Conduct HIV Counselling  and Testing outreaches to OVC and their households

- Hold FOCAGIFO Day

Specific Objective 2.1.5.To support OVC in  informal and formal education to  retain  them in school

- Pay tuition to OVC to acquire vocational education

- Conduct follow up on  revolving fund for OVC caregivers

- Facilitate  OVC to acquire  health services

- Conduct child protection sessions to reduce child abuse in the community.

- Distribution of OVC support & empowerment IEC   promotion materials

Strategic Objective 2. To strengthen the Capacity of Orphans and Vulnerable Children (OVC) to become HIV & AIDS Competent, gainfully skilled, productively employed, spiritually empowered, and social justice sensitive.

Objective 2.2To establish Hope University Semuto(developing infrastructures and furnishings)

2.2.1  Carry out resource mobilisation to raise Ugshs293,410,000 aimed to;

- Develop the HUS constitution, Bills of quantities, Human Resource Policy, Interns and Volunteers Policy, HUS Development Plan

- Generate Architectural, Structural Drawings and Master Plan (this includes approval fees)

- Conduct landscaping and Aesthetical designs/ impressions

- Carry out Site  Clearance and Leveling

- Carry out registration with Ministry of Education and Sports ( MoES), National Council for Higher Education  ( NCHE ) and Inter –University Council

2.2.1.1Planned Activities to achieve the above will include;

- Develop proposals and concept papers and sent to different agencies.

- Coordinate volunteers who come in to support in construction of the HUS Library

- Hold a meeting with Katikiro and Minister of Education, Buganda Government

- Hold a meeting with the Speaker of Parliament

- Hold a meeting with the President /Vice President of the Republic of Uganda

- Hold a meeting with Ambassador of the Government of Japan

- Hold a meeting with Ambassador of the Government of Germany

- Hold a meeting with Ambassador of the Government of Netherland

Strategic Objective 2. To strengthen the Capacity of Orphans and Vulnerable Children (OVC) to become HIV & AIDS Competent, gainfully skilled, productively employed, spiritually empowered, and social justice sensitive.

Objective 2.2 To establish Hope University Semuto (developing infrastructures and furnishings)

2.2.2 Carry out resource mobilisation to attract UgShs 163,000,000 meant for;

- Conducting   opening and construction of Access Roads (gravel at least 7m wide with Drainage works)

- Carry out design and construction of a simple water supply system with production capacity of 1600m3 per month.

- Carry out design and construction of a sewerage system with Lagoons (Oxidation Ponds)

- Conduct construction of Administration and Accounts Section Building (Senate), approx 1,200m2

2.2.2.2 The activities planned to raise the above  will include;

- Hold a  meeting with the Minister of Education & Sports  GoU

- Hold a meeting with Ambassador of the Government of Belgium

- Hold a meeting with the Ambassador of USA

- Develop proposals and concept papers to raise funds.

- Hold a meeting with Ambassador of the Government of Sweden

- Hold a meeting with Ambassador of the Government of Ireland

- Conduct HUS Task Force  meeting

2.2.3 Carry out resource mobilisation geared to raise Ugsh5,400,000,000 which will be used to;

- Construct  a school with 6 class rooms, 6 workshops, an office, a staff room,  a Lecture hall, a store and Toilets

- Construct  a Dormitory to accommodate 1,000 students (250 Rooms)

Strategic Objective 2. To strengthen the Capacity of Orphans and Vulnerable Children (OVC) to become HIV & AIDS Competent, gainfully skilled, productively employed, spiritually empowered, and social justice sensitive.

Objective 2.2 To establish Hope University Semuto (developing infrastructures and furnishings)

2.2.3.3 Planned activities to achieve the above will include;

- Coordinate volunteers who come in to  construct the HUS Library

- Hold a meeting with Ambassador of the Government of United Kingdom ( UK)

- Hold a meeting with Country Director of USAID

- Hold a meeting with the Ambassador of China

- Hold a meeting with Country Director of Irish AID

- Hold a meeting with country of Director DANIDA

- Hold a meeting with Ambassador of the Government Denmark

- Hold a meeting with Executive  DFCU

- Hold a meeting with Executive Director  DFID

- Carry out fundraising dinners

- Formation of HUS University Council and Council Committees

- Coordinate   holding of a fundraising friendly match between Uganda Cranes & Togo National Team

Strategic Objective 2. To strengthen the Capacity of Orphans and Vulnerable Children (OVC) to become HIV & AIDS Competent, gainfully skilled, productively employed, spiritually empowered, and social justice sensitive.

Objective 2.2 To establish Hope University Semuto (developing infrastructures and furnishings)

2.2.4. Carry out resource mobilisation to raise atUgshs1,080,000,000 which will be used to;

- Conduct  construction of  HUS  Library Approx. covering 1,200m3

- Conduct construction of Staff Quarter (3 Bedroom self contained house)

2.2.4.4 PlannedActivities to be carried will include;

- Carry out branding of HUS products

- Conduct a breakfast meeting with BaggaggaKwagalana Kampala Group

- Hold a friendly fundraising match between Uganda Cranes & Togo

- Hold a meeting with Executive Director of Coca Cola

- Hold a meeting with Executive Director of Airtel

- Hold a meeting with Executive Director of MTN

- Hold a meeting with Executive Director of Roofings

- Hold a meeting with Pastor of Miracle centre Cathedral

- Hold a meeting with Executive Director of Stanbic Bank-Main Branch

- Hold a meeting with Executive Director of Barclays Bank –Main Branch

- Hold a meeting with Executive Director of UCHUMI Garden City &GAME Lugogo

2.2.5Carry out fundraising to raise Ugshs250,000,000 meant for;

- Construction of a dining Hall, Kitchen and store inclusive

- Construction of a Health Centre

- Construction of a 5 stance Drainable VIP Latrine

Strategic Objective 2. To strengthen the Capacity of Orphans and Vulnerable Children (OVC) to become HIV & AIDS Competent, gainfully skilled, productively employed, spiritually empowered, and social justice sensitive.

Objective 2.2 To establish Hope University Semuto (developing infrastructures and furnishings)

2.2.5.5  Planned Activities to be conducted will include;

- Hold a meeting with Executive Director of Standard Charted Bank ( Main)

- Hold a meeting with Executive Director of Equity bank  ( Main)

- Hold a meeting with Executive Director of  Catholic Relief- National Secretariat

- Hold a meeting with  Executive Director of Adventist Relief Agency ( ADRA)

- Hold a meeting with secretary General of Inter Religious Council of Uganda

- Hold a meeting with Executive Director of Anglican Development Relief Fund

- Hold a meeting with the Ambassador of Australia

- Hold a meeting with a consular of Canada

- Hold a meeting with the consular of Israel

2.2.6 Carry out activities  to mobilize Ugshs  349,500,000 meant for

- Furnishing of Classrooms (buying chairs, tables and chalkboards.

- Furnishing of Dormitories

2.2.6.6 PlannedActivities to raise the above funds will include;

- Carry out University Council meetings

- Hold talk shows on Radio & TV

- Hold meeting with Consular of Norway

- Hold a meeting with Executive Director of Vivo Energy Uganda

- Hold a meeting with Executive Director of Total

- Hold a meeting with Executive Director of Standard Super Market

Strategic Objective 3. To promote HIV and AIDS competence working through the faith sector communities.

Specific objective 3.1:To strengthen Congregational and local community level responses for HIV prevention

- Conduct training workshop for community and local level Trainers of Ambassadors of Life and Peace

- Facilitate and monitor Ambassadors of Life, Health and Peace in peer – to – peer SSDDIM Reduction and SAVE- Multiplication AIDS Competency.

- Carry out capacity and competency building workshop of fait leaders to effectively engage in theological dialogue, reflection and critical analysis of HIV &AIDS

- Develop, print and distribute SSDDIM Reduction and SAVE- Multiplication IEC Materials

- Mobilize religious leaders to mainstream SSDDIM reduction and SAVE multiplication approaches into various religious ceremonies and events.

- Conduct music ,dance and drama  festivals among local congregations and schools to disseminate HIV prevention messages and HCT

- Facilitate youth with  sportsequipments to reach out  to community members with SSDDIM reduction and SAVE multiplication  messages

- Develop and document  best practices, success stories and learning regarding SSDDIM reduction and SAVE multiplication interventions

Strategic Objective 4. To Enhance the Institutional Capacity of FOCAGIFO for effective programme Implementation.

Specific objective 4.1 To mobilize resources (in-kind & Financial)  for   FOCAGIFO Hope Institute& Hope University Semuto.

- Conduct courtesy visit calls to 30 corporate institutions &companies.

- Conduct courtesy visits to 30 business entrepreneurs and individuals

- Develop proposals and concept papers

- Establish a Bakery to produce FOCAGIFO Bread

- Establish FOCAGIFO Hope Institute Farm at Semuto

Specific Objective 4.2   To develop systems, policies &procedures to guide operation of  Hope institute & Hope University Semuto.

- Conduct FOCAGIFO/ HUS/HI-TLD  Trustees Conference on governance & management

- Review FOCAGIFO constitution

- Develop Volunteers & Interns Management Policy

- Formation of  New FOCAGIFO Board

- Hold a retreat to review FOCAGIFO Strategic Plan 2009/2010-2012/2013.

- Hold Professors-In –Residence Forum for HUS Curriculum and Courses Development

- Procure Institute’s   vehicle

- Procure  Institute’s computers

Specific objective 4.3 To support the Board Governance to effectively carry out their governance role.

- Hold orientation workshop of the new Board

- Hold bi-annual   Board meetings

- Hold bi-annual  Board committees

- Hold Board & staff retreat

- Hold Annual General meeting.

- Hold monthly management meetings

Specific Objective 4.4  To enhance the competencies of the staff for effective planning & implementation of FOCAGIFO programs.

- Facilitate staff who have gone for higher studies.

- Facilitate staff to attend  tailor made training e.g  resource mobilisation & management among others

- Facilitate staff to attend District & National workshops and seminars.

Strategic Objective 4. To Enhance the Institutional Capacity of FOCAGIFO for effective programme Implementation.

Specific Objective 4.5  .To Carry out Monitoring and Evaluation

- Conduct school and home visits to OVC

- Carry out support supervision to OVC graduates

- Conduct follow up activities to revolving fund beneficiaries

- Conduct community mapping to establish a community Referral System for OVC support

- Conduct Stakeholders ‘review meetings

- Document  and sharing of success stories

- Conduct follow up to OVC Caretakers’ IGA Initiatives.

- Update of FOCAGIFO website

FOCAGIFO WORKPLAN/RESULTS CHAIN ( MAY 2014-JULY2016)

| Time Frame | Time Frame in Quarters of 6 months each. |  |  |
| --- | --- | --- | --- |
|  | Activities | Target | Responsible Person | QR1 | QR2 | QR3 | QR4 | What is required | Budget estimate in UgShs |
| SO1. To advocate for the reduction of HIV and AIDS related SSDDIM and the Multiplication of SAVE at Individual, family, community and Institutional level. |
| Specific objective 1.1 To enhance Leadership Lobbying, Advocacy and Concretization for the type of HIV Governance, AIDS Management and Societal Legislation needed to achieve and sustain zero new HIV infections, zero stigma and discrimination and zero AIDS related deaths in Uganda. |
|  | Facilitate establishment of vibrant National Policy Dialogue and Action Forums on HIV and AIDS governance | 50 Stakeholders | Executive Director |  |  |  |  | Airtime Fuel Refreshments Stationary | 1,872,000 |
|  | Facilitate National Working Group (NWG) monthly meetings | 50 Stakeholders | Executive Director |  |  |  |  | Airtime Fuel Refreshments Stationary | 2,944,000 |
|  | Conduct workshops to promote policy dialogue among policy makers, researchers, civil society on good governance and leadership | 75 People trained | Executive Director |  |  |  |  | Airtime Fuel Refreshments Stationary | 10,806,350 |
|  | Hold roundtable dialogues with Parliamentary HIV and AIDS Committees, National AIDS Commissions, religious leaders, and other key policy makers to support and adopt the SSDDIM reduction and SAVE multiplication approach. | 150 Legislators | Executive Director |  |  |  |  | Airtime Fuel Stationary Refreshments | 4,116,000 |
|  | Hold advocacy talk shows on TV and Radio | 2 Radios and 2 Television | Executive Director |  |  |  |  | Airtime fee Fuel | 4,144,000 |
|  | Facilitate SSDDIM reduction and SAVE multiplication Solidarity Enhancement Days of Petitioning & Prayer (SEDOPP) | 150 people | Executive Director |  |  |  |  | Airtime Stationary Refreshments Personnels | 3,304,500 |
|  | Facilitate key staff to attend GWG conferences and seminars at Global and regional level on SSDDIM reduction and SAVE multiplication approach | 3 Staff | Executive Director |  |  |  |  | Air tickets Perdiem Accomodation | 5,800,000 |

|  | Enhance FOCAGIFO Capacity in Policy analysis and Advocacy | 20 people | Executive Director |  |  |  |  | Airtime Stationary Refreshments | 3,592,000 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective 2. To strengthen the Capacity of Orphans and Vulnerable Children (OVC) to become HIV & AIDS Competent, gainfully skilled, productively employed, spiritually empowered, and social justice sensitive |
| Objective 2.1. To strengthen FOCAGIFO Hope Institute to deliver OVC Empowerment services . |
| Activity 1 To mobilize Children (OVC) to attend FOCAGIFO Hope Institute |  |  |  |  |
|  | Carry out advertisement on TVto mobilisation students (OVC) | 1 advert carried out | Principal |  |  |  |  | Airtime Personnel Transport costs | 200,000 |
|  | Carry out advertisement on Radio to mobilize students (OVC) | 50 announcements on 5 Radios | Principal |  |  |  |  | Airtime Personnel Transport costs | 500,000 |
|  | Conduct radio programmes | 3 Radio Programmes Conducted | Principal |  |  |  |  | Airtime Personnel Transport costs | 900,000 |
|  | Print out advertisement brochures and flyers | 1000 brochures & flyers printed | Principal |  |  |  |  | Funds Personnel Transport costs | 600,000 |
|  | Carry out field visits to identify and verify OVC (churches ,mosques & schools) | 20 field visits conducted | Principal |  |  |  |  | Personnel Transport costs | 300,000 |
|  | Carry out Radio DJ slots | 20 slots conducted | Principal |  |  |  |  | Airtime Personnel Transport costs | 30,000 |
|  | Sign post | 3 |  |  |  |  |  | Transport Professional fee | 600,000 |
|  | Printing of posters | 100 |  |  |  |  |  | funds | 100,000 |
| Strategic Objective 2. To strengthen the Capacity of Orphans and Vulnerable Children (OVC) to become HIV & AIDS Competent, gainfully skilled, productively employed, spiritually empowered, and social justice sensitive. |
| Objective 2.1. To strengthen FOCAGIFO Hope Institute to deliver OVC Empowerment services |
|  | Printing of posters | 100 posters printed |  |  |  |  |  | Funds Airtime Transport costs | 100,000 |
|  | Print out sign posts | 3 sign posts printed |  |  |  |  |  | Funds Airtime Transport costs | 600,000 |
| Activity 2 To facilitate the departments of FOCAGIFO Hope Institute |
|  | Facilitate Fashion and Design Department | Materials and equipments procured | Principal & Administrator |  |  |  |  | Funds for materials Fuel | 2,462,000 |
|  | Facilitate Motor Vehicle Department | Materials and equipments procured | Principal & Administrator |  |  |  |  | Funds for materials Fuels | 3,329,250 |
|  | Facilitate Beauty and Cosmetology Department | Materials and equipments procured | Principal & Administrator |  |  |  |  | Funds for materials Fuel | 5,812,300 |
|  | Facilitate Carpentry and Joinery Department | Materials &equipments procured | Principal & Administrator |  |  |  |  | Funds for materials Fuel | 4,760,000 |
| Strategic Objective 2. To strengthen the Capacity of Orphans and Vulnerable Children (OVC) to become HIV & AIDS Competent, gainfully skilled, productively employed, spiritually empowered, and social justice sensitive. |
| Objective 2.1. To strengthen FOCAGIFO Hope Institute to deliver OVC Empowerment services. |
|  | Facilitate Electrical Installation Department | Materials &equipments procured | Principal & Administrator |  |  |  |  | Funds for materials Fuels | 1,075,750 |
|  | Facilitate the welfare department | Materials and equipments procured | Dean of students |  |  |  |  | Funds for materials Fuels | 32,960,000 |
| Activity 3 To expand the provision &access of vocational skills to OVC |
|  | Construct toilet facility | Toilet facility built | Executive Director |  |  |  |  | Materials Labour | 7,768,500 |
|  | Plastering,shutting and flooring of the main block which serves as class rooms | Canon Ernest Building plastered floored, windows and doors fixed. | Executive Director |  |  |  |  | Materials Labour | 6,990,000 |
|  | Registration of Hope Institute with UBTEB and HUS with NCHE | Hope Institute acquire a UNEB centre and registered with MOES, HUS acquires Interim Authority | Principal |  |  |  |  | Personnel Professional fee Fuel | 3,450,000 |
| SO2. Objective 2.1. To strengthen FOCAGIFO Hope Institute to deliver OVC Empowerment services. |
|  | Conduct OVC graduation ceremony | 60 Graduands passed out | Principal |  |  |  |  | Airtime Personnel Stationary Fuel Refreshment | 1,540,000 |
|  | Hold FOCAGIFO Day | 12 meetings conducted | Executive Director |  |  |  |  | Personnel Airtime Venue | 1,020,000 |
|  | Conduct Play or games therapy sessions | 150 youths | Principal |  |  |  |  | Funds Fuel Personnel | 1,590,000 |
|  | Facilitate youth with tuition fee | 40 | Principal |  |  |  |  | Personnel Professional fee | 30,000,000 |
|  | Provide start up kits to the OVC graduate |  |  |  |  |  |  |  | 10,080,000 |
| Activity 5 To strengthen the spiritual, health, psychosocial and HIV&AIDS competencies of OVC at the Institute |
|  | Promote Health services for the Youths | 3 meetings | M&E Department |  |  |  |  | Sports equipments Time Personnel | 3,120,000 |
|  | Conduct Child protection sessions | 40 sessions conducted | M&E Department |  |  |  |  | Personnel Time | 375,000 |
| SO2. Objective 2.1. To strengthen FOCAGIFO Hope Institute to deliver OVC Empowerment services. |
| Activity 6. To support OVC in formal education to retain them in school |
| SO2. Objective 2.Establish Hope University Semuto( Developing infrastructures and furnishings) |  |  |  |
| Activity 2.1 Raise Ugshs293,410,000 todevelop the HUS constitution, Bills of quantities, Human Resource Policy, Interns and Volunteers Policy, HUS Development Plan |
|  |  | Raise Ugshs293,410,000 to -Develop the HUS constitution, Bills of quantities, Human Resource Policy, Interns and Volunteers Policy, HUS Development Plan Generate Architectural, Structural Drawings and Master Plan |  |  |  |  |  |  |  |
|  | Conduct Official launch of the Business Plan to the Public |  | HUS rector |  |  |  |  | Venue Stationary Personnel Refreshments | 7,981,000 |
|  | Hold a one day Board meeting to receive the HUS Business Plan 2013-2017 |  | HI-TLD Principal |  |  |  |  | Refreshments Communication Venue Personnel Transport refund | 2,561,000 |
|  | SO2. Objective 2.Establish Hope University Semuto( Developing infrastructures and furnishings) |
| Activity 2.1 Raise Ugshs293,410,000 todevelop the HUS constitution, Bills of quantities, Human Resource Policy, Interns and Volunteers Policy, HUS Development Plan |
|  | Develop proposals and concept papers and sent to different agencies | (this includes approval fees) -Conduct landscaping and Aesthetical designs/ impressions -Carry out Site -Clearance and Leveling -Carry out registration with Ministry of education and sports, -NCHE | HUS Rector |  |  |  | Personnel Communication Fuel Professional fee Transport/Vehicle | In -kind |
|  | Coordinate volunteers who come in to support in construction of the HUS Library |  |  |  |  |  |  | Airtime Fuel Refreshments | 705,000 |
|  | Coordinate process for registration with NCHE & NEMA | Raise Ugshs293,410,000 to -Develop the HUS constitution, Bills of quantities, Human Resource Policy, Interns and Volunteers Policy, HUS Development Plan Generate Architectural, Structural Drawings and Master Plan (this includes approval fees) -Conduct | HUS Rector |  |  |  |  | Personnel Stationary Transport/Vehicle Fuel Airtime Registration costs | 174,000 |
|  | Hold a meeting with Katikiro and Minister of Education, Buganda Government |  | HUS Rector |  |  |  |  | Airtime Personnel Fuel Vehicle Professional fee | 174,000 |
|  | Hold a meeting with the Speaker of Parliament |  | Planning & Projects Director |  |  |  |  | Personnel Laptop Computer Modem Internet airtime Fuel Vehicle | 174,000 |
| SO2. Objective 2.Establish Hope University Semuto( Developing infrastructures and furnishings) |
| Activity 2.1 Raise Ugshs 293,410,000 to develop the HUS constitution, Bills of quantities, Human Resource Policy, Interns and Volunteers Policy, HUS Development Plan . |
|  | Hold a meeting with Ministry of Education & Sports Minister | landscaping and Aesthetical designs/ impressions -Carry out Site -Clearance and Leveling -Carry out registration with Ministry of education and sports, -NCHE and Inter –University Council |  |  |  |  |  | Fuel Personnel Stationary Vehicle | 174,000 |
|  | Hold a meeting with Ambassador of the Government of Japan |  | HUS Rector |  |  |  |  |  | 174,000 |
|  | Hold a meeting with Ambassador of the Government of Germany |  | HUS Rector |  |  |  |  | Fuel Personnel Stationary Vehicle Allowances | 174,000 |
|  | Hold a meeting with Ambassador of the Government of Netherland |  | HUS Rector |  |  |  |  | Fuel Personnel Stationary Vehicle Allowances | 174,000 |
|  | Hold quarter HUS Task force meeting |  | HUS Rector |  |  |  |  | Fuel Personnel Stationary Vehicle | 560,000 |
|  | SO2. Objective 2.Establish Hope University Semuto( Developing infrastructures and furnishings) |
|  | Specific objective2.2 Raise UgShs 163,000,000 meant for;-Conducting opening and construction of Access Roads (gravel at least 7m wide with Drainage works) |
|  | Hold a meeting with Ambassador of the Government of Belgium | Raise UgShs 163,000,000 meant for; -Conducting opening and construction of Access Roads (gravel at least 7m wide with Drainage works) -Carry out design and construction of a simple water supply system with production capacity of 1600m3 per month. -Carry out design and construction of a sewerage system with Lagoons (Oxidation Ponds) -Conduct construction of Administration and Accounts Section Building (Senate), approx 1,200m2 | HUS Rector |  |  |  |  | Fuel Personnel Stationary Vehicle | 174,000 |
|  | Hold a meeting with the Ambassador of USA |  | HUS Rector |  |  |  |  | Fuel Personnel Stationary Vehicle | 174,000 |
|  | Develop proposals and concept papers to raise funds |  | HUS Rector |  |  |  |  | Fuel Personnel Stationary Vehicle | 174,000 |
|  | Hold a meeting with Ambassador of the Government of Sweden |  | HUS Rector |  |  |  |  | Fuel Personnel Stationary Vehicle | 174,000 |
|  | Hold a meeting with Ambassador of the Government of Ireland |  | HUS Rector |  |  |  |  | Fuel Personnel Stationary Vehicle | 174,000 |
|  | 2.3 Raise Ugshs 5,400,000 for construction of 6 class rooms,6workshops,offices,staff rooms etc |  |  |  |  |  |  |  |  |
|  | Conduct HUS Task Force meeting | Raise Ugsh5,400,000,000 which will be used to; -Construct of a school with 6 class rooms, 6 workshops, an office, a staff room, a Lecture hall, a store and Toilets -Construct of Dormitory to accommodate 1,000 students (250 Rooms) | Hus Rector& Executive Director |  |  |  |  |  | 280,000 |
|  | Coordinate volunteers who come in to support in construction of the HUS Library |  | Hus Rector & Executive Director |  |  |  |  | Personnel Fuel Vehicle | 280,000 |
|  | Hold a meeting with Ambassador of the Government of Britain |  | Hus Rector & Executive Director |  |  |  |  | Fuel Personnel Stationary Vehicle | 174,000 |
|  | Hold a meeting with Country Director of USAID |  | Hus Rector & Executive Director |  |  |  |  | Fuel Personnel Stationary Vehicle | 174,000 |
|  | Hold a meeting with Country Director of Irish AID |  | Hus Rector & Executive Director |  |  |  |  | Fuel Personnel Stationary Vehicle | 174,000 |
|  | Hold a meeting with country Director DANIDA |  | Hus Rector & Executive Director |  |  |  |  | Fuel Personnel Stationary Vehicle | 174,000 |
|  |  | 2.3 Raise Ugshs 5,400,000 for construction of 6 class rooms,6workshops,offices,staff rooms etc |
|  | Hold a meeting with Ambassador of the Government Denmark |  | Hus Rector & Executive Director |  |  |  |  | Fuel Personnel Stationary Vehicle | 174,000 |
|  | Hold a meeting with Managing Director DFCU | 1 meeting conducted | Hus Rector & Executive Director |  |  |  |  |  | 174,000 |  |
|  | Hold a meeting with Managing Director DFID | 1 meeting conducted | Hus Rector & Executive Director |  |  |  |  | Fuel Personnel Stationary Vehicle | 174,000 |
|  | Formation of HUS University Council and Council Committees | Hus University Council formed | Hus Rector & Executive Director |  |  |  |  | Fuel Personnel Stationary Vehicle | 298,000 |
|  | Coordinate holding of a fundraising friendly match between Uganda Cranes & Togo National Team | Fundraising match conducted between | Hus Rector & Executive Director |  |  |  |  | Airtime Fuel Vehicle | 7,171,000 |
|  | Conduct fundraising visits to USA and UK | 5 group | Hus Rector & Executive Director |  |  |  |  | Air ticket Inland travel Per diem | 7,500,000 |
| 2.3 Raise Ugshs 5,400,000 for construction of 6 class rooms,6workshops,offices,staff rooms etc |
|  | Hold a meeting with Country Director of USAID | 1 meeting conducted | Executive Director & HUS Rector |  |  |  |  | - | 174,000 |
|  | Hold a meeting with the Ambassador of China | 1 meeting conducted | Executive Director & HUS Rector |  |  |  |  |  | 174,000 |
| 2.4 Raise UgShs 1,080,000,000 to construct HUS Library (Approx.Covering 1,200m3) and staff quarters ( 3 bedroom self contained house. |
|  | Carry out branding of HUS products | RaiseUgShs 1,080,000,000 to; Construct HUS Library ( Approx.Covering 1,200m3) Construct staff quarters ( 3bedroom self contained house) | HUS Rector |  |  |  |  | T-shirts -Key holders -Pens -Stickers -Flags | 4,750,000 |
|  | Conduct a breakfast meeting with BaggaggaKwagalana Kampala Group |  | HUS Rector |  |  |  |  | Personnel Fuel Stationary Vehicle Venue | 1,828,000 |
| 2.4 Raise UgShs 1,080,000,000 to construct HUS Library (Approx.Covering 1,200m3) and staff quarters ( 3 bedroom self contained house |  |
|  | Hold a meeting with Managing Director of Coca Cola |  | HUS Rector |  |  |  |  | Fuel Airtime Personnel Vehicle | 174,000 |
|  | Hold a meeting with Managing Director of Airtel&Warid | Raise UgShs 1,080,000,000 to; Construct HUS Library ( Approx.Covering 1,200m3) Construct staff quarters ( 3 bedroom self contained house) | HUS Rector |  |  |  |  | Fuel Airtime Stationary Personnel Vehicle | 174,000 |
|  | Hold a meeting with Managing Director of MTN |  | HUS Rector |  |  |  |  | Fuel Airtime Stationary Personnel Vehicle | 174,000 |
|  | Hold a meeting with Managing Director of Roofing |  | HUS Rector |  |  |  |  | Fuel Airtime Stationary Personnel Vehicle | 174,000 |
|  | Hold a meeting with Pastor of Miracle centre Cathedral |  | HUS Rector |  |  |  |  | Fuel Airtime Stationary Personnel Vehicle 174,000 |
| 2.4Raise UgShs 1,080,000,000 to construct HUS Library (Approx.Covering 1,200m3) and staff quarters ( 3 bedroom self contained house |
|  | Hold a meeting with Managing Director of Stanbic Bank-Main Branch |  | HUS Rector |  |  |  |  | Fuel Airtime Stationary Personnel Vehicle | 174,000 |
|  | Hold a meeting with Managing Director of Barclays Bank –Main Branch |  | HUS Rector |  |  |  |  | Fuel Airtime Stationary Personnel Vehicle | 174,000 |
|  | Hold a meeting with Managing Director of Barclays Bank –Main Branch | Raise UgShs 1,080,000,000 to; Construct HUS Library ( Approx.Covering 1,200m3) Construct staff quarters ( 3 bedroom self contained house) | HUS Rector |  |  |  |  | Fuel Airtime Stationary Personnel Vehicle | 174,000 |
|  | Hold a meeting with Managing Director of UCHUMI Garden City &GAME Lugogo |  | HUS Rector |  |  |  |  | Fuel Airtime Stationary Personnel Vehicle | 174,000 |
| 2.5 Raise Ugshs 250,000,000 to;-Construct a dinning hall, Kitchen and a store- Construct a Health Centre- construct a 5 stance drainable VIP latrine. |
|  | Hold a meeting with Managing Director of Standard Charted Bank ( Main) | Raise Ugshs 250,000,000 to; -Construct a dinning hall, Kitchen and a store - Construct a Health Centre - Construct a 5 stance drainable VIP latrine |  |  |  |  |  |  | 174,000 |
|  | Hold a meeting with Managing Director of Equity bank (Main) |  |  |  |  |  |  |  | 174,000 |
|  | Hold a meeting with Managing Director of Catholic Relief- National Secretariat |  |  |  |  |  |  |  | 174,000 |
| 2.5 Raise Ugshs 250,000,000 to construct a dining hall, Kitchen and a store Construct a Health Centre and construct a 5 stance drainable VIP latrine. |
|  | Hold a meeting with Executive Director of Adventist Relief Agency (ADRA) | Raise Ugshs 250,000,000 to; -Construct a dinning hall, Kitchen and a store - Construct a Health Centre - construct a 5 stance drainable VIP latrine | HUS Rector |  |  |  |  | Fuel Airtime Stationary Personnel Vehicle | 174,000 |
|  | Hold a meeting with secretary General of Inter Religious Council of Uganda |  | HUS Rector |  |  |  |  | Fuel Airtime Stationary Personnel Vehicle | 174,000 |
|  | Hold a meeting with Executive Director of Anglican Development Relief Fund |  | HUS Rector |  |  |  |  | Fuel Airtime Stationary Personnel Vehicle | 174,000 |
|  | Hold a meeting with the Ambassador of Australia |  | HUS Rector |  |  |  |  | Fuel Airtime Stationary Personnel Vehicle | 174,000 |
| 2.5 Raise Ugshs 250,000,000 to construct a dining hall, Kitchen and a store Construct a Health Centre and construct a 5 stance drainable VIP latrine. |
|  | Hold a meeting with a Consular of Canada |  | HUS Rector |  |  |  |  | Fuel Airtime Stationary Personnel Vehicle | 174,000 |
|  | Hold a meeting with the Consular of Israel |  | HUS Rector |  |  |  |  | Fuel Stationary Personnel Vehicle | 174,000 |
| 2.6 Raise Ugshs 349,500,000 to furnish classrooms and dormitories |  |  |
|  | Hold meeting with Consular of Norway |  | HUS Rector |  |  |  |  | Fuel Vehicle Personnel | 174,000 |
|  | Hold a meeting with Executive Director of Vivo Energy Uganda |  | HUS Rector |  |  |  |  | Fuel Vehicle Personnel | 174,000 |
|  | Hold a meeting with Executive Director of Total |  | HUS Rector |  |  |  |  | Fuel Stationary Vehicle Personnel | 174,000 |
|  | Hold a meeting with Executive Director of Standard Super Market |  | HUS Rector |  |  |  |  | Fuel Stationary Vehicle Personnel | 174,000 |
| Strategic Objective 3. To promote HIV and AIDS competence working through the faith sector communities. |
|  | Conduct training workshop for community and local level Trainers of Ambassadors of Life and Peace | 90 trained | Executive Director |  |  |  |  | Airtime Fuel Stationary Transport refund refreshments | 7,611,000 |
|  | Facilitate and monitor Ambassadors of Life, Health and Peace in peer – to – peer SSDDIM Reduction and SAVE- Multiplication AIDS Competency. | 40 facilitated | Executive Director |  |  |  |  | Airtime Fuel Stationary Transport refund refreshments | 1,240,000 |
|  | Carry out capacity and competency building workshop of fait leaders to effectively engage in theological dialogue, reflection and critical analysis of HIV &AIDS | 90 trained | Executive Director |  |  |  |  | Airtime Fuel Stationary Transport refund refreshments | 8,511,000 |
|  | Develop, print and distribute SSDDIM Reduction and SAVE- Multiplication IEC Materials | 855 IEC materials produced( T-shirts, Books, Key holders, Calenders | Executive Director |  |  |  |  | Airtime Fuel Stationary Transport refund refreshments | 5,025,000 |
|  | Mobilize religious leaders to mainstream SSDDIM reduction and SAVE multiplication approaches into various religious ceremonies and events. | 500 Religious leaders mobilised | Executive Director Executive Director |  |  |  |  | Airtime Fuel Stationary Transport refund refreshments | 1,410,000 |
|  | Conduct music ,dance and drama festivals among local congregations and schools to disseminate HIV prevention messages and HCT | 12 groups supported | Executive Director |  |  |  |  | Airtime Fuel Stationary Transport refund refreshments | 2,500,000 |
|  | Facilitate youth with sportsequipments to reach out to community members with SSDDIM reduction and SAVE multiplication messages | 10 teams facilitated | Executive Director |  |  |  |  | Airtime Fuel Stationary Transport refund refreshments | 6,145,000 |
|  | Develop and document best practices, success stories and learning regarding SSDDIM reduction and SAVE multiplication interventions | 200 copies produced | M& E Specialist |  |  |  |  | Airtime Fuel Stationary Transport refund Refreshments | 5,025,000 |
| Strategic Objective 4. To Enhance the Institutional Capacity of FOCAGIFO for effective programme Implementation. |
| 4.1 To develop systems, policies &procedures to guide operation of Hope institute & Hope University Semuto. |
|  | Conduct FOCAGIFO/ HUS/HI-TLD Trustees Conference on governance & management | 1 workshop conducted | Executive Director |  |  |  |  | Airtime Fuel Refreshments Transport refund Venue Stationery | 3,500,000 |
|  | Hold Professors-In Residence Forum for HUS Curriculum and Courses Development | HUS Curriculum and Courses Development workshop conducted | Executive Director |  |  |  |  | Airtime Refreshments Stationary Fuel | 25,000,000 |
|  | Conduct a workshop to review FOCAGIFO constitution | 1 Constitution Review workshop conducted | Executive Director |  |  |  |  | Stationary Personnel venue | 1,500,000 |
|  | Formation of New FOCAGIFO Board | 15 new Board members identified | Executive Director |  |  |  |  | Airtime Stationary Fuel Personnel | 500,000 |
|  | Hold a retreat to review FOCAGIFO Strategic Plan 2013/2014-2016/2017. | A Strategic Review workshop conducted | Executive Director |  |  |  |  | Airtime Stationary Refreshments Fuel | 5,815,000 |
| 4.2 To support the Board Governance to effectively carry out their governance role. |
|  | Hold orientation workshop of the new Board | 1 Board orientation workshop conducted | Executive Director |  |  |  |  | Airtime Refreshments Stationary Fuel | 1,500,000 |
|  | Hold Board meetings | 2 Board meetings conducted | Executive Director |  |  |  |  | Airtime Refreshments Stationary Fuel | 3,191,600 |
| 4.2 To support the Board Governance to effectively carry out their governance role. |
|  | Hold Board sub committees | 3 Board sub committees conducted | Executive Director |  |  |  |  | Airtime Refreshments Stationary Fuel | 1,577,600 |
|  | Hold Board & staff retreat | 1 Board and staff retreat conducted | Executive Director |  |  |  |  | Airtime Refreshments Stationary Fuel | 6,070,000 |
|  | Hold Annual General meeting. | Annual General Meeting conducted | Executive Director |  |  |  |  | Airtime Refreshments Stationary Fuel | 4,526,000 |
|  | Hold monthly management meetings | 12 management meetings conducted | Executive Director |  |  |  |  | Airtime Refreshments Stationary Fuel | In- kind |
| 4.3 To enhances the competencies of the staff for effective planning & implementation of FOCAGIFO programs. |
|  | Facilitate staff to attend District, National, workshops and seminars. | 4 staff facilitated | Executive Director |  |  |  |  | Fuel Personnel Funds | 1,800,000 |
| 4.4 .To Carry out Monitoring and Evaluation of Organisation activities. |
|  | Carry out support supervision to OVC graduates | 100 graduates followed up | M&E Department |  |  |  |  | Fuel Stationary Airtime | 857,500 |
|  | Strategic Objective 4. To Enhance the Institutional Capacity of FOCAGIFO for effective programme Implementation. |
|  | 4.4 .To Carry out Monitoring and Evaluation of Organisation activities. |
|  | Hold quarterly caregivers meetings |  |  |  |  |  |  |  | 1,590,000 |
|  | Follow up revolving fund beneficiaries | 50 caretakers followed up | M&E Department |  |  |  |  | Fuel Stationary Airtime | 300,000 |
|  | Conduct Stakeholders ‘review meetings | 4 stakeholders review meetings conducted | M&E Department |  |  |  |  | Fuel Stationary Airtime | 1,500,000 |
|  | Conduct referral and follow up of the child abuse cases | At least 5 Cases will be followed up quarterly |  |  |  |  |  |  | 500,000 |
|  | Document success stories | 30 success stories documented | M&E Department |  |  |  |  | Fuel Stationary Airtime | 1,500,000 |
|  | Conduct follow up to OVC Caretakers’ IGA Initiatives. | 80 caretakers followed up | M&E Department |  |  |  |  | Fuel Stationary Airtime | 280,000 |
|  | Develop of Newsletters | 4 Newsletters developed | M&E Department |  |  |  |  | Fuel Stationary Airtime 600,000 | 600,000 |
|  | Re-design and update of FOCAGIFO website | FOCAGIFO website updated quarterly | M&E Department |  |  |  |  | Fuel Stationary Airtime | 1,100,000 |
| Strategic Objective 4. To Enhance the Institutional Capacity of FOCAGIFO for effective programme Implementation. |
| 4.5 To mobilize resources (in-kind & Financial) for FOCAGIFO Hope Institute& Hope University Semuto. |
|  | Conduct courtesy visits to 30 business entrepreneurs and individuals | 30 business entrepreneurs and individuals visited | Executive Director |  |  |  |  | Fuel Airtime Personnel | 420,000 |
|  | Conduct courtesy visit calls to 30 corporate institutions &companies. | 30 Corporate Institutions visited | Executive Director |  |  |  |  | Fuel Airtime Personnel | 420,000 |
|  | Develop proposals and concept papers | 60 proposals and concept papers developed | Planning Offices |  |  |  |  | Personnel Computer Modem | In -kind |
|  | Establish a Bakery to produce FOCAGIFO Bread | A bakery established | Principal |  |  |  |  | Materials Equipments Personnel | 17,578,000 |
|  | Procure Institute’s vehicle | 1 vehicle procured | Executive Director |  |  |  |  | Funds Personnel | 7,000,000 |
|  | Procure Hope Institute’s computers | 8 computers procured | Principal |  |  |  |  | Funds Fuel Personnel | 9,000,000 |
|  | Programme administration | Utitities | Logistics and Administration |  |  |  |  | Funds Stationary Airtime | 15,780,000 |
|  | Staff allowances | 26 staff members | Accountant |  |  |  |  | Funds | 111,540,000 |

APPENDICES. COMPOSITION OF THE TEAM BEHIND IMPLEMENTATION OF THIS PLAN

Appendix 1: Composition of FOCAGIFO  Board of Trustees 2010-2015

- Rt. Rev Samuel BagaladdeSsekkadde- Chairman

- Hon. Dr MatovuByatike – Vice Chairman

- Ms Harriet sseganneMusoke- Secretary

- Rev Ernest Kibuuka-     Treasurer

- Prof. Eric Edroma- Member

- Haji Mudirikat K Mukasa- Member

- Mr. Gabriel Amori-Member

- Mr. Sam Ocen- Member

- Mr. Paddy Nahabwe-Member

- Rev James Bukomeko- Member

- Haji Mudirikat K Mukasa-Member

- Rev Canon Gideon Byamugisha-Member

- Mr. David Matovu (Advocate –Member

Appendix 2: FOCAGIFO Management Team 2014-2015

- Executive Director / Institute Principal-Mrs Ruth M. Ninsiima

- Project officer/ Academic Registrar-TenywaDifasi

- Dean of students- Herbert Mbalinda

- Librarian- Sandra Nabukalu

- Accountant/ Institute Bursar- JacklineAlanyo

- Human Resource- Juliet Mukunde

- M&E/ Quality Assurance - James Claude Mutyaba

Appendix 3: Heads of Departments 2014-2015

- Fashion & Design- Mrs Esther Semakula

- Motor vehicle Engineering- Mr.Seguya Mathias

- Capentry& Joinery- ArinaitweJoas

- Beauty and Cosmetology- NamataAmina

- Electrical Installation- Kiragga Brian