TITLE OF PROJECT
Educate 800 villagers on COVID-19 in Cameroon

ORGANIZATION PRESENTATION
Community Development Volunteers for Technical Assistance (CDVTA) is a registered development Charity providing basic services for disadvantaged elderly people, children, women, youths and disabled people in poor rural communities in North West Cameroon. CDVTA partners with leading organizations to support these targeted groups. 
Organization Representative: Francis Njakom Nchii

Title: Director, 

Address: CDVTA Head office, 2nd Floor, Imagine Bakery Building, Metta Quarters, Bamenda, P.O.Box 5091, Nkwen Post Office, Bamenda, North West Region, Cameroon. Telephone: +237 678 721 653. E-mail: cdvtaprojects@yahoo.com
Website: http://www.cdvta.org/
PROJECT SUMMARY
CDVTA plans to educate 800 elders, women, disabled and people with frail health conditions on the covid-19 outbreak in Cameroon ensuring that information on this pandemic is accessible to locals in 8 poorest villages. The project will train and support 50 local volunteers to sensitize and educate the population on preventive measures while providing protective gear and hand sanitizers to 800 needy persons. Hand washing facilities will be installed in the villages for Covid-19 prevention

JUSTIFICATION OF THE PROJECT

Cameroon is politically and economically unstable, resulting in increased hardship and people fleeing armed conflicts to unaffected areas. The covid-19 outbreak has caused increased suffering, especially in conflict affected rural villages. As  the 6th most affected African country, given their limited access to good health facilities, the number of affected persons in rural areas could triple among women, elders and people with underlying health conditions due to lack of information on covid-19

Solution

CDVTA will establish a covid-19 response framework in 8 villages by training and supporting 50 volunteers to sensitize and educate 800 vulnerable people on prevention measures. 800 needy people will be supported with facemasks, hand sanitizers and soap, while hand washing facilities will be installed in these villages, close to homes of people with disabilities and elders for Covid-19 prevention. Information to be made accessible in these villages through leaflets and local communication methods
Long Term Impact

The covid-19 response will empower volunteers and vulnerable people to continue to share and practice covid-19 prevention measures with their families and community members who will in turn adopt these preventive measures to protect themselves from the virus. It will prevent conditions of increased suffering among vulnerable people, caused by lack of information on covid-19 and their inability to provide basic subsistence for their families if they contract the virus. 
Donation options 

1. $30 will provide hand sanitizers to 18 persons with disabilities

2. $35 will provide facemasks for 70 poor women

3. $40 will provide hand sanitizers for 24 poor women

4. $50 will provide tablets of hand washing soap to 100 poor women

5. $70 will provide facemasks and tablets of hand washing soap to 70 poor elders

BUDGET FOR ACTIVITIES

	RESULTS/ACTIVITIES
	BUDGETARY LINES (XAF)
	SOURCES OF FUNDING

	
	
	Requested from donors (XAF)
	Beneficiaries’ contribution (XAF)
	Co-funding (CDVTA) (XAF)
	TOTAL (XAF)

	Result 1: 800 villagers (women, people with underlying health problems, people with disability and internally displaced persons) are aware of the methods of preventing Covid-19 and following rules of prevention as prescribed by WHO
	Meeting, Transport/Food/Accommodation
	
	
	
	

	Activity 1.1: Establish a coordination and information management framework for Covid-19 prevention education in 8 villages
	300,000
	250,000
	0
	50,000
	300,000

	Activity 1.2: Organize a 1 day meeting with all actors from 8 villages on coordination and information management framework for Covid-19 prevention education in 8 villages
	500,000
	350,000
	50,000
	100,000
	350,000

	Activity 1.3: Work with village groups like churches, elderly groups, women’s groups, village development associations, traditional rulers, religious leaders, local councils, local volunteers, district health services, media and other development actors to improve communications on COVID-19 prevention measures.
	450,000
	350,000
	50,000
	50,000
	450,000

	Activity 1.4: Organize a 1 day meeting with health services, NGOs in the area, councillors and 8 village quarter representatives to sensitize and educate community leaders to continue awareness raising on COVID-19 prevention measures in the communities
	280,000
	260,000
	20,000
	0
	260,000

	Activity 1.5: Organize 3 Radio Talks on Covid-19 prevention and 3 Newspaper Publications on Covid-19 prevention methods
	600,000
	480,000
	0
	120,000
	480,000

	Result 2: 50 community volunteers have been trained on Covid-19 prevention measures and are using knowledge acquired to educate and sensitize the local population.
	
	
	
	
	

	Activity 2.1: Training, building capacity and assisting of 50 of our community volunteers on the prevention of COVID 19.
	300,000
	220,000
	0
	30,000
	300,000

	Activity 2.2: Providing guidance documents like information leaflets and posters to people in the 8 communities highlighting COVID-19 prevention messages
	2,000,000
	1,700,000
	0
	300,000
	2,000,000

	Activity 2.3
	
	
	
	
	

	Result 3: 800 vulnerable people (the elderly, PWD, PLHIV, women and people who are chronically ill are supported with preventive gear such as washing soap, face masks, gloves, water containers and hand sanitizers and are using these items to prevent the spread of the Covid-19 virus. 
	
	
	
	
	

	Activity 3.1: Supporting vulnerable populations in 8 villages with preventive gear such as washing soap, face masks, gloves, water containers, hand sanitizers etc which are not available in the rural communities to help combat the Covid-19 virus spread
	1,790,000
	1,626,000
	0
	164,000
	1,790,000

	Activity 3.2: Installing hand washing facilities with soap and hand sanitizers in 8 rural communities and closer to homes of people with disability, elderly and people with serious health conditions.
	159,000
	120,000
	39,000
	120,000
	159,000

	Visibility/Communication/Knowledge management
	570,000
	470,000
	0
	100,000
	570,000

	Monitoring and Evaluation by 4 staff


	3,000,000
	2,250,000
	0
	750,000
	3,000,000

	Institutional Support 
	
	
	
	1,705,000
	1,705,000

	TOTAL  RQUESTED FROM GLOBAL GIVING  IS             $13,877 USD
	13,877 USD
	13,877 USD
	482 USD
	2,842 USD
	13,877 USD
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CDVTA care worker shares lessons with rural women on social distancing to curb the spread of covid-19
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Water is essential for good health and curbing the spread of covid-19 in rural communities through the regular washing of hands with soap
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CDVTA has provided many village children and their families in North West Cameroon access to clean drinking water through improvement of village water sources.
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Women and children are primary users of water in remote rural communities.
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Children and families accessing clean water supply close to their homes Chuaku village, North West Cameroon thanks to CDVTA and international partners.
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Elderly women are vulnerable to covid-19
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Women are front-liners in the fight against covid-19
