**Atzin Desarrollo Comunitario, A.C. 29 June, 2020**

**Atzinmexico97@gmail.com**

**Summary "Atzin: Response to covid19 in Tlamacazapa Phase 1”**

To respond to the covid19 situation in Guerrero and assist in public education, Atzin organized a campaign, “Prevention of covid19 in rural Guerrero,” that started on March 14, 2020.

Phase 1 of the campaign had three areas of focus: community education; family support; and production of cloth masks and hand sanitizer. All planned activities are now completed or are in continuation (distribution of food, for example).

Main outputs over three months include:

1. Week training of promoters on covid-related topics, organization of activities; practice sessions on distributions process, recordkeeping and conversations with family members. Total of 24 supervisory/ organizational/ training days in Tlamacazapa by office staff between March 14-June 25th.
2. Production of six flyers and information sheets related to covid19 (prevention; care and use of face masks; making hand sanitizer; correct handwashing; care of patients at home; monitoring symptoms).
3. Completion of two rounds of visits to households, street by street, in order to explain prevention measures of covid; correct handwashing; and, care of patients at home.
4. Completion of five distributions of food packages to selected families between 27th April to 11 June, increasing from 400 to 620 families by the fifth distribution.
5. Production of 4,241 face masks made of double cloth in the sewing workshop as of June 15th, with distribution of 3,400 to all family members receiving food packages; 573 sold (at cost in TLA; with small markup to others); and 97 included as part of information packages delivered.
6. Delivery of 22 information packages to different institutions, government departments and women’s groups in Guerrero. In Chilpancingo, a total of 14 packages: 4 state government departments (Social Welfare; Ministry of Women; Guerrero State Human Rights Commission; Senator Nestora) plus 9 women’s groups located in Chilpancingo and La Montana, and human rights lawyer, Luis Jeronimo. In Taxco, total of 8 packages to different government departments.

**Additional activities added to campaign:**

1. Initiation and maintenance of a death registry for Tlamacazapa from April 26 to present, starting mid-May. Data shared with Taxco municipality and village *Comisario* weekly since early June.
2. Initiation and continuation of condolence visits to families with a death of family member, with gift of food package, 200 pesos and confirmation of symptoms of patient.
3. Initiation and maintenance of locations on a street map of households with a villager death since April 26th.
4. Preparation of letter and summary death data, sent to Municipal President on June 10th, copies to different directors, with expression of concern, petitions for 3 distributions of food packages for 850 families and tanks/kitchen gardens for 50 families construction project for youth. Meeting June 18 with directors in Taxco, attended by SS, XR and 4 promoters. In follow-up of verbal agreements, two short proposals submitted week of June 22nd, with no response to date.
5. Promotion: initiation of short 3-4-minute promotional video regarding covid in TLA, with Rodrigo Cruz. Pending.