Report on the project to provide educational services to displaced children in Yemen.

October 2025 AD

Report prepared by: Shaif Ezz El-Din

Project data

| Project name | Project to provide educational services to displaced children in Yemen. |  |  |
| --- | --- | --- | --- |
| Project location | Yemen |  |  |
| Name of the organization applying for the scholarship | Sand Organization for Relief and Development ( SORD ) |  |  |
| Report duration | My quarter |  |  |
| Start date | July 2025 | Expiration date | October 2025 |
| Organization address | Capital Secretariat - Shu'ub District - Al Habari |  |  |
| Phone number | 0096701205757 |  |  |
| Report prepared by | I see Ezz El-Din |  |  |
| Current job | project manager |  |  |
| e-mail | Programs.officer@sanid.org |  |  |
| Mobile number | 00967 775907606 |  |  |
| The organization's website | www.sanid.org |  |  |

Overview of the tragic situation of children in Yemen

The project aims to help the targeted students realize their most important rights and provide them with hope and a future, amid the bleak conditions facing Yemeni children and displaced persons, affecting their education and nutrition, which constitutes the largest humanitarian crisis in the world. Furthermore, it will provide work for mothers and sisters of displaced children without a breadwinner, contributing to bridging the large and dangerous gap in education .

The project aims to increase access to safe and healthy basic education services for displaced male and female school-age students who are not enrolled, and to strengthen the capacity of teachers and parent councils in sites hosting displaced persons over a period of one academic year. The areas and schools were selected in cooperation and coordination with the Executive Unit, partners, the Education Cluster of the Office for the Coordination of Humanitarian Affairs, and local authorities .

The project's outcomes will include 500 male and female students receiving essential educational and nutritional supplies during class hours, in addition to 100 male and female volunteer teachers receiving the necessary cash incentives to support the educational process in temporary schools in the governorate's displacement hosting sites .

The project will be implemented in integration and coordination with other activities targeted by the organization to protect children, which aim to help 1,500 to 3,000 children, and in coordination and cooperation with the Education Cluster partners in the governorates .

The overall goal of the project is to contribute to the realization of the most important rights of displaced male and female students in Yemen, particularly with regard to education and nutrition. By providing access to safe and healthy basic education services, the project aims to open up opportunities and hope for the future for these vulnerable children. Additionally, the project seeks to address the humanitarian crisis in Yemen by bridging the education gap and providing employment opportunities for mothers and sisters of displaced children. Through these efforts, the project aims to empower communities, enhance educational capacities, and improve the overall well-being of displaced individuals in the region.

: Activities implemented

- Follow-up of 400 male and female students benefiting from educational services for displaced children who have been returned to education

- 50 students were targeted with morning meals at their schools for a month.

- Conducting 20 counseling sessions with 40 male and female students, with the help of a social worker, to discuss the students' problems, identify their causes, address them, and follow up with them according to their needs and psychological and social circumstances.

- 15 male and female students received medical care immediately after contracting severe diarrhea (cholera) and other diseases, with 8 of them being referred to isolation centers designated by the competent authorities.

- Two sessions were held during the period with the Education Office and relevant authorities to discuss the situation of the targeted children, review their educational, social, psychological and living reports, and follow up on the implementation of the plan agreed upon with the educational authorities.

- Three meetings were held with the Parents ' Council in the targeted areas to discuss the needs of the targeted children and find solutions to their problems.

- Continuing awareness campaigns in the targeted areas to highlight the importance of education and the benefits of the project. (Target audience: parents, caregivers, community leaders) from during SORD team .

Obstacles: The large number of students who are eligible for assistance and who are not included in this project.

Lack of support, donations and capabilities to target the largest possible number of those entitled to educational services through this project, as the targeted number of activities has been reduced from what it was previously due to the lack of financial capabilities, scarcity of resources and small donations.

Recommendations: The need to intensify efforts and provide sufficient support to cover the largest possible number of children included in the project.

Finally, we extend our sincere thanks to all supporters and donors who extend a helping hand to the Yemeni people to protect their children from slipping into the clutches of terrorism and extremism and to make them a righteous generation who, like others, enjoy the rights they have been deprived of.