## ورقة1
Year | first ( 1.1.2021-1.1.2022)
Months | January | February | March | April | May | June | July | August | September | october | Novemer | December | NOTE | EXTNOTE
Activities
provision overall needs; equipments, materials, raws for each program; physiotherapy, occupational, speech therapy sesssions and , training, and learning difficulties | bar: first ( 1.1.2021-1.1.2022) January; first ( 1.1.2021-1.1.2022) July
start implemintation learning difficulties activities of all (four groups) | [12 empty] | Saturday-Thursday | bar: first ( 1.1.2021-1.1.2022) January to first ( 1.1.2021-1.1.2022) December
medical day with medical doctore | bar: first ( 1.1.2021-1.1.2022) February; first ( 1.1.2021-1.1.2022) April; first ( 1.1.2021-1.1.2022) June; first ( 1.1.2021-1.1.2022) August; first ( 1.1.2021-1.1.2022) october; first ( 1.1.2021-1.1.2022) December
community rehabilitation ( mental health program ) | [12 empty] | Saturday,Thursday | bar: first ( 1.1.2021-1.1.2022) January to first ( 1.1.2021-1.1.2022) December
training courses for new benificiearies | bar: first ( 1.1.2021-1.1.2022) March; first ( 1.1.2021-1.1.2022) June; first ( 1.1.2021-1.1.2022) September; first ( 1.1.2021-1.1.2022) December
ostupathy program withRose | [12 empty] | Wednesday, Saturday | bar: first ( 1.1.2021-1.1.2022) January to first ( 1.1.2021-1.1.2022) December
physiotherapy home visits | [12 empty] | twice a week | bar: first ( 1.1.2021-1.1.2022) January to first ( 1.1.2021-1.1.2022) December
physiotherapy program | [12 empty] | Sunday-Thursday | bar: first ( 1.1.2021-1.1.2022) January to first ( 1.1.2021-1.1.2022) December
occupational program | [12 empty] | Sunday-Thursday | bar: first ( 1.1.2021-1.1.2022) January to first ( 1.1.2021-1.1.2022) December
speech program | [12 empty] | Sunday-Thursday | bar: first ( 1.1.2021-1.1.2022) January to first ( 1.1.2021-1.1.2022) December
physio training for mothers | [12 empty] | Saturdays | bar: first ( 1.1.2021-1.1.2022) March; first ( 1.1.2021-1.1.2022) June; first ( 1.1.2021-1.1.2022) September; first ( 1.1.2021-1.1.2022) December
occupational training
special needs traning | bar: first ( 1.1.2021-1.1.2022) January to first ( 1.1.2021-1.1.2022) April
social worker traning
speech training
sharing awareness conferenses | [12 empty] | Saturdays | bar: first ( 1.1.2021-1.1.2022) May; first ( 1.1.2021-1.1.2022) September
reports every (3 months) | bar: first ( 1.1.2021-1.1.2022) March; first ( 1.1.2021-1.1.2022) June; first ( 1.1.2021-1.1.2022) September; first ( 1.1.2021-1.1.2022) December
training courses for staff | bar: first ( 1.1.2021-1.1.2022) April; first ( 1.1.2021-1.1.2022) August