MORE TREES PROJECT.

In recent months we have worked on the restoration of degraded lands and eradication of poverty

The design is aimed at more than 4000 families and 1900 hectares annually for approximately 7 continuous years. The provinces selected for their location are Paruro with 4 districts, Huanoquite, Omacha, Accha and Ccapi. And the province of Chumbivilcas in the district of Ccapacmarca.

Dear Donors,

We continue to affirm that the future of the planet is in the hands of family farmers.

Our main Target of the MORE TREES project is to restore 13,300 hectares and establish 1,330 hectares in conservation.

This project offers environmental, economic and social benefits in rural communities.

The analysis of the degraded ecosystem requires a lot of research and action. The assessment strategy we have implemented comprises the following steps:

- Mapping and identification of the degraded area in the communities.

- Diagnosis and selection of the Pachamama Raymi Methodology.

- Identification of the reference ecosystem

- Consultation with local actors

The project is aligned with ten of the sustainable development objectives

MAIN OBJECTIVE:

Achieve the prosperity of peasant families and the recovery of natural resources, through the establishment of forest plantations, which generate goods and ecosystem services in favor of peasant families and communities.

The project began in February 2023, we have managed to recover 1,365 hestareas in the first Forestry campaign, we are currently in our second Campaign (2024 - 2025), with a lot of effort together with the protagonists of the project, which are the peasant communities, the local government and Pachamama Raymi have exceeded our expectations by managing to plant more than 2,200 hectares.

We have managed to establish 627 hectares of conservation

Our next steps:

- Finalize our 2024 forestry campaign.

- Certify planting areas.

Generate economic income for communities in poverty and extreme poverty through the sale of carbon credits

We are grateful to be in a situation that allows us to continue to serve our community during this crisis.

We hope to continue to count on your generosity and continue to sow prosperity!

Help us with your donation to Planting Prosperity!

BLESSINGS, TEAM PACHAMAMA RAYMI

Calle Pavitos 567 Interior, Cusco – Perú.

Telf. +51-84-236540, www.pachamamaraymi.org