تقرير مشروع تمكين وحماية النساء والفتيات المتضررات من الحرب في اليمن

ابريل 2026

| اسم المشروع | تمكين وحماية النساء والفتيات المتضررات من الحرب في اليمن |  |  |
| --- | --- | --- | --- |
| موقع المشروع | اليمن |  |  |
| اسم المنظمة المتقدمة للمنحة | منظمة ساند للإغاثة والتنمية |  |  |
| مدة التقرير |  |  |  |
| تاريخ البدء | فبراير 2026م |  | ابريل 2026م |
| عنوان المنظمة | أمانة العاصمة ــ مديرية شعوب ــ الحباري |  |  |
| رقم التلفون | 0096701205757 |  |  |
| معد التقرير | شايف عزالدين |  |  |
| الوظيفة الحالية | مدير المشروع |  |  |
| البريد الالكتروني | Programs.officer@sanid.org |  |  |
| رقم الموبايل | 00967 778515109 |  |  |
| موقع المنظمة على الويب | www.sanid.org |  |  |

مقدمة:

تعتبر النساء والفتيات في اليمن من الفئات الأكثر تضرراً من الصراع الدائر، حيث يتعرضن للعنف القائم على النوع الاجتماعي، والنزوح، والحرمان من الخدمات الأساسية. يهدف هذا المشروع إلى تقديم الدعم الحماية والتمكين للنساء والفتيات المتضررات من الحرب في اليمن، وذلك من خلال مجموعة من الأنشطة والبرامج التي تستهدف تعزيز قدرتهن على الصمود والمشاركة في عملية إعادة البناء.

الأهداف:

المساهمة في خلق بيئة مستدامة ومرنة للنساء والفتيات في اليمن. ومن خلال تزويدهم بالأدوات والموارد اللازمة للاعتماد على أنفسهم، يهدف المشروع إلى تمكينهم من السيطرة على حياتهم ويصبحوا عوامل تغيير في مجتمعاتهم. وهذا لن يساعدهم فقط في التغلب على التحديات التي يواجهونها يوميًا، بل سيمكنهم أيضًا من المساهمة في تنمية بلدهم. ويهدف المشروع أيضًا إلى رفع مستوى الوعي حول أهمية حماية النساء والفتيات من جميع أشكال العنف، بما في ذلك الاستغلال والاعتداء الجنسي، وتعزيز المساواة بين الجنسين وتمكين المرأة في اليمن.).

الحد من معدلات العنف بكافة أشكاله المرتكب ضد النساء والفتيات وخاصة الأشخاص الأكثر ضعفاً والمتضررين من النزاع، مع التركيز على تعزيز الاعتماد على الذات، وحماية النساء والفتيات من العنف، وتمكينهن ليكونن عوامل تغيير، إلى إحداث تغيير كبير في حياتهن. ومن خلال تزويدهم بفرص كسب العيش وتدخلات الحماية، لا يعالج المشروع احتياجاتهم الفورية فحسب، بل يمكّنهم أيضًا من المساهمة في مجتمعاتهم والمجتمع الأكبر. في المناطق (صنعاء- اب -عدن- وتعز- وشبوة - ومارب..)

يهدف مشروع "تمكين وحماية النساء والفتيات المتضررات من الحرب في اليمن مع حمايتهن من الاستغلال والاعتداء الجنسي" إلى تعزيز الاعتماد على الذات للنساء النازحات والمعرضات للخطر في المناطق المتضررة من النزاع من خلال تدخلات سبل العيش والحماية. يدعم المشروع وصول المرأة إلى سبل العيش والحماية من جميع أشكال العنف، بما في ذلك

- الهدف العام تحسين أوضاع النساء والفتيات المتضررات من الحرب في اليمن من خلال توفير الحماية والخدمات الأساسية وتمكينهن اقتصادياً واجتماعياً.

الاستغلال والاعتداء الجنسي، مع تمكينها لتكون عوامل التغيير وصانعي القرار في سياق الأزمة الحالية.. سيحتوي المشروع على المكون التالي:

الخدمات ذات الصلة المباشرة بالحماية (الاستشارات القانونية وأنشطة مراقبة الحماية وبناء القدرات بما في ذلك التثقيف الرئيسي في مجال الراحة والتوعية بمخاطر الألغام والإحالة بالإضافة إلى نظام إدارة الحالات للعنف القائم على النوع الاجتماعي)

- تعزيز الوصول إلى سبل العيش: تزويد النساء النازحات والضعيفات بالتدريب على المهارات والأنشطة المدرة للدخل وفرص التمويل الصغير لدعم أنفسهن وأسرهن.

- تعزيز آليات الحماية: تنفيذ التدخلات لمنع جميع أشكال العنف القائم على النوع الاجتماعي والاستجابة لها، بما في ذلك الاستغلال والاعتداء الجنسي (SEA) . ويشمل ذلك إنشاء مساحات آمنة، والمساعدة القانونية، وخدمات الدعم النفسي والاجتماعي.

تمكين المرأة كعوامل للتغيير: تزويد المرأة بالمعرفة والمهارات والثقة للمشاركة في عمليات صنع القرار على جميع المستويات، بما في ذلك في سياق الاستجابة الإنسانية وجهود بناء السلام.

المستفيدون

- النساء والفتيات المتضررات من الحرب في اليمن، بتركيز خاص على الأسر النازحة والفقيرة.

| - عقد جلسات توعية بأهمية حماية المرأة وحقوقها. لعدد 6 جلسة استفاد منها 32 امرأة وفتاة. - عقد جلسات دعم نفسي جماعي عن طريق مختصين نفسيين (إناث) 5 جلسة استفاد منها 26 امرأة وفتاة. - عقد جلسات دعم نفسي فردي من قبل مختصات. لعدد 12 جلسات استفاد منها 12 حالات. - تم تقديم الاستشارات القانونية والمساعدات المادية والاحالات إلى مقدمي الخدمة لعدد 7 حالة GBV. تحتفظ المنظمة بوثائقهن بطريقة سرية حيث تحكي الوثائق جملة من الانتهاكات التي تعرضن لهن والعنف الذي أصابهن خلال الفترة الماضية. - الاستمرار في التدريب لتعلم الخياطة لعدد 15 امرأة وفتاة . | الإنجازات |
| --- | --- |
| - شحة الإمكانات: - الظروف الصعبة التي تعيشها النساء والفتيات المستفيدات في جلسات الحماية وصعوبة مساعدتهن ماديا أو بسلات غذائية على الأقل. - عدم توفر الحماية القانونية لبعض الحالات التي تعاني من تعرض للعنف | التحديات / الصعوبات |
| - استمرار الدعم لهذا المشروع - توفير مساعدات غذائية للنساء والفتيات المستحقات للحماية - توفير مستشار قانوني للوقوف على بعض القضايا | مقترحات |

تقرير إنجاز المشروع: تمكين وحماية النساء والفتيات المتضررات من الحرب

فترة التقرير: فبراير – أبريل 2026

1. بطاقة تعريف المشروع (Project Profile)

- اسم المشروع: تمكين وحماية النساء والفتيات المتضررات من الحرب في اليمن.

- الجهة المنفذة: منظمة ساند للإغاثة والتنمية (SORD).

- النطاق الجغرافي: الجمهورية اليمنية.

- المستهدفون: النساء والفتيات المتضررات من النزاع (خاصة النازحات والأسر الأشد فقراً).

- مسؤول التقرير: شايف عزالدين (مدير المشروع).

2. السياق والمقدمة (Introduction & Context)

تعد النساء والفتيات في اليمن الفئة الأكثر عرضة لتبعات الصراع، حيث يواجهن مخاطر متزايدة تتعلق بالعنف القائم على النوع الاجتماعي (GBV)، والنزوح القسري، وفقدان سبل العيش. يهدف هذا التدخل إلى تعزيز مرونة هذه الفئات وقدرتها على الصمود والمشاركة الفاعلة في إعادة بناء المجتمع.

3. الأهداف الاستراتيجية (Strategic Objectives)

- التمكين الاقتصادي: تزويد النساء بالمهارات المدرة للدخل وتسهيل وصولهن للتمويل الأصغر.

- تعزيز آليات الحماية: الاستجابة الفورية ومنع كافة أشكال العنف، بما في ذلك الاستغلال والاعتداء الجنسي (SEA).

- الدعم النوعي: توفير المساحات الآمنة، والمساعدة القانونية، وخدمات الصحة النفسية.

- المناصرة والقيادة: بناء ثقة النساء للمشاركة في اتخاذ القرار وجهود بناء السلام.

4. مصفوفة الإنجازات المحققة (Key Achievements - Q1 2026)

| النشاط المنفذ | عدد الجلسات | عدد المستفيدات | المخرجات الرئيسية |
| --- | --- | --- | --- |
| التوعية الحقوقية | 6 جلسات | 32 امرأة وفتاة | رفع الوعي بأهمية حماية المرأة وحقوقها القانونية. |
| الدعم النفسي الجماعي | 5 جلسات | 26 امرأة وفتاة | تعزيز الصحة النفسية الجماعية عبر مختصات مؤهلات. |
| الدعم النفسي الفردي | 12 جلسة | 12 حالة | تقديم رعاية نفسية مكثفة وسرية للحالات الأكثر تضرراً. |
| الحماية القانونية والمادية | - | 7 حالات (GBV) | تقديم استشارات قانونية، مساعدات مالية، وإحالات آمنة. |

5. المنهجية والمعايير المهنية (Methodology & Standards)

- السرية والأمان: تلتزم المنظمة بأقصى درجات السرية في أرشفة وثائق الناجيات من العنف، مع ضمان خصوصية القصص والانتهاكات المرصودة.

- الحماية من الاستغلال والاعتداء الجنسي (PSEA): يتم تطبيق بروتوكولات صارمة لضمان بيئة عمل آمنة لجميع المستفيدات والكادر الوظيفي.

- نظام الإحالة: تفعيل قنوات إحالة فعالة لمقدمي الخدمات الطبية والقانونية المتخصصين.

6. معلومات التواصل الرسمي (Contact Information)

- المقر الرئيسي: صنعاء – مديرية شعوب – الحصبة – شارع الجمهورية – جولة الحباري.

- الهاتف: 01205757 00967.

- البريد الإلكتروني: Programs.officer@sanid.org.

- الموقع الإلكتروني: www.sanid.org.

Project Performance Report

Project Title: Empowerment and Protection of Women and Girls Affected by War in Yemen

Reporting Period: February – April 2026

1. Project Profile

- Implementing Organization: Sanid Organization for Relief and Development (SORD)

- Location: Yemen

- Report Preparer: Shaif Ezzeddine (Project Manager)

- Contact Information: Programs.officer@sanid.org | +967 01205757

- Website: www.sanid.org

2. Introduction & Context

Women and girls in Yemen are among the groups most severely affected by the ongoing conflict, facing heightened risks of Gender-Based Violence (GBV), displacement, and deprivation of basic services. This project aims to provide essential protection, support, and empowerment to affected women and girls through a comprehensive range of activities designed to enhance their resilience and enable their participation in the recovery and peacebuilding process.

3. Strategic Objectives

- Socio-Economic Empowerment: Equipping vulnerable women and girls with vocational training, income-generating skills, and micro-financing opportunities to achieve self-reliance.

- Strengthening Protection Mechanisms: Implementing interventions to prevent and respond to all forms of GBV, including Prevention of Sexual Exploitation and Abuse (PSEA). This includes establishing Safe Spaces, providing legal aid, and professional psychosocial support.

- Women as Agents of Change: Providing women with the knowledge, skills, and confidence to participate in decision-making processes at all levels, including humanitarian response and peacebuilding.

4. Key Achievements Matrix (Feb – Apr 2026)

| Activity | Sessions | Beneficiaries | Key Outcomes |
| --- | --- | --- | --- |
| Legal & Rights Awareness | 6 | 32 Women/Girls | Enhanced awareness of legal rights and protection pathways. |
| Group Psychosocial Support (PSS) | 5 | 26 Women/Girls | Peer-support healing facilitated by female specialists. |
| Individual Counseling | 12 | 12 Cases | Confidential, specialized mental health interventions. |
| Legal Aid & Case Management | — | 7 Cases | Provision of legal counsel, financial aid, and safe referrals. |

5. Protection Standards & Confidentiality

SORD strictly adheres to the "Do No Harm" principle and international protection standards. All sensitive data regarding GBV survivors is archived with the highest level of confidentiality. Our records reflect the complex patterns of violence and violations encountered by women during this period, which are addressed through integrated and secure response pathways.

6. Institutional Contact Information

- Headquarters: Al-Habari, Shu'ub District, Sana'a, Yemen.

- Phone: 00967 01205757

- Email: info@sanid.org | Programs.officer@sanid.org

# 📑 April 2026 Quarterly Project Performance Report

Project Title: Empowerment and Protection of Women and Girls Affected by War in Yemen Reporting Period: February – April 2026

## 1. Project Profile

- Implementing Organization: Sanid Organization for Relief and Development (SORD)

- Location: Yemen

- Report Preparer: Shaif Ezzeddine (Project Manager)

- Contact Information: Programs.officer@sanid.org | +967 01205757

- Website: www.sanid.org

## 2. Introduction & Context

Women and girls in Yemen continue to face heightened risks of GBV, displacement, and deprivation of basic services due to the ongoing conflict. This project delivers protection, empowerment, and resilience-building interventions to enable their participation in recovery and peacebuilding.

## 3. Strategic Objectives

- Socio-Economic Empowerment

  - Vocational training, income-generating skills, micro-financing.

  - Outcome: Increased self-reliance.

- Strengthening Protection Mechanisms

  - GBV prevention and response, including PSEA.

  - Safe Spaces, legal aid, psychosocial support.

- Women as Agents of Change

  - Knowledge, skills, and confidence for decision-making.

  - Participation in humanitarian response and peacebuilding.

## 4. Key Achievements (Feb – Apr 2026)

| Activity | Sessions | Beneficiaries | Key Outcomes |
| --- | --- | --- | --- |
| Legal & Rights Awareness | 6 | 32 Women/Girls | Awareness of legal rights and protection pathways |
| Group Psychosocial Support (PSS) | 5 | 26 Women/Girls | Peer-support healing facilitated by female specialists |
| Individual Counseling | 12 | 12 Cases | Confidential, specialized mental health interventions |
| Legal Aid & Case Management | — | 7 Cases | Legal counsel, financial aid, safe referrals |

## 5. Challenges & Lessons Learned

- Challenges:

  - Security constraints limiting outreach.

  - Stigma surrounding GBV reporting.

  - Limited resources for scaling interventions.

- Lessons Learned:

  - Community-based safe spaces increase trust.

  - Peer-support groups accelerate psychosocial recovery.

  - Legal aid partnerships strengthen survivor protection.

## 6. Protection Standards & Confidentiality

- Strict adherence to “Do No Harm” principle.

- Compliance with international protection standards.

- Sensitive GBV survivor data archived with confidentiality.

- Integrated response pathways to address complex violence patterns.

## 7. Institutional Contact Information

- Headquarters: Al-Habari, Shu'ub District, Sana'a, Yemen

- Phone: 00967 01205757

- Email: info@sanid.org | Programs.officer@sanid.org

# 📊 Project Performance Report

Project Title: Empowerment and Protection of Women and Girls Affected by War in Yemen Reporting Period: February – April 2026

## 1. Project Profile

- Implementing Organization: Sanid Organization for Relief and Development (SORD)

- Location: Yemen

- Report Preparer: Shaif Ezzeddine (Project Manager)

- Contact Information: Programs.officer@sanid.org | +967 01205757

- Website: www.sanid.org

## 2. Introduction & Context

Women and girls in Yemen remain among the most severely affected groups in the ongoing conflict. They face heightened risks of Gender-Based Violence (GBV), displacement, and deprivation of basic services. This project provides protection, support, and empowerment through activities designed to enhance resilience and enable participation in recovery and peacebuilding.

## 3. Strategic Objectives

- Socio-Economic Empowerment

  - Vocational training, income-generating skills, micro-financing opportunities.

  - Goal: Achieve self-reliance.

- Strengthening Protection Mechanisms

  - GBV prevention and response, including PSEA.

  - Safe Spaces, legal aid, psychosocial support.

- Women as Agents of Change

  - Knowledge, skills, and confidence for decision-making.

  - Participation in humanitarian response and peacebuilding.

## 4. Key Achievements Matrix (Feb – Apr 2026)

| Activity | Sessions | Beneficiaries | Key Outcomes |
| --- | --- | --- | --- |
| Legal & Rights Awareness | 6 | 32 Women/Girls | Enhanced awareness of legal rights and protection pathways |
| Group Psychosocial Support (PSS) | 5 | 26 Women/Girls | Peer-support healing facilitated by female specialists |
| Individual Counseling | 12 | 12 Cases | Confidential, specialized mental health interventions |
| Legal Aid & Case Management | — | 7 Cases | Provision of legal counsel, financial aid, and safe referrals |

## 5. Protection Standards & Confidentiality

- Adherence to “Do No Harm” principle.

- Compliance with international protection standards.

- Sensitive GBV survivor data archived with strict confidentiality.

- Integrated response pathways to address complex patterns of violence.

## 6. Institutional Contact Information

- Headquarters: Al-Habari, Shu'ub District, Sana'a, Yemen

- Phone: 00967 01205757

- Email: info@sanid.org | Programs.officer@sanid.org