Title of project:  	IMPROVING AIR QUALITY IN PUBLIC SCHOOLS THROUGH FOREST RESTORATION AND TREE MANAGEMENT

Organisation name: 			Nigerian Conservation Foundation (NCF)

Principal investigator:		NCF Technical Programmes Department (TPD)

Organisation address:		Km 19, Lekki-Epe Express Way, Victoria Island, Lagos

Project location: 			Nigeria

Project duration: 			3 years

Total Project Budget:		40,700 million Naira

Total To Be Crowd Funded: 	20 million Naira

Start Date:			 	January 2022

Project Category:		 	Space – Green Recovery Nigeria (GRN)

Challenge

Most school environment are bare and void of trees. This has led to hot, noisy, and polluted environment making school children to be more restless, prone to ill health, and generally low performance in their studies.  Children with attention deficit disorder have been more affected as trees or green spaces which will boost their immunities are not available.

Rationale

Multiple evidence from scientific studies opines that exposure to trees or green space can improve human health. Trees play important roles in maintaining a virile and sustainable environment. Trees provide the means of paying “carbon debt”,  by absorbing carbon IV oxide (CO2) and giving out oxygen. Adebayo and Owolabi (2004) reported that destruction of green space for human use will create an environment with more carbon IV oxide circulating in the air causing havoc. This havoc can be seen as more heat are trapped within the atmosphere which contributes immensely to global warming and climate change making the learning environment most times uncomfortable and more school children having respiratory tract diseases.

Trees/greenspace are indicators of a community’s ecological health. When trees are large and healthy, the ecological systems – soil, air, and water – that support them are also healthy. In turn, healthy trees provide valuable environmental benefits. The greater the tree cover, the less the impervious surface, the more ecosystem services are produced in terms of reducing storm water runoff, increasing air and water quality, storing, and sequestering atmospheric carbon and reducing energy consumption due to direct shading of residential buildings.

Without trees, the world would be bleak, and life as it is known would be impossible. Man is already acquainted with the vast importance of trees to his survival. Primitive people were dependent on trees for food. Fossilized products of trees like coal (carbonized and fossilized wood) supply fuel for the energy needs of man. Modern man is no less dependent upon trees, particularly the soaring demand for tree products in the many sectors.

Trees also serve as screens to secure privacy, to reduce noise and they provide shade, unfortunately, little or no value or priority has been placed on tree planting in Nigeria as a whole.  According to Ojeh et. al (2019), trees serve as wind breaks, however, only few stands or non are currently standing in Nigerian schools as the environment is characterized by a lot of open space which make windstorms one of the disasters that destroy classrooms or other buildings within schools.

Long term Impact

The planting of trees or creation of green space in schools will create a pure air for generations of students. Abilities such as reading, learning and creative thinking will gradually return to the education system. Shaded areas will be available. Outdoor learning would be fun for the growing students. Health related issues will be minimized.

Trees only need care in their first few years. They ecological services is worth more than the care in years to come. Depending on the type of trees, availability of trees in school might be source of food for hungry children who may not be able to confide in their teachers or other students.

Funders of tree planting project can always visit the school for monitoring and the information on how their support has been useful and can be evaluated now and in the future.

Description/ Activities

The proposed improving air quality in public schools through forest restoration and tree management in Nigeria represent the continuation of the NCF Green Recovery Nigeria (GRN) initiative. Driven by the global climate change action and the desire to enhance quality of life in public schools with pure air for indigent students.  The tree-planting process will begin with research on the nature of the school environment to create a database on the topography of the selected schools, building damage by wind and student creativity/ health gap. This research will be carried out by selected volunteers possibly from the National Youth Service Corps.

The selected plant might be mostly fruit plant to help provide multiple service within the school. Trees will be planted and nurtured by the students (especially members of the created  NCF conservation club) and teachers. For proper sustainability, stipend will be given in the early years of tree planting. Schools with conservation clubs will be given preference during selection.

Activities

| Activities |  | Duration per year (This will be duplicated for 3years ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Key performance indicator |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | J | F |  | M |  | A |  | M |  |  | J | JL |  |  | A |  | S | O |  | N |  | D |  |
| School topography investigation | Sourcing for schools through existing database from ministry of education |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Evidence of database from ministry of education |
|  | Visiting selected schools to using google earth to check the topography |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A short description of school landscape |
|  | Selection of one out of every ten schools. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | List of schools selected |
| Tree Selection | Stakeholders meeting with Forestry research institute, state ministry of environment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Pictures showing meeting |
|  | Selection of desired trees |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | List and pictures of selected trees |
|  | Purchase/Delivery of trees to schools |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Pictures of number of schools with trees |
| Creation of conservation club | Selection of volunteers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Initial number applying volunteers and bases for selection of the current number |
|  | Training and distribution volunteers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Names and location of where selected volunteers will work |
|  | Establishment of conservation club in schools |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Number of conservation clubs created |
| Training of selected schools | Training of selected schools’ teachers and students |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Number of teachers trained in each of the selected schools |
| Distribution of tools and safety equipment | Distribution of tools and safety equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Written report evidence of tools and equipment distributed to schools |
| Tree planting exercise | Tree planting exercise |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Number of trees planted in selected schools |
| Media activities | Publicising the activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Social media, local print and virtual media |
| Monitoring and evaluation | Monitoring and evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Evaluation Report |
| Reporting | Writing of technical and financial report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Availability of technical and financial report. |

Partners

The project will be partnering with the following institution:

- State ministry of education

- Forestry research institute

- NYSC

- State ministry of environment

- Lagos State parks and Garden

- Community based NGOs

Project locations

Project will be located in 40 community development areas, each in the six (6) geopolitical zones of Nigeria.

Number of beneficiaries

All public schools are eligible for the project. However, preference will be given to schools with conservation clubs and schools recommended based on topography and need assessment. 240, conservation clubs, 240 schools, 800 teachers and 4000 students will be trained

Budget

| S/N | Items | Unit | Quantity | Unit rate (N) | Total cost(N) | Comment |
| --- | --- | --- | --- | --- | --- | --- |
|  | Research | 1 | 5 | 50,000 | 250,000 |  |
|  | Stipend for volunteers | 40 | 6 | 10,000 | 2,400,000 |  |
|  | Stakeholder’s meeting | 6 | 1 | 100,000 | 600,000 |  |
|  | Purchase of trees | 30 | 240 | 500 | 3,600,000 |  |
|  | Purchase and distribution of tree planting equipment | 40 | 6 | 50,000 | 12,000,000 | Topsoil and manure inclusive |
|  | Creation of conservation club | 40 | 20 | 5,000 | 4,000,000 | Each volunteer is expected to create 20 conservation club and carry out tree planting in one |
|  | Training of teachers and students | 240 | 5 | 1,000 | 1,200,000 | 240 schools 800 teachers and 4000 students to be trained |
|  | Tree planting exercise | 240 | 1 | 20,000 | 4,800,000 |  |
|  | Trees nurturing | 240 | 1 | 5,000 | 1,200,000 |  |
|  | Monitoring and evaluation | 6 | 1 | 100,000 | 600,000 |  |
|  | Media | 6 | Lumpsum | 3,000,000 | 3,000,000 |  |
|  | Miscellaneous | 1 | Lump sum | 3,600,000 | 3,600,00 |  |
| Total cost |  |  |  |  | 37,000,000 |  |
|  | Admin. charges |  |  |  | 3,700,000 |  |
| Grand Total |  |  |  |  | 40,700,000 |  |