## Funding Allocation Summary Prod
Summary of Project Funds Allocation |  | Percent Allocation
Global Giving Processing and Service | 903 | 10.84%
Construction of Organic Coconut Processing Facility | 4023.6183 | 48.29%
Development of Organic Coconut Processed Products | 1556 | 18.67%
Transportation | 57.7 | 0.6925%
Balance | 1792 | 21.51%
TOTAL | 8332.3183 | 100%
Organic Coconut Processed Product Made During Quality Production Method Development
Date of Production | Organic Virgin Coconut Oil (L) | Organic Coconut honey (L) | Organic Coconut Sap Drink (Liter) | Organic Coconut sugar (Kg)
2021-12-21 | 1 | 4 | 4 | 0.5
2021-12-21 | 1 | 6 | 4 | 8.2
2021-12-21 | 1.5 | 6 | 6 | 1
2021-12-21 | 2 | 12 | 8 | 2
2021-12-29 | 2.2 | 10 | 8 | 1.2
2021-12-29 | 2.5 | 12 | 8 | 1.5
2021-12-29 | 3.5 | 12 | 8 | 2
2022-01-07 | 3.5 | 12 | 8 | 2
TOTAL | 17.2 | 74 | 54 | 18.4

## Funding Allocation Details
Funding Allocation Details
|  | Summary of Project Funds Allocation |  | Percent Allocation |  |  |  | Global Giving Funds Raised | 8332
|  | Global Giving Processing and Service | 903 | 10.84% |  |  |  | 12% Global Giving Processing and Service Fee | 903
|  | Construction of Organic Coconut Processing Facility | 4023.6183 | 48.29%
|  | Development of Organic Coconut Processed Products | 1555.7134 | 18.67% |  |  | Fund Received from Global Giving | Philippine Peso | Peso to USD rate
|  | Training | 57.7 | 0.6925% |  | 44495 | 4714.73 | 236066.53 | 50.07
|  | Balance | 1792 | 21.51% |  | 11/24/2021 | 785.04 | 39390.95 | 50.18
|  | TOTAL | 8332.0317 | 100% |  | 12/24/2021 | 1928.28 | 95677.4 | 49.62
[7 empty] | 7428.05 | 371134.88 | Total Fund Received
-362802.88
How Donation for Support 1000 Philippine Coconut Farmers Project was used from October to January, 2021
Date |  | Organic Coconut Processing Facility Construction |  | Labor for Organic Processing |  | Training Expense |  | Supply for Production Development of Organic Processed Products |  | Note | Staff Responsibilities | Staff output for the month
|  | Philippine Peso (PHP) | US Dollar ($) | Philippine Peso (PHP) | US Dollar ($) | Philippine Peso (PHP) | US Dollar ($) | Philippine Peso (PHP) | US Dollar ($)
2021-10-28 | CV#6419 |  |  | 1800 | 35.9497 |  |  |  |  | One (1) Food processing production staff | Aid in preparation of the facility (cleaning, reconditioning), buying of supplies, utensils and scouting of equipment suppliers. | Quotations from suppliers, build up of initial consumable supplies, a more prepared facility
2021-10-28 | CV#6419 |  |  | 2500 | 49.9301 |  |  |  |  | One (1) Food processing production staff | Receive training; learn and amster the holistic VCO and coco products production system of FARMCOOP; Improvement of production efficiency. | A more effiocient production system; prodcution staff who are more efficient and have thorough knowledge of all the rationale of the processes they conduct.
2021-10-28 | CV#6419 |  |  | 2000 | 39.9441 |  |  |  |  | One (1) Food processing production staff | Produce samples and keep them for further product improvement, setting of production standards, and keep retention samples for physico-chemical and microbiological analysis and shelflife study; | Have data and product information re Nutritional facts and physico-chemical and microbioligical characteristics of the products.
2021-11-02 | CV#6432 | 28672.4 | 572.6463 | [6 empty] | Construction supplies for VCO Processing Room-CI#17732
2021-11-12 | CV#6441 |  |  |  |  | 2885.23 | 57.4976 |  |  | (1 )Food processing Production staff, (1) Food technologist, (1) Production administrator, (1) Coop coordinator, (1)Production Finance Administrator | To thoroughly learn the tranferred technology re coconut food processing and be able to relay the transferred technology to all FARMCOOP personnel who will be involved in the VCO and other coocnut food product processing. To develop a system of production applicable to FARMCOOP based on the learned technology. | Re-echoing of training. Development of production system and overall business plan for FARMCOOP's venture in VCO and other coconut food product processing.
2021-11-29 | CV#6477 | 3225 | 64.2686 | [6 empty] | Labor for construction of organic coconut production facility (11/11/2021-11/25/2021)
2021-11-29 | CV#6477 |  |  | 5500 | 109.6054 |  |  |  |  | Two (2) Food processing production staff | Do actual production dry runs, prior to the formal opening, using the final facility and equipment set up; Help prepare and set up the facility for the launching, and and other coconut product. | A crew, set of equipment, and a facility ready for actual official production of VCO and other coco products for market.
2021-11-29 | CV#6477 | 3500 | 69.7489 | [6 empty] | Labor for construction of organic coconut production facility (11/22/2021-11/26/2021)
2021-11-29 | CV#6477 | 3500 | 69.7489 | [6 empty] | Labor for construction of organic coconut production facility (11/22/2021-11/26/2021)
2021-11-30 | Temporary | 1009 | 20.1076 | [6 empty] | contruction supplies
2021-12-02 | CV#6499 | 45707 | 921.1407 | [6 empty] | Construction supplies for VCO Processing Room-CI#17946
2021-12-06 | CV#6501 | 3500 | 70.5361 | [6 empty] | VCO Painting Labor 11/27-12/03/2021
2021-12-06 | CV#6501 | 3500 | 70.5361 | [6 empty] | VCO Painting Labor 11/27-12/03/2021
2021-12-17 | CV#6524 | 39270 | 791.4148 | [6 empty] | Installation of acryclic window glass-labor and materials for VCO processing plant
2021-12-21 | CV#6531 |  |  | 4637.5 | 93.4603 |  |  |  |  | One (1) Food processing production staff | Initial production of finished products stocks (to be given to guests during launching). | 1 liters VCO, 0.5 kg coco sugar, 4 Liters coco honey, 4 Liters coco sap drink
2021-12-21 | CV#6531 |  |  | 7087.5 | 142.8356 |  |  |  |  | One (1) Food processing production staff | Building up of stocks ready for selling | 1 liter VCO, 8.2kg coco sugar, 6 liters coco honey, 1 liters coco sap drink
2021-12-21 | CV#6531 |  |  | 7087.5 | 142.8356 |  |  |  |  | One (1) Food processing production staff | Building up of stocks ready for selling | 1.5 liters VCO, 1kg coco sugar, 6 liters coco honey, 6 Liters coco sap drink
2021-12-21 | CV#6531 |  |  | 2475 | 49.8791 |  |  |  |  | One (1) Food processing production staff | Building up of stocks ready for selling | 2 liters VCO, 2 kg coco sugar, 12 liters coco honey, 8 Liters coco sap drink
2021-12-21 | CV#6531 |  |  | 500 | 10.0766 |  |  |  |  | One (1) Food processing production staff | Lauching preparation (general cleaning of the facility and the surrounding area, assists in decoration and preparation of the program area, bottling/packing of samples as giveaways for guests, etc.) | A facility ready to accommodate guests for the launching and is also ready for Food and Drug Aministration visit on the daya after the launching.
2021-12-22 | CV#6536 |  |  | 4200 | 84.6433 |  |  |  |  | One (1) Coconut Sap or Toddy Collector | Maintenance (cleaning and conditioning of the tree, its immediate surrounding, and sap catching receptacles) of the coconut tree and every 3 hour collection of coconut sap and endorsement of the sap to the delivery rider (going to the production facility) | 30 gallons of sap
2021-12-22 | CV#6536 |  |  | 4200 | 84.6433 |  |  |  |  | One (1) Coconut Sap or Toddy Collector | Maintenance (cleaning and conditioning of the tree, its immediate surrounding, and sap catching receptacles) of the coconut tree and every 3 hour collection of coconut sap and endorsement of the sap to the delivery rider (going to the production facility) | 30 gallons of sap
2021-12-27 | CV#6544 | 29097 | 586.3966 | [6 empty] | Construction supplies for VCO Processing Room-CI#17982 & 17984
2021-12-28 | CV#6552 |  |  | 3600 | 72.5514 |  |  |  |  | One (1) Coconut Sap or Toddy Collector | Maintenance (cleaning and conditioning of the tree, its immediate surrounding, and sap catching receptacles) of the coconut tree and every 3 hour collection of coconut sap and endorsement of the sap to the delivery rider (going to the production facility) | 40 gallons of sap
2021-12-28 | CV#6552 |  |  | 3600 | 72.5514 |  |  |  |  | One (1) Coconut Sap or Toddy Collector | Maintenance (cleaning and conditioning of the tree, its immediate surrounding, and sap catching receptacles) of the coconut tree and every 3 hour collection of coconut sap and endorsement of the sap to the delivery rider (going to the production facility) | 40 gallons of sap
2021-12-29 | CV#6559 |  |  | 7053.75 | 142.1554 |  |  |  |  | One (1) Food processing production staff | Building up of stocks ready for selling (VCO extraction, honey and sugar cooking, sap juice pasteurization) | 2.2 liters VCO, 1.2kg coco sugar, 10 Liters coco honey, 8 Liters coco sap drink
2021-12-29 | CV#6559 |  |  | 7425 | 149.6372 |  |  |  |  | One (1) Food processing production staff | Building up of stocks ready for selling (VCO extraction, honey and sugar cooking, sap juice pasteurization) | 2.5 liters VCO, 1.5kg coco sugar, 9 Liters coco honey, 8 Liters coco sap drink
2021-12-29 | CV#6559 |  |  | 7400.25 | 149.1385 |  |  |  |  | One (1) Food processing production staff | Building up of stocks ready for selling (VCO extraction, honey and sugar cooking, sap juice pasteurization) | 3.5 liters VCO, 2kg coco sugar, 12 Liters coco honey, 8 Liters coco sap drink
2021-12-29 | CV#6568 | [6 empty] | 142 | 2.8617 | Purchase of Coconut at Libay-Libay,Maco-12/28/2021
2021-12-29 | CV#6568 | [6 empty] | 1000 | 20.1532 | Purchase of Coconut at Libay-Libay,Maco-12/28/2021
2021-12-29 | CV#6568 | [6 empty] | 5000 | 100.7658 | Purchase of Coconut at Libay-Libay,Maco-dehusked coconut@8.50kg 12/28/2021
2021-12-29 | CV#6568 |  |  | 104 | 2.0959 |  |  |  |  | One (1) Farm Level Quality Controller | Manually check the individual quality of nuts that will be dlievered to the processing facility. | 1487 nuts were quality checked
2021-12-29 | CV#6572 | 39054.6 | 787.0738 | [6 empty] | Construction supplies for VCO Processing Room-CI#18113;18121 and 18134
2021-01-07 |  |  |  | 9600 | [5 empty] | Three (3) Food processing production staff | Building up of stocks ready for selling (VCO extraction, honey and sugar cooking, sap juice pasteurization) | 3.5 liters VCO, 2kg coco sugar, 12 Liters coco honey, 8 Liters coco sap drink
TOTAL |  | 200035 | 4023.6183 | 80770.5 | 1431.9327 | 2885.23 | 57.4976 | 6142 | 123.7807

## Coconut Products
Organic Coconut Processed Product Made During Quality Production Method Development
Date of Production | Organic Virgin Coconut Oil (L) | Organic Coconut honey (L) | Organic Coconut Sap Drink (Liter) | Organic Coconut sugar (Kg)
2021-12-21 | 1 | 4 | 4 | 0.5
2021-12-21 | 1 | 6 | 4 | 8.2
2021-12-21 | 1.5 | 6 | 6 | 1
2021-12-21 | 2 | 12 | 8 | 2
2021-12-29 | 2.2 | 10 | 8 | 1.2
2021-12-29 | 2.5 | 12 | 8 | 1.5
2021-12-29 | 3.5 | 12 | 8 | 2
2022-01-07 | 3.5 | 12 | 8 | 2
TOTAL | 17 | 74 | 54 | 18