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Our Ref: FCDA/BD/A/001/8/23

AGRIBUSINESS ACTIVITY REPORT-MARCH- DECEMBER 2022, BERTOUA, CAMEROON
The first year of agribusiness experimental phase resulted to a 28% return on investment following the 123,000 frs invested in the project, we recorded 157,000frs in revenue, Gross profit of 34,000frs with source from personal savings of the Founder.
The project was geared towards experimenting the potentials which lies to capacitate the Internally Displaced Persons through generating livelihoods, income, food security, employment from agriculture and technology.
This was a 10 months project which began in March 2022 and ended in December 2022, with a dedicated 159 hours.
In September 2022, Jan Afungchui joined and supported the project idea and initiative partnering with the sum of 100,000frs, also accompanied by eagerness for expansion to Livestock, planting of cassava, support and trainings, documentations and integrated following up with the value chain in Agriculture through learnings and practicality for Moral Leadership and thereby making the World a better place.
Please find attached table for expenditures report for after first phase of experimenting

Financial Report- First Experimental Project
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We successfully ploughed back 34,000frs from the profit, added to the 100,000frs from a partner, totaling 134,000frs to engage in the second season of cultivation. 
The team decided to plant cassava and yam on the 7,500Sq Metres of Gifted Land, amidst the drastic climate situation and poor planning for season, only cassava was planted on 3,750Sq of land where the potatoes had just been harvested, making it fertile for cassava production.
From September 2022 till 31st December 2022, 96,000frs have been used for production of the latter with a balance of 38,000frs cash at at date.
Please find attached details of expenditure report
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We also engaged into digital fundraising for the project through GlobalGiving Foundation platform and raised 111 USD which is yet to be dished out to FCDA following recommendations to reach a certain quota before depositing into the account of FCDA. We look forward to intensify our campaigns through inviting volunteer, other members, encourage atleast 100 IDPs to join and benefit from the projects while also working with other organizations for shared opportunities, learning and sustainable partnerships.
Our goal is to harvest the cassava in July, transform into grains (garri), packaged and to be sold in the local markets. We envisage generating 800 KGs of yellow and white garri. These will be sold at 25,000frs per 100KG. We hope to have 200,000frs as revenue and further expenditures till goods reach the clients is estimated at 45,000frs. Thus, total expenditure of 141,000frs and net profit of 59,000frs by the one-year period in September 2023.
The team is poised to undertake piggery activities and they are set to raise funds and invite other members so as to step up production, generate income and stay in the business.
The next virtual meeting for partners will be on Friday the 6th of January 2023 for one hour.
Partners will discuss on project expansion, outlook and resources needs.

Challenges
Poor transport system. Farm to market roads is deplorable. This makes cost soar and thus preventing farmers to sell at fair price
· Fluctuation in prices
· Lack of storage facilities
· Climate action
· Limited tools
· Inadequate capital
· Covid 19 Pandemic
· Growing insecurity
Recommendation
· Partners should extend project to call for funds
· Build a storage facility
· Provide a means of transportation
· Increase farm land
· Recruit 100 IDPs
· Source for more local and international partnerships
· Need to raise 2,000,000frs by June 2023 through other sources to increase production and diversify
· Undertake Piggery Farming






Name: Etienne Ayuk Ayuk Ndip
Location: Bertoua, Cameroon
Date: 6-1-2023
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Maize harvested at storage room             Farm Coordinator post with Founder Etienne on Cassava Farm
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Harvesting of Sweet Potatoes 3/9/2022
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Location of Project

Expenses Activities Maize 3,750Sq Potatoes 3,750Sq Yam  Cassava Total

Effective 

Hours Dates

Land  0 710th March 2022 

Equipment tools( Cutlass, Hoe, booths, 

wheel barrow  and File) 10,000 10,000 212th March 2022 

Clearing of Land 6,000 6,000 12,000 1019th March 2022

Preparation of land( Digging) 10,000 10,000 20,000 79th April 2022

Seeds 10,000 12,000 22,000 810th April 2022

Treatment/Spraying 7,000 10,000 17,000 2017th April, 2022

Planting 6,000 7,000 13,000 2521st April 2022

Weeding/Maintenance 7,000 5,000 12,000 4015th September, 2022

Transport 8,000 5,000 13,000 10Every visit

Communications 2,000 2,000 4,000 30Weekly

Total Cost 66,000 57,000 0 0 123,000 159

Revenue Number of Bags 100/KG 5 6

Unit Amount Per Bag 17,000 12,000 26,000 15,000

Total Revenue 85000 72000 0 0 157000

Net Gain 19,000 15,000 0 0 34,000

Selling of Produces-Farm 

land Aug-22 Aug-22 15th August 2022

Profitability Ranking 2nd 1st

Cost of Investment 123,000

Revenue 157000

Pofit 34,000

Return on Investment( ROI) % 28                       

7,500 Sq. M- Koume Goffi- 15 KMs from Bertoua Town
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Location of Project

Expenses Activities Maize  Potatoes 3,750Sq Yam  Cassava Total

Effective 

Hours Dates

Balance B/D 34,000 30th September 2022 

Contribution From Jan 100,000 30th September 2022 

134,000

Equipment tools( Cutlass, Hoe, booths, wheel 

barrow  and File) 0

Clearing of Land 13,000 13,000 104th October 2022

Preparation of land( Digging) 12,000 12,000 2011th October 2022

Seeds 16,000 16,000 1011th October 2022

Treatment/Spraying 11,000 11,000 1215th October, 2022

Planting 15,000 15,000 1418th October 2022

Weeding/Maintenance 15,000 15,000 4015th December, 2022

Transport 10,000 10,000 10Every visit

Communications 4,000 4,000 30Weekly

Total Cost 0 0 0 96,000 96,000 146

Total Amount Available 38,000

Projected Expenditure tii September 2023 45,000

Estimated Cash at hand by By Beginning October 97,000

Revenue Number of Bags 100/KG 8

Unit Amount Per Bag 25,000

Total Revenue 0 0 0 200000 200000

Net Gain 0 0 0 104,000 104,000

Selling of Produces-Farm 

land Sep-23 05th September 2022

Profitability Ranking 2nd 1st

Cost of Investment

Revenue

Pofit

Return on Investment( ROI) %

7,500 Sq. M- Koume Goffi- 15 KMs from Bertoua Town
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Location of Project


Expenses


Activities


Maize 3,750Sq


Potatoes 3,750Sq


Yam 


Cassava


Total


Effective 


Hours


Dates


Land 


0


7


10th March 2022 


Equipment tools( Cutlass, Hoe, booths, 


wheel barrow  and File)


10,000


10,000


2


12th March 2022 


Clearing of Land


6,000


6,000


12,000


10


19th March 2022


Preparation of land( Digging)


10,000


10,000


20,000


7


9th April 2022


Seeds
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12,000


22,000


8


10th April 2022


Treatment/Spraying


7,000


10,000


17,000


20


17th April, 2022


Planting


6,000


7,000


13,000


25


21st April 2022


Weeding/Maintenance
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40


15th September, 2022


Transport
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10


Every visit


Communications


2,000
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Total Cost
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0
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Revenue


Number of Bags 100/KG
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Unit Amount Per Bag
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Total Revenue
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Location of Project

Expenses Activities Maize 3,750Sq Potatoes 3,750Sq Yam  Cassava Total

Effective 

Hours Dates

Land  0 710th March 2022 

Equipment tools( Cutlass, Hoe, booths, 

wheel barrow  and File) 10,000 10,000 212th March 2022 

Clearing of Land 6,000 6,000 12,000 1019th March 2022

Preparation of land( Digging) 10,000 10,000 20,000 79th April 2022

Seeds 10,000 12,000 22,000 810th April 2022

Treatment/Spraying 7,000 10,000 17,000 2017th April, 2022

Planting 6,000 7,000 13,000 2521st April 2022

Weeding/Maintenance 7,000 5,000 12,000 4015th September, 2022

Transport 8,000 5,000 13,000 10Every visit

Communications 2,000 2,000 4,000 30Weekly

Total Cost 66,000 57,000 0 0 123,000 159

Revenue Number of Bags 100/KG 5 6

Unit Amount Per Bag 17,000 12,000 26,000 15,000

Total Revenue 85000 72000 0 0 157000

Net Gain 19,000 15,000 0 0 34,000

Selling of Produces-Farm 

land Aug-22 Aug-22 15th August 2022

Profitability Ranking 2nd 1st

Cost of Investment 123,000

Revenue 157000

Pofit 34,000

Return on Investment( ROI) % 28                       

7,500 Sq. M- Koume Goffi- 15 KMs from Bertoua Town

