## Foglio1
GOAL | ACTIVITIES | 2022-2023
|  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
PREPARATORY AND CONTINUING ACTIVITIES
Purchase of medicines and medical equipment
Strengthening relationships with migrant communities
Defining the timetable for monthly visits with communities
ACTIVITY 1 Monthly organization of mobile clinics in project target migrant communities
Strengthening the network of volunteers in each community to provide logistical support for the mobile clinic
Preparation and verification of health materials for monthly activities
Organization of the mobile clinic with the health team
Progressive inclusion of the new 30 CHVs within the management of mobile clinics | bar: 2022-2023 6 to 2022-2023 12
Distribution of questionnaires at the conclusion of the projects | bar: 2022-2023 12
ACTIVITY 2 Community Health Volunteer (CHV) training on the topics of first aid, preventive health care and the HICS program
Identification of the 30 training participants for CHV | bar: 2022-2023 1
Definition of training topics in the field of health, nutrition, and access to the national health care system | bar: 2022-2023 1
Training of Community Health Volunteers by Medacross health staff | bar: 2022-2023 1 to 2022-2023 5
Organization of community awareness days on health security and legal rights of migrants by CHVs | bar: 2022-2023 6 to 2022-2023 12
Distribution of Pre- and Post-training Tests for CHVs. | bar: 2022-2023 1; 2022-2023 12
RECURRING AND CONCLUDING ACTIVITIES
Digital communication activities
Preparation of the final report | bar: 2022-2023 12