# ACTIVITY REPORT

### Distribution of Dignity Kits to Conflict-Affected Women and Adolescent Girls in Commemoration of the 16 Days of Activism to End Violence against Women and Girls

| Activity Title: | ### Tarmuwa, Gujba, and Damaturu LGAs – Yobe State, Nigeria |
| --- | --- |
| Supported by: | ### United Nations Population Fund (UNFPA) |
| Reporting Period: | ### 4th, 5th and 6th December 2025 |
| Background / Context | Communities in Gujba, Tarmuwa, and parts of Damaturu continue to suffer the humanitarian consequences of prolonged insecurity, forced displacement, poverty, and limited access to essential protection services. Women and adolescent girls face unique protection risks including: - Lack of access to menstrual hygiene materials - Increased exposure to GBV - Poor sanitation and hygiene - Limited mobility and loss of livelihoods To address these urgent needs, HOPLE, with support from UNFPA, implemented a dignity kit distribution targeting the most vulnerable women and girls to promote safety, dignity, and improved menstrual hygiene management. |
| ## Executive Summary | HOPLE has successfully conducted the distribution of 400 dignity kits to conflict-affected women and adolescent girls in Gujba, Tarmuwa, and Damaturu LGAs of Yobe State, with generous support from the United Nations Population Fund (UNFPA). The activity followed a transparent and fairness-based targeting process, conducted in coordination with SEMA, CDO offices, and relevant stakeholders. The distribution took place over three days: - 150 kits – Buni Yadi (Gujba LGA) Secretariat on Thursday, 4th December 2025 - 150 kits – Tarmuwa LGA Secretariat on Friday, 5th December 2025 - 100 kits – Bulabulin, Damaturu on Saturday, 6th December 2025 Beneficiaries were primarily conflict-affected women and adolescent girls aged 15–40, including survivors of displacement, GBV, vulnerable households, and those at heightened protection risk. The distribution was completed successfully, safely, and in an orderly manner, with no recorded incidents of harm to beneficiaries or aid workers. |
| ## Objectives of the Activity | The primary objectives of the dignity kits distribution included: - Promote women and girls’ dignity, safety, and wellbeing through access to essential hygiene and protection items. - Support conflict-affected households with menstrual hygiene materials to reduce negative coping mechanisms. - Improve awareness of GBV prevention, child protection, and available referral pathways through community engagement. - Strengthen coordination with government actors (SEMA, CDOs, and community leaders) to ensure fair, inclusive, and transparent selection of beneficiaries. |
| ## Target Beneficiaries | Targeted beneficiaries were: - Conflict-affected women and adolescent girls - IDPs, returnees, and vulnerable host community members - Age group: 15–40 years - Prioritized groups include female-headed households, widows, young girls at risk, and women with limited access to income or hygiene materials. |
| ## Coordination and Stakeholder Engagement | The activity was carried out in close collaboration with: - UNFPA (support and technical guidance) - SEMA Representatives (oversight and coordination) - Community Development Officers (CDOs) from Gujba, Tarmuwa, and Damaturu - Community Leaders and Women Focal Persons - Local Government Authorities Stakeholder engagement ensured: - Transparent beneficiary targeting - Smooth logistical arrangements - Community acceptance and participation - Security and crowd control during the distribution |
| ## Distribution Summary | ### 6.1 Distribution Schedule and Locations Date; Location; LGA; Quantity Distributed. 4th December 2025; Buni Yadi LGA Secretariat; Gujba; 150 kits. 5th December 2025; Tarmuwa LGA Secretariat; Tarmuwa; 150 kits. 6th December 2025; Bulabulin Ward; Damaturu; 100 kits. ### Total Distributed: 400 dignity kits |
| ## Activity Implementation Process | ### Beneficiary Targeting - Targeting was conducted through an inclusive and fairness-based approach. - Community leaders, women groups, CDOs, and SEMA were fully involved. - Verification of beneficiary lists was completed prior to the distribution date. ### Distribution Approach - Registration and identity verification - Awareness and brief orientation on kit contents - Safe, orderly line-up and crowd control - Distribution supervised jointly by HOPLE, SEMA, and CDO staff - GBV and child protection key messages delivered before handover of kits Safety and Do-No-Harm - The distribution adhered to UNFPA protection principles - No security incident or harm recorded - Safe and dignified access ensured for adolescent girls and women - Complaint and feedback mechanisms were available at each site. |
| ## Key Achievements | - Successfully reached 400 conflict-affected women and adolescent girls across 3 LGAs. - Enhanced menstrual hygiene and protection for vulnerable women/girls. - Strengthened local coordination with SEMA, CDOs, and community leaders. - Increased awareness of GBV prevention, child protection, and available services. - Conducted safe and orderly distribution with zero incidents recorded. - Improved community trust and visibility of UNFPA and HOPLE interventions. |
| ## Challenges and Mitigation Measures | Challenge; Mitigation. High demand due to large population of vulnerable women and girls; Beneficiary lists were strictly verified and prioritized based on vulnerability criteria.. Distance and mobility constraints for some beneficiaries; Community volunteers supported with referrals and transportation arrangements for the most vulnerable.. Large crowd turnout; Crowd control support was provided through community leaders and CDO offices.. |
| ## Lessons Learned | - Early coordination with stakeholders ensures efficient implementation. - Fairness-based targeting reduces tension and promotes community acceptance. - Distributing GBV awareness messages before kit handover leads to better understanding of available protection services. - Engaging women volunteers improves communication with adolescent girls |
| ## Recommendations | - Increase allocation of dignity kits due to the high level of need across LGAs. - Strengthen follow-up activities to monitor how the items support menstrual hygiene and dignity. - Expand GBV awareness and referral pathways training for local women groups. - Continue collaboration with SEMA, CDOs, and UNFPA for future protection interventions. |
| ## Conclusion | The dignity kits distribution activity was successfully implemented and contributed significantly to restoring dignity, enhancing menstrual hygiene, and improving the wellbeing of conflict-affected women and adolescent girls in Tarmuwa, Gujba, and Damaturu LGAs. HOPLE remains committed to promoting dignity, protection, and resilience of vulnerable groups, and appreciates UNFPA’s continuous support in enabling impactful humanitarian interventions. |
| Annexes |  |