# YOUTH THRIVE OVERALL MONTHLY REPORT – APRIL 2025

Reporting Sub-Counties: Jomvu, changamwe & Likoni

Compiled by: Saumu Hussein

Designation: Project Officer

Reporting Month: April 2025

Facilities: Mikindani Health Center (Jomvu), Likoni Sub-County Hospital (Likoni), Coast General Teaching and Referral Hospital.

# Introduction

This report provides a consolidated overview of the activities, achievements, challenges, and recommendations from the Youth Thrive project implemented in April 2025 across Jomvu, Changamwe and Likoni Sub-Counties. The Youth Thrive project aims to improve access to Sexual and Reproductive Health and Rights (SRHR), HIV prevention, mental health awareness, and youth empowerment through integrated community engagement and facility-based interventions.

This report highlights community outreach activities, male engagement forums, mental health sensitizations, and collaborations with local organizations to reach adolescents and young people (AYP). It also underscores emerging challenges and provides actionable recommendations to enhance service delivery and youth participation in future programming.

# 1. Activities Conducted

## Jomvu Sub-County (Mikindani Health Center)

Male Engagement Forum:
  - Discussed SRHR, condom use, and positive masculinity.
  - Resulted in the formation of a “Boys to Men Club”.

Family Planning Inreach (with SHOFCO):
  - Engaged young women; formed a support group for young mothers.

Condom Sensitization & HIV Prevention (Kwashee):
  - Reached 21 participants.

Community Mobilization (Bangladesh & Mikindani):
  - Demonstrated condom use, discussed family planning, and made clinic referrals.

## Likoni Sub-County (LSCH)

Community Outreach Activities:
  - Reached 150 adolescents and youth on HIV/AIDS, mental health, SRHR, and drug abuse.
  - Improved mental health literacy and increased AYP access to youth-friendly services.

## Changamwe Sub-County

- Community Outreach Activities:

- Reach 46 AYP on safe sex, safe use of contraception and responsible sexual behaviors

- mental health sessions with AYPs

# 2. Achievements

Formation of interest/support groups (e.g., Boys to Men Club, Young Mothers Support Group – Jomvu).

Increased awareness and openness on SRHR topics among youth people

Engagement of over 308 youth across the 3 sub-counties.

Mental health education integrated into outreaches

Improved visibility and demand for AYFS in the 3 facilities.

# 3. Challenges Identified

Cultural stigma around SRHR, especially male involvement.

Youth-unfriendly health facilities- some of the health facilities are still lacking essential youth friendly services and resources

Limited resources (e.g., demonstration materials, refreshments, printing costs).

Harsh weather affecting outreach.

Participant scheduling conflicts due to personal commitments.

# 4. Recommendations

Partner with health facilities to enhance youth- and male-friendly services.

Continue engaging community and religious leaders to reduce stigma especially in socially and religious conserved communities

Invest in community-friendly venues for private sessions, this will improve confidentiality among the peers

Incorporate service delivery with information-sharing during outreach.

Advocate for a dedicated Youth Friendly Center in facilities – most of the youth friendly centres are not stand alone, they do intergrated services hence not providing ideal youth friendly services

# 5. Performance Summary (April 2025)

| Indicator | Jomvu | Likoni | changamwe | Total |
| --- | --- | --- | --- | --- |
| Reached with HIV/SRH info (male) | 26 | 50 | 24 | 100 |
| Reached with HIV/SRH information (Female) | 40 | 146 | 22 | 208 |
| Total Number Reached (Male) | 26 | 50 | 24 | 100 |
| Total Number Reached (Female) | 40 | 146 | 22 | 208 |
| Grand Total Reached | 66 | 196 | 46 | 308 |