_________________________________

#### Kashf Foundation

- Towards the Economic Empowerment of Women

_________________________________

_________________________________

_________________________________

- Quarterly Report

_________________________________

- Period: April-June 2006

_______________________________________________________________

- Kashf Foundation

Head Office: 19 Aibak Block, New Garden Town, Lahore, Pakistan.

Tel: 92-111-981-981     Fax: 92-42-5847816

Email: info@kashf.org.pk

WEB-PAGE: www.kashf.org

Table of Contents:

April-June 2006: At a Glance	3

Summary of the Main Outcomes	5

Performance during the April-June Quarter	6

Total Outreach For Programme 	7

Financial Sustainability	10

Overall Performance	10

Profitability Ratios	11

Efficiency Ratios	11

Operational Performance	12

Financing Sources:	13

Human Resource Management	13

Staff Capacity Development	15

Gender Empowerment & Social Advocacy	17

1. April- June 2006 at a Glance

| Total Outreach For Programme |  |  |
| --- | --- | --- |
|  | Jan-March ‘06 | April-June ‘06 |
| Outreach (cumulative) | 80,191 | 90,326 |
| Number of Loans (GL) (cumulative) | 263,104 | 287,246 |
| Number of Loans (EL) (cumulative) | 179,847 | 200,552 |
| Number of Loans (BSL) (cumulative) | 518 | 698 |
| Total Loans (Cumulative) | 443,469 | 488,496 |
| Savings (cumulative) | 6,520,632 | 6,148,431 |
| Saving per client (Rs.) | 82 | 73 |
| Customers attrition rate (%) | 3.85% | 2.85% |

| Portfolio Quality-Recovery & Risk Analysis |  |  |
| --- | --- | --- |
|  | Jan- March | April-June |
| Recovery % | 100 % | 100 % |
| PAR (%) | 0.27 % | 0.10 % |
| Overdue amount | 2,062,735 | 5,792,305 |

| Source of Income Generation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Income from Financial Services | Jan-March 2006 | April-June 2006 | Percentage Change | Percentage Share (%) |
| Service Charge | 61,123,562 | 69,955,719 | 14.5% | 88.5 |
| Investments | 2,480,444 | 7,862,252 | 217% | 9.9 |
| Other Income | 1,483,991 | 1,213,775 | (-)18.2% | 1.53 |
| Total Income | 65,087,997 | 79,031,746 | 21.5% | 100 |

| Efficiency Ratios |  |  |
| --- | --- | --- |
| Efficiency Ratios | FY to March 2006 | FY to June 2006 |
| Administrative Efficiency | 18.67% | 18.96% |
| Operational Efficiency | 23.26% | 23.59% |
| Operational Self sufficiency | 164.98% | 164.60% |
| Financial Self Sufficiency | 112.63% | 114.11% |

| Profitability Ratios |  |  |
| --- | --- | --- |
| Profitability Ratios | FY to March 2006 | FY to June 2006 |
| Return on Assets (Adjusted) | 2.64% | 3.03% |
| Return on Equity (Adjusted) | 4.89% | 5.80% |
| Yield on Portfolio | 36.03% | 35.31 % |

# 2. Summary of the Main Outcomes

During the course of the Quarter April-June 2006, the programme reached out to 90,000 clients. In terms of amount disbursed, the disbursement of all loan products, that is the General Loan (GL), the Emergency Loan (EL) and Business Surmaya Loan (BSL) increased over this quarter and can be attributed to greater turn around time of repeat clients and reduction in the exit ratio. The number of customers increased primarily due to upgradation of branches from 4/5 LOs to 5/6 LOs. Due to better monitoring polices and weekly tracking of pending centers client delinquency and dropout rates have been checked to a considerable extent.

The recovery rate has been maintained at 100%, while PAR has fallen from 0.27% to 0.1 % this quarter and can be attributed to the continuing emphasis on strong portfolio management and strong client screening procedures. The cumulative amount saved, however, decreased over the quarter. The pilot phase of the Home Improvement Loan (HIL) is running in two of Kashf’s branches: Ravi Rayon and Jorah Pull. The response to this new product is very encouraging and the pilot phase has been monitored to streamline all operational and policy features

Over this quarter, the organization has continued to concentrate on maintaining a strong portfolio quality, curbing the client attrition rate, propelling portfolio growth and catering to the needs of its clients by offering them a wider range of even more flexible services.

# Kashf’s Economic Empowerment Programme

True to its meaning, Kashf is an organization that has become the means of a ‘miracle’ or a ‘revelation’ for its clients. Through a sustained financial window, clients have been able to overcome their destitution by realizing their own potential and discovering that poverty is assailable through determination and enterprise. Kashf commenced as an action research programme in 1996, to evaluate whether formal credit opportunities for women from low income households would serve to enhance their productivity and facilitate opportunities for them to earn a steady income in order to ensure a dignified standard of living for their families. Having been spurred by 15 poor women who decided to put their faith in Kashf, the organization has been able to sustain rapid growth and currently caters to thousands of clients involved in various enterprises including livestock, basket making, shoe making, carpet making, weaving, sewing, and trading in cloth, wheat, rice etc and other accessories. The centerpiece of Kashf’s methodology is the alleviation of poverty by greater investment in gender empowerment. Therefore even while maintaining a household focus, at present Kashf is one of the few microfinance institutions in Pakistan that provides micro credit exclusively to poor women.

Kashf’s economic empowerment strategy is based on the provision of the following services:

- Microfinance Services:  Kashf offers sustained access to small loans and micro deposit services to its customers. The loans are provided without any physical collateral or personal guarantees.  However, in order to qualify for loans, women must self-select into a center of 25 members, who then take responsibility for loan repayment.

- Capacity Development: In addition to its microfinance programme, Kashf also offers its customers a host of training opportunities: these range from leadership trainings and gender awareness trainings to basic functional trainings.  Kashf provides all trainings to its customers within their own communities.

# 3. Program performance during April - June

- New branches opened during the quarter:

| Location Area-5 Okara | No. of branches 3 |
| --- | --- |
| Area-7 Faisalabad | 4 |
| Area-8 Faisalabad | 2 |
| Area-9 Sargodha | 1 |
| Area-10 Sahiwal | 1 |
| Yakki Gate (BSL branch) | 1 |
| Total | 12 |

## Total Outreach of the Programme

| Outreach |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Quarter Jan-march 2006 | April | May | June | Quarter April-June |
| Outreach (cumulative) | 80,191 | 82,736 | 86315 | 90326 | 90326 |
| Customers (drop out) | 3091 | 801 | 1020 | 749 | 2570 |
| Customers attrition rate (%) | 3.85% | 0.96 | 1.18 | 0.82 | 2.85% |

There has been an increase in the number of customers which has primarily been due to upgradation of branches from 4/5 LOs to 5/6 LOs increasing output. Furthermore, due to better monitoring policies and weekly tracking of pending centers, client delinquency and dropout rates have been curtailed to a considerable extent.

Weekly tracking of pending centers report resulted in the time of average pending centers per month to drop considerably. This substantial decrease in pending centers is due to diligent and timely feedback from HO to AMs to eliminate pending centers on the basis of aforementioned report which was started from Mar’06 onwards.

Currently the General Loan constitutes one of Kashf’s most popular services since it has enabled a number of clients to benefit from a marked increase in their income by granting them an opportunity to invest in various small enterprises and thus continues to grow strongly.

Disbursement – General Loan

| Disbursement-General Loan |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| By end Qtr Jan-March |  | April | May | June | By end Quarter April-June 2006 |
| Loan Amount Disbursed (Rs.) | 2,980,143,083 (cumulative) | 107,703,000 | 151,886,083 | 109,375,000 | 3,349,107,166 (cumulative) |
| Number of Loans | 263,104 (cumulative) | 6,860 | 9,651 | 7,631 | 287,246 (cumulative) |
| Average Loan Size (Rs.) | 11,327 | 15,700 | 15,738 | 14,333 | 11,659 (cumulative) |

The table above illustrates the trends in GL disbursement over the last two quarters. The total amount of loans disbursed in the quarter April-June 2006 has increased by 12.4% while that of the number of loans granted have registered a rise of 9.2%. These statistics indicate an increase in GL disbursement; this may be explained by the increase in the Average Loan Size, which increased by 2.9% this quarter. Previously, due to lack of monitoring thorough out the year branches tried to reach their targets at year end i.e. during the Quarter Oct-Dec. However, now that branches are being monitored on a monthly basis, disbursements are expected to be equally staggered through out the year. The difference between the two quarters, the current and the previous can be explained by this practice.

Disbursement – Emergency Loan

| Disbursement-Emergency Loan |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | By end Quarter Jan-March 2006 | April | May | June | By end Quarter April-June 2006 |
| Loan Amount Disbursed (Rs.) | 443,777,669 (cumulative) | 23,839,000 | 28,987,000 | 22,624,000 | 519,227,669 (cumulative) |
| Number of Loans | 179,847 (cumulative) | 6536 | 7,883 | 6,286 | 200,552 (cumulative) |
| Average Loan Size (Rs.) | 2,467 | 3,647 | 3,677 | 3,599 | 2,589 (cumulative) |

The Emergency Loan is mainly utilized for contingency reasons or for day to day running expenses which have to be incurred immediately. The particular value of the emergency loan is that it is “women friendly” product and enables the clients to access ready cash in the case of any small family emergency. Informal evidence has shown that the EL is often used to pay school fees or meet basic health care expenditures.

The average loan size has showed a modest increase when compared with the previous Quarter. The loan amount disbursed increased by 17% in the Quarter April-June 2006. In other words, the growth in disbursement of the EL has been sustained over this period. The number of loans disbursed has undergone an increase due to change in policy of the loan, which was previously disbursed once a year and is now available twice a year to the same client.

Disbursement – Business Surmaya Loan

| Disbursement-Business Surmaya Loan |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| By end Qtr Jan-March |  | April | May | June | By end Qtr April-June |
| Loan Amount Disbursed (Rs.) | 20,405,000 (cumulative) | 1,535,000 | 2,420,000 | 2,800,000 | 27,130,000 (cumulative) |
| Number of Loans | 518 (cumulative) | 45 | 66 | 69 | 698 (cumulative) |
| Average Loan Size (Rs.) | 39,392 | 34,111 | 36,666 | 40,580 | 38,868 (cumulative) |

The provision of the Business Sarmaya Loan (BSL) represents Kashf’s commitment to providing quality services to its customers according to their evolving needs. This product targets the missing middle of the market, that is, small entrepreneurs with existing businesses who require greater amounts of capital for developing and “running” their enterprises.

The table above illustrates the trends in BSL disbursement over the last two quarters. The total amount of loans disbursed in the current quarter has registered a rise while that of the number of loans granted have also aggravated.

Savings

| Savings |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | By end Qtr Jan-March | April | May | June |
| Savings (cumulative) | 6,520,632 | 6,353,292 | 6,260,612 | 6,148,431 |
| Saving per client (Rs.) | 82 | 77 | 73 | 68 |

The savings product has exhibited a slight downward trend. In this quarter, the total amount saved decreased by 5.7%, and the average savings per client also took a hit and came down to an average of Rs 73 for the quarter. This may be an early indicator telling us that we really need to focus on improving our saving product design that gives the right incentives to save.

Portfolio Quality-Recovery & Risk Analysis (PAR)

| Portfolio Quality-Recovery & Portfolio at Risk Analysis (PAR) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | End of Qtr Jan- march | April | May | June | End of Qtr April-June |
| Recovery % | 100 % | 100 % | 100 % | 100 % | 100 % |
| PAR (%) | 0.27 % | 0.26 % | 0.25 % | 0.10 % | 0.10 % |
| Overdue amount | 2,062,735 | 2,017,312 | 2,008,754 | 792,305 | 792,305 |

Indicators attesting portfolio quality and recovery rates are essential to gauge the success and feasibility of any micro finance institution. Kashf’s recovery rate has continued to be maintained at 100% this quarter. The table above shows PAR declining to 0.10%. The reduction in the PAR can be ascribed to the fact that additional clients have not been added to the delinquent portfolio while new loans have been disbursed over this period, thus bringing down this ratio.

In June’06, PAR of KRK Branch was excluded from the total PAR due to closure of the branch.

# 4. Financial Sustainability

## 1) Overall performance

The period under review experienced high growth strategy, opening of 12 new branches inclusive of 1 BSL branch, regional office in Karachi and launching of the new product dubbed “Home Improvement Loan” in two existing branches.

The organization’s equity stood at Rs 656 M [Mar 2006: Rs 626 M]. The growth of Rs. 30M in equity resulted from higher net income earned by Kashf. The income from loans increased to Rs. 69M from Rs 61 M for the quarter ended Mar, 2006. Personnel cost increased by 13% to Rs. 25.63Million [Quarter ended March 2006: 22.67 M]. The major variation in personnel cost is due to hiring of staff for new branches. Number of total staff has increased to 535 [Quarter ended March 2006: 446]. The administrative costs increased by 46% to Rs. 4.11M over the quarter. The major increase is due to setup cost of new branches and regional office.

| Quarterly Income From Financial Services |  |  |  |  |
| --- | --- | --- | --- | --- |
| Income from Financial Services | Jan-March 2006 | April-June 2006 | Percentage Change from last quarter | Percentage Share (%) In total income |
| Income from Service Charge | 61,123,562 | 69,955,719 | 14.5 | 88.5 |
| Income from Investments | 2,480,444 | 7,862,252 | 217 | 9.9 |
| Other Income | 1,483,991 | 1,213,775 | (-)18.2 | 1.53 |
| Total Income | 65,087,997 | 79,031,746 | 21.5 | 100 |

Compared to the last quarter, income rose from 65 million to 79 million registering an increase of 21.5%. Percentage share of income generated over the quarter resulted from 88.5% income generation in service charges, 9.9% from investment income and 1.53% from other sources. The respective indicators for the previous quarter were 94%, 3.8% and 2.2%.

This quarter the share of income generated from service charges has decreased and the share of income from investments has expanded. The income from other sources has also decreased as well.

## 2) Profitability Ratios

| Profitability Ratios |  |  |  |
| --- | --- | --- | --- |
| Profitability Ratios | FY to Dec 2005 | FY to March 2006 | FY to June 2006 |
| Return on Assets (Adjusted) | 2.08% | 2.64% | 3.03% |
| Return on Equity (Adjusted) | 3.45% | 4.89% | 5.80% |
| Yield on Portfolio | 33.02% | 36.03% | 35.31 % |

Definition of important ratios:

The Return on Assets maps the ability of the organization to generate income from all of its assets, i.e. how profitable has the organization been in investing its resources.

The Return on Equity maps the ability of the organization to generate income relative to the equity (donor funds).

The Yield on Portfolio maps the ability of the organization to generate income from its loan portfolio.

The return on assets ratio rose from 2.64% last quarter to 3.03% this quarter, while the return on equity ratio jumped from 4.89% to 5.80%. Yield on portfolio slipped from 36.03% last quarter to 35.31% showing a negative trend this quarter.

## 3) Efficiency Ratios

| Efficiency Ratios |  |  |  |
| --- | --- | --- | --- |
| Efficiency Ratios | FY to Dec 2005 | FY to March 2006 | FY to June 2006 |
| Administrative Efficiency | 15.80% | 18.67% | 18.96% |
| Operational Efficiency | 20.51% | 23.26% | 23.59% |
| Operational Self sufficiency | 183.46% | 164.98% | 164.60% |
| Financial Self Sufficiency | 110.61% | 112.63% | 114.11% |

The above table illustrates the trend of administrative efficiency, operational efficiency, operational self sufficiency and financial self sufficiency over successive quarters from Oct-Dec 2005 to April-June 2006.

Administrative efficiency, defined as the cost required in maintaining Rs 1 in the market increased from 18.67% last quarter to 18.96% this quarter. Operational efficiency highlights the efficiency of the loan disbursement system and has slightly increased from 23.26% last quarter to 23.59% this quarter.

Operational self-sufficiency measures whether the revenue generated by the program is sufficient to cover its overheads and financial self-sufficiency estimates whether the program would still be sustainable if it is compelled to borrow at market rates. Operational self-sufficiency somewhat remained steady since last quarter dropping only from 164.98% to 164.60%. Financial self-sufficiency increased from 112.63% last quarter to 114.11% this quarter.

## 4) Operational performance

OSS, Yield and Efficiency Ratios

The sustainability ratios show a very consistent trend as compared to previous quarter, OSS stood at 165% [Mar 2006 165%] despite of opening of 11 [March 2006:7] new branches in the quarter.

Income on loans has shown increase of over 9% as compared to previous quarter however 9% lower compared to targeted income. This shortfall is primarily due to summer vacations in branches during the month of June. The overall impact of summer break on income is around 6.4M.

The operating efficiency ratio has slightly gone up by 0.33% as compared to previous quarter; this variation is due to additional costs of 11 new branches and Regional office in Karachi. As on June’06 there were 44 productive branches out of 53.

## 5) Financing Sources:

As of June 2006, the amounts accessed as loan from different sources are as under

| Source | Limit | Interest rate | Loan proceeds | Outstanding as on June 30,2006- Rupees in millions |
| --- | --- | --- | --- | --- |
| PPAF | 1.350M | 6-8% | 100 M | 381 |
| * MCB | 300M | 10% | RF | 0 |
| Grameen | 21.19M | 2% | NIL | 21.19 |
| Acumen | 8.9 M | 6% | NIL | 8.9 |
| Total |  |  |  | 411.09 |

We accessed funds from PPAF as the market interest rate is higher than what PPAF is offering. Among all the loans agreements, only the arrangement with MCB exposes the organization to interest rate risk. All other agreements neither carry interest rate or currency risk.

During the quarter, we finalized our long term financing strategy. The objective of the strategy is to secure adequate funds to fuel the projected growth of reaching half a million clients in 5 years. The intended steps and sources include commercial sources (financial and money market), privately and publicly placed bonds, funds from international agencies and subsidized funds. In line with the strategy, we have been able to secure offers from three commercial banks which are under consideration in consultation with the treasurer.

- 5. Human Resource Management

As a dynamic, sustainable and enterprising organization, the expansion, capacity building and development of its staff represent some of Kashf’s integral policy objectives.

During this quarter HR implemented an extensive exercise of salary mapping for Kashf staff on upgraded compensation and grading structure along with the completion of the annual performance management system. The table below gives a brief on the structure of the Kashf staff and how it compares vis-à-vis the previous quarter

|  | Jan-Mar, 2006 |  | Apr-Jun, 2006 |  | %age Change |  |
| --- | --- | --- | --- | --- | --- | --- |
| Total Permanent Staff | 446 |  | 474 |  | 6.3% |  |
| Total Staff (HO) | 50 |  | 68 |  | 36% |  |
| Total Staff (Field) | 396 |  | 406 |  | 2.5% |  |
| Gender Ratio | Male | Female | Male | Female | Male | Female |
|  | 58% | 42% | 58% | 42% | Same | Same |

The table shows a considerable expansion of staff in the Head Office for better management of existing operations plus researching on product development for further expansion, research on new localities and scaling up operations.

A more detailed overview of the April-June quarter follows:

| Beginning of Period End of Period |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Total Permanent Staff Total Staff (HO) Total Staff (Field) | 447 64 383 |  |  | 474 68 406 |  |
| Gender Ratio | Male |  | Female | Male | Female |
|  | 57% |  | 43% | 58% | 42% |
| Total Trainee Staff Total Trainees (HO) Total Trainees (Field) | 37 8 29 |  |  | 157 3 154 |  |
| Gender Ratio | Male | Female |  | Male | Female |
|  | 78% | 22% |  | 72% | 28% |
| Turn Over (Quarterly) | 12% |  |  | 16% |  |

## Staff Capacity Development

The need of trainings can just not be understated enough and Kashf is committed to providing its employees with trainings which help the latter with personal and technical skills development so as to contribute towards capacity building. These trainings assist staff to innovate and see things in their work environment from a new angle and thus provide with a qualified and skillful staff pool that sustain the organization’s growth rate.

In order to facilitate staff members to enhance their skills set, incorporate more efficient practices and systems and to be able to communicate more effectively, the following trainings were held under the auspices of Kashf:-

| Objective of Training | Location | Trainer Institution | Date | Trainees |
| --- | --- | --- | --- | --- |
| Gender Strategic Review | Islamabad | Shazreh Hussain | May 11-12, 2006 | Nasir, Farzana, and Hafsa, PAs (GESA) |
| Financial Management | Lahore | PIM | May 15-18, 2006 | Noman Shaukat, Jr. Associate Finance |
| National Consultative Workshop | Islamabad | PPAF | May 24-25, 2006 | Shahla Sattar, Assistant Manager Finance |
| Effective Communication Skills | Lahore | PIM | May 29-Aug 3, 2006 | Robina Alvi, Mubashir Hassan and Riffat Anwer, Area Managers, Asim Salim, Ops Analyst, Hassan Ali Zaidi, Ops Associate Noreen Shaukat, Ops Associate, Ahsan Ali Khan, IT Analyst |
| Financial Analysis: Concepts & Techniques | Lahore | PIM | Aug 13-16, 2006 | Waseem Aslam, PA Finance, Kamran Yousaf and Asjid Qureshi ILBMs |
| English Business Program | Lahore | PIM | August 20, 2006 | Sadia Akram, Jr. Associate Admin SanaUllah, Associate Admin Irshad Ahmad, Zeeshan Ahmad, Iqbal |
| Development Course for Managers | Lahore | PIM | Aug 26-Sept 1, 2006 | Shahla Sattar, Assistant Manager Finance |

6. Gender Empowerment & Social Advocacy (GESA)

| Initiative | Key Outcomes |
| --- | --- |
| Leadership | - Module Redesigned after research - 12 sessions conducted in YG and DP - 300 CMs, CSs participated |
| GESA Staffing | - 3 Loan officers selected for Junior Associates position. - Training on going |
| Gender Sensitization training | - 6 Gender workshops conducted - 150 Loan officers sensitized |
| Gender Client Council | - 2 Gender councils set up at Karim Park and Ravi Rayon. - 5 Gender council meetings for each council conducted - Ravi Rayon Gender council has solved the health facilities issue of their Tehsil hospital. Ravi Rayon council arranged community seminar in which Medical Superintendent, 2 lady doctors, Nazim and councilors with 150 people participated - KP GCC has addressed the issue of birth certificate of their children and actively participated to solve this issue - Meetings/correspondence with concerned departments is currently under progress to resolve this issue |
| Theatre | - Chanan theatre group trained for area 1&2 on the theme of Hadood Ordinance - Theatre performances planned and coordinated with branches and groups - Total 21 performances delivered with an out reach of 3675 clients on themes of gender discrimination and Hadood Laws - New theatre group has been identified for LHR |
| Training for the councilors at UC level | - Area-wise database of UCs provided to AOMs, AMs & BMs - 4 Orientation sessions have been conducted for the Union and Tehsil councils |
| Media & Networking | - One staff member was elected as a Co-focal person for Gender Network Lahore - Press reporting for dignitary visit of Ms. Cherie Blair - Press coverage of Kashf’s 3rd phase project with DFID. - Database of the media official for Lahore, Kasur and Faisalabad - Daily “Jang” interview of Kashf Foundation’s President. - Contact person list has been provided to HR coordinator Kashf media products are archived |
| Study Circle | - Concept paper documented - Seminar on Hadood laws organized for all HO staff, AMs and BMs |
| HIV/Aids Sessions | - 5 session were arranged with the collaboration of CWS in which 300 clients got awareness |
| Orientation Session for new LOs | - Provide assistance in session conduction and feedback to improve the quality of sessions |

During April – June 2006, GESA participated enthusiastically in various activities as part of its efforts to effectively disseminate information on a multitude of social issues. The diverse trainings imparted to our employees show our keenness in exposing them to different ideas and innovative methodologies so that they can better themselves. The table below gives further details about the training programmes offered here at Kashf: