Project Budget

| Sl# | Particulars | Unit | Unit Number | Unit Cost | Amount USD | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 01 | Salary for PC | Man Month | 13 | 300 | 3900 | Including Festival incentive |
| 02 | Salary for Field Facilitators | Mon Month | 13 | 150 | 1950 | Including Festival incentive |
| 03 | Assistive Device for disabled persons (Wheel Chair) | No. | 10 | 100 | 1000 |  |
| 04 | Crouches | No | 20 | 5 | 100 |  |
| 05 | Training on ICT | No | 20 | 100 | 2000 |  |
| 07 | Laptop for Disabled youth after training | No | 20 | 400 | 8000 |  |
| 08 | Community Meeting | No | 50 | 10 | 500 |  |
| 09 | Travelling Cost |  |  |  | 200 |  |
| 10 | Reporting Documentation |  |  |  | 100 |  |
| 11 | Project Launching Workshop | No | 01 | 300 | 300 |  |
| Total cost amounting USD Eighteen Thousand and Fifty Only |  |  |  |  | 18050 |  |

Implementation Plan of the project:

| List the activities necessary to produce the results and indicate who is responsible for each activity. (1 year Plan, October,2023-September,2024) |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activities | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| Screening the youth disable in communities |  |  |  |  |  |  |  |  |  |  |  |  |
| Potential Staffs recruiting |  |  |  |  |  |  |  |  |  |  |  |  |
| Staffs Orientation |  |  |  |  |  |  |  |  |  |  |  |  |
| Procurement of materials |  |  |  |  |  |  |  |  |  |  |  |  |
| Project launching workshop with Government and others service providers |  |  |  |  |  |  |  |  |  |  |  |  |
| Sensitization workshop with Government and others service providers |  |  |  |  |  |  |  |  |  |  |  |  |
| Organise vocational training for youths disabled |  |  |  |  |  |  |  |  |  |  |  |  |
| Organise ICT Training for youth Disabled |  |  |  |  |  |  |  |  |  |  |  |  |
| Parents Meetings |  |  |  |  |  |  |  |  |  |  |  |  |
| Reporting |  |  |  |  |  |  |  |  |  |  |  |  |
| Documentation |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitoring |  |  |  |  |  |  |  |  |  |  |  |  |