PROPOSED FOLLOW-UP SUPPORT TO POLICE TRAINING IN CHILD RIGHTS AND CHILD PROTECTION PROJECT

2010-2013

DESCRIPTION OF THE FIRM AND THE FIRM’S QUALIFICATIONS

Founded in 1995, the Consortium for Street Children (CSC) is a British nongovernmental organisation currently made up of 60 member organisations working with street children and children at risk of taking to the streets in 100 countries. The Consortium’s London-based Secretariat coordinates and supports its members to make a difference in the lives of vulnerable children in five key areas: Prevention and Early Intervention; Violence; HIV and AIDS; Education; and Child Participation and Empowerment. The Secretariat implements four programmes: Advocacy, Capacity Building (including a Grants Scheme), Best Practice and Research.

CSC is affiliated with the following:

- UN Economic and Social Council (special consultative status)

- UNICEF’s Better Care Network (the CSC director is also on the advisory board)

- The UK Foreign and Commonwealth Office’s Child Rights Committee (member)

- Founding member of DFID’s Children and Youth Network

- UK Consortium on Aids and International Development (member)

- Coalition of Children Against Aids (CCABA) (member)

- Grow Up Free From Poverty  Coalition (member)

- Keeping Children Safe Coalition (member)

Qualifications:

CSC is well-placed to successfully implement this project. Within the last few years CSC has carried out the following projects and activities relevant to in child rights and child protection:

- Trained 49 trainers from the Ethiopian Police University College (EPUC) in child rights and child protection in 2008, as well as how to investigate child abuse cases, in collaboration with UNICEF.

- Trained 42 mid-level training managers, the majority from the Ethiopian Federal Police, in child rights and child protection and how to investigate child abuse cases.

- Trained 29 street workers from 8 Ethiopian NGOs and 2 police trainers from the EPUC in 2008 on how to improve their work with street children, in collaboration with UNICEF.

- Carried out research on violence and street children worldwide, with the report, State of the World’s Street Children – Violence, launched in 2007 in the UK Parliament and in nine other countries. In Ethiopia the report was launched by the African Child Policy Forum.

- Trained nearly 1,000 Guatemalan police officers (including mid-level grades) in child protection and child rights in Guatemala City and four provinces (2006-2007). The training was carried out in Spanish. Funded by the British Foreign and Commonwealth Office (FCO).

- Trained 15 Guatemalan police instructors in child rights and child protection at the National Civil Police Training Academy in Guatemala City. The training was carried out in Spanish. (2006). Funded by the FCO.

- Adapted the Consortium’s Police Training on Child Rights & Child Protection: Lessons Learned and Manual for the Guatemalan context. This included translating the manual into “Guatemalan” Spanish. (2006)

- Developed the Police Training on Child Rights & Child Protection: Lessons Learned and Manual, which was launched in the UK Parliament in 2006. The manual is based on best practices recommended by police, street children, judges, prosecutors, and social workers in more than 40 countries.

- Co-developed Keeping Children Safe, a child protection training manuals and DVD for international organisations working in developing countries. (2006). The materials were produced by the Steering Committee of the Keeping Children Safe Coalition, which include the Consortium.

- Co-developed the Child Protection Toolkit, along with ChildHope (2006)

- Was a member of the United Nations Secretary General’s Study on Violence Against Children NGO Advisory Panel. This NGO advisory panel was formed to advise on all aspects of the establishment of the Study, provide the independent expert and study secretariat with input on the study's content, process and outcomes, encourage and facilitate broad and effective NGO involvement in the study, and help mobilize effective follow-up to the study. (2005)

- Researched juvenile justice and street children in more than 40 countries to identify best practices. The findings were published in a book entitled An Outside Chance: Street Children and Juvenile Justice – An International Perspective (2004). The report was cited by the UN’s World Report on Violence Against Children. Intensive research was carried out and separate reports were published by the Consortium on juvenile justice in:

  - Kenya,

  - Pakistan,

  - Romania,

  - the Philippines,

  - Nicaragua, and

  - Nigeria.

- Organised regional conferences with UNICEF on “Promoting and Protecting the Rights of Street Children.” Each Forum analysed juvenile justice and police-street children relations and came up with important recommendations. One of the forums was: “A Civil Society Forum for East and Southern Africa on Promoting and Protecting the Rights of Street Children,” 11 – 13 February, 2002 – Nairobi, Kenya. Ethiopia sent six delegates from the following organisations: Forum on Street Children (FSCE); Love for Children; Marry Joy (Aid Through Development); ANPPCAN Ethiopia; PACT-Ethiopia; and Children Aid Ethiopia.

UNDERSTANDING OF THE REQUIREMENTS FOR SERVICES, INCLUDING ASSUMPTIONS

In its response to Ethiopia’s third periodic report (2006) on its implementation of the UN Convention on the Rights of the Child, the Committee on the Rights of the Child (CRC) expressed its deep concern at the increasing number of street children, especially in major urban centres, who are also victims of drug abuse, sexual exploitation, harassment and victimization by members of the police force. Furthermore, the Committee is concerned at the stigmatization of street children and negative attitudes in society towards them based upon their social condition.” In examining juvenile justice in Ethiopia, the Committee recommended to “Improve training programmes on relevant international standards for all professionals involved with the system of juvenile justice.”

In 2008 the Consortium for Street Children, a London-based NGO, and UNICEF entered into a Special Service Agreement (institutional contractor) to train police trainers of the Ethiopian Police University College (EPUC) in child rights and child protection, as well as how to carry out child abuse investigations. The project was implemented in partnership with the Ethiopian Police University College (EPUC). As a result, a child rights/protection training of trainers’ manual was produced in Amharic and 49 police trainers were trained over a two-week period. In turn, they are expected to train 36,000 police officers over the next three years. The course also included practical tips on how to improve training skills.

In 2009 a child rights/protection training of trainers manual for mid-level Federal Police managers was produced and 42 mid-level managers (the majority of whom were from the Federal Police) were trained. In addition, in 2009 a manual on how to investigate child abuse cases was produced and the same 42 mid-level managers were trained.

The course was based on research CSC carried out around the world on the juvenile justice system, with a special focus on street children. The research culminated in the publication in 2004 of a book, An Outside Chance: Street Children and Juvenile Justice – An International Perspective. The research focuses on a systems approach to improving child rights and child protection within juvenile justice. CSC subsequently published a Police Training on Child Rights & Child Protection: Lessons Learned and Manual, which is based on the systemic approach. The UNICEF-funded training of Ethiopian police trainers project was based on this approach, along with valuable insights into the Ethiopian context provided by the project’s local consultant, Tsegaye Deda. The systemic approach to juvenile justice views the police as one of seven key, inter-related actors: police, judges, prosecutors, public defenders, detention officials, social workers, and community.

The overall goal of the project as it related to child rights and child protection was to reduce the incidents of harassment and victimization of street children by police through changing the attitudes and behaviour of the police toward street children.  The first step was to accomplish this with the police trainers. This was successfully carried out, judging from the participants’ positive written and oral comments at the end of the training.

However, the police trainers stated that, without further support, they expected a positive behaviour change in no more than 10% of the 36,000 police to be trained over the next three years. In order to have a greater impact, workshop participants made recommendations for additional technical assistance in two areas: (i) support for police trainers, and (ii) support for the police in general to help them change their behaviour toward street and other vulnerable children.

Among their recommendations were:

- Developing/implementing a baseline survey of street children regarding police behavior toward them and then carrying out periodic surveys to monitor impact of police training;

- Facilitating a three-day workshop for mid-level and senior-level police officials on managing

- Creating posters and brochures promoting child rights and child protection;

- Delivering a 3-day follow-up workshop for the 49 police trainers who participated in the 2008 training to assess progress and jointly address challenges, also to deliver additional training on how to work with street children;

- Holding quarterly meetings of police with street children, NGOs, community, and other key stakeholders (including judges, prosecutors, etc.)

- Creating manuals and guidelines on how to increase public awareness about the protection and assistance of street children;

- Creating an NGO directory of available services/resources so police can make referrals. This directory needs to created for each region.

- Training and manuals on how to design/implement child protection projects;

- Training on how to work in partnership with NGOs, street children and the community;

- Training on how to handle street children;

- Training on how to deal with domestic violence which participants identified as a major push factor causing children to run away from home.

- Training and practical tools to affect behaviour change;

- Creating an action plan together with all the key stakeholders in the juvenile justice system, including street children, to reduce police violence against street children.

PROPOSED APPROACH, METHODOLOGY, TIMING AND OUTPUTS

The proposed three-year project will make a significant contribution to the Ethiopian Government’s reform of the criminal justice system.

The project will be firmly grounded in the UN Convention on the Rights of the Child and take place within a framework of a number of positive developments in Ethiopia, as reported by the Committee on the Rights of the Child (1 November 2006). Among them are:

- The provisions in the New Criminal Code of 2005 which criminalize harmful traditional practices and most forms of human trafficking;

- The provision in the Revised Family Code setting 18 years of age for marrying for both girls and boys;

- The adoption of a National Plan of Action for Children (2003-2010)

- The ratification of the Convention of the International Labour Organization No. 29 concerning Forced or Compulsory Labour and No.182 concerning the Prohibition and Immediate Action for the Elimination of the Worst Forms of Child Labour, both on 2 September 2003;

- The African Charter on the Rights and Welfare of the African Child on 2 October 2002.

The project focuses on (i) promoting a standardised approach throughout the juvenile justice system to child rights/protection and investigating child abuse; (ii) strengthening the management support system within the Ethiopian Federal Police that promotes child rights/protection both in the field and at the Ethiopian Police University College (EPUC); (iii) building police/community partnerships for child rights/protection; and  (iv) creating child rights/protection resource materials for police trainers and officers in the field; (v) facilitating a national street children strategy.

This systemic approach will be implemented through a partnership that includes UNICEF Ethiopia, the Ethiopian Federal Police and the Justice Organs Professional Training Centre. Key elements of the proposed project have already been discussed with representatives of the three organisations and there is agreement on the project framework outlined in this document.

The Project Purpose/Impact

The specific purpose of the project is to support the Ethiopian Federal Police’s transformation into a law enforcement agency that routinely respects and promotes the rights of all children and proactively protects vulnerable children from abuse and neglect.

Over a three-year period the project will have the following impact:

- The number of child abuse cases prosecuted successfully increases 60% nationally by the end of Year 3 of the project.

- Reported cases of physical and psychological abuse by police as reported by street children decreases at least 40% nationally by the end of Year 3 of the project.

- Number of children in conflict with the law who are diverted from the criminal justice system increases at least 30% nationally by the end of Year 3 of the project.

The project will achieve its purpose by:

- Enhancing the abilities of police officers in nine regions to investigate child abuse cases by using the most up-to-date procedures available;

- Facilitating a national street children strategy;

- Strengthening police management practices and structures so that they better promote and support child rights/protection training and implementation by officers in the field;

- Piloting police/community child rights/protection partnership projects centred on existing CPUs in four regions;

- Developing and implementing a child rights/protection police training monitoring and evaluation system;

- Enhancing the abilities of juvenile justice stakeholders in nine regions to cooperate in promoting child rights/protection;

- Enhancing the effectiveness of police trainers and officers in the field by making available child rights/protection resource materials;

- Enhancing the skills of two, full-time child rights/protection training consultants.

This will be achieved by:

- Creating a child abuse intelligence gathering model;

- Facilitating courses on gathering, identifying and utilising intelligence to prevent child abuse and arrest and prosecute and convict offenders;

- Facilitating courses on evidence gathering and presentation in child abuse cases;

- Facilitating child rights/protection collaboration courses for juvenile justice stakeholders;

- Carrying out a national street children survey, which includes information on police/street children relationships;

- Gathering and analysing statistics on children in conflict and child abuse arrests, prosecution and convictions;

- Facilitating a national street children strategy;

- Assessing police management practices and structures that support child rights/protection;

- Developing and implementing an action plan to strengthen police management practices and structures;

- Provide technical assistance in implementing the action plan;

- Strengthen four CPUs to design, implement and monitor and evaluate community-based child rights/protection projects;

- Designing and publishing child rights/protection resource materials for police trainers and officers in the field;

- Developing a transfer of knowledge, skills and abilities programme for two local consultants;

- Developing trainers’ manual and training guidelines and aids (for both child protection and child abuse investigation)

- Establishing a mutually supportive partnership between the police and local NGOs working with children in conflict with the law

- Establishing post-project, web-based support to the Ethiopian Police by linkages with law enforcement officers in other parts of the world who are applying best practices in their dealings with children conflict with the law. Such linkages can take the form of mentors, accessing toolkits, manuals, answering questions and concerns by e-mail, among others.

The measurable impact will result through the achievement of the following key outputs:

1.0:  The most up-to-date methods of investigating child abuse cases are adapted by the Federal Police throughout the country.

2.0: A national street children strategy is adopted by the Ethiopian Government.

3.0: Federal Police management practices and structures that promote child rights and protection are assessed and strengthened at central and regional levels.

4.0: Police/community partnership projects centred on existing CPUs are piloted in four regions of the country.

5.0: A child rights/protection training monitoring and evaluation system is designed and implemented.

6.0: Child rights/protection courses for criminal justice stakeholders are facilitated in all regions.

7.0: Child rights/protection materials for trainers and officers in the field are designed and produced.

The objectively verifiable indicators for the outputs are as follows:

| 1.0: | Child abuse investigation processes outlined in the training course are used regularly by officers throughout the country by the end of Year 2 of the project. At least 225 criminal justice stakeholders in 9 regions have been trained in child abuse investigation by the end of Year 3. |
| --- | --- |
| 2.0: | The strategy is officially adopted by the Ethiopian Government and the appropriate ministry is charged with implementing it by the middle of Year 2. |
| 3.0: | An organisational assessment is designed and carried out at national police hq, the 2 police training centres in Addis Ababa and the training centres in 8 regions to identify the management driving and restraining forces for supporting training in child rights/protection by the end of Year 1; A consolidated report with recommendations is prepared for the director of the Federal Police is prepared by the end of Year 1; The director of the Federal Police issues a directive strengthening management structures based on the consolidated report by the end of Year 1 of the project. |
| 4.0: | Police/community partnerships established in 4 regions of Ethiopia by the end of the project’s 1st year; 4 communities recognise their local CPUs as leaders in promoting child rights/protection by the end of the project’s 2nd year. 4 pilot community child rights/protection projects have been successfully completed by the end of the project’s 3rd year; |
| 5.0: | EPUC institutionalises the M&E system in all 9 regions by the end of Year 2; The following baseline information is gathered and analysed b y the end of the project’s 1st year: Survey of police/street children relationships in each of the 9 regions; Annual statistics re children in conflict with the law in each of the 9 regions; Annual statistics re child abuse cases successfully prosecuted in each of the 9 regions. Annual statistics re number of police officers trained in child rights/protection. Annual statistics re number of police officers trained in how to investigate child abuse cases |
| 6.0: | At least 90 police trainers/managers are interviewed in all 9 regions to assess progress by the end of Year 2; Mentoring & individual training is offered on-site to 90 police trainers/managers to address challenges in each of the 9 regions by the end of the project’s 3rd year; At least 225 police trainers, judges, prosecutors, staff from local NGOs and other key stakeholders from the criminal justice system are trained in child rights/protection by the end of the project’s 3rd year. |
| 7.0: | A national poster design contest re child rights is organised by police for children over a 3-month period, with the winner receiving a cash prize by the end of Year 1; 10,000 copies of the winning poster are printed in local languages and distributed within each of the 9 regions by the end of Year 1; A brochure promoting child rights/protection is designed for police, translated from English into major local languages and distributed on CDs to police in each of the 9 regions by the end of Year 1; 10,000 brochures promoting child rights/protection are printed from the CDs in each of the 9 regions by the end of Year 1; 5,000 copies of child rights/child protection field manuals for officers are printed by the end of Year 1; 5,000 copies of child rights/child protection resource directories are printed by the end of Year 1. |

To carry out this project, the following personnel will be needed: a project coordinator/lead trainer; a project liaison officer; a child abuse investigation consultant; an organisation development consultant; and two local training consultants; interpreters for the training workshops; office space (ideally within the EPC or UNICEF); access to a computer; access to a printer; access to Internet; training rooms (ideally at the EPUC centres); and training materials (flipcharts, markers, flipchart stand, masking tape, screen for DVD showings).

Key Assumptions:

In designing and implementing this project with UNICEF and the Ethiopian Police, CSC would take into consideration a number of key assumptions and lessons learned, based on its extensive research of children in conflict with the law in numerous countries and its practical experience in delivering police training in child rights and child protection in Guatemala:

- That child rights and child protection are a Federal Police priority;

- That Federal Police leadership is committed to improving management practices that promote and protect the rights of children;

- That UNICEF will pay the costs of the workshops (local transportation and accommodation of participants; meals and snacks; materials such as markers, flipchart papers, masking tape, etc.; and photocopying);

- That UNICEF will pay the costs of translation of documents, manuals and other printed material;

- That police training is only one part of an overall, holistic strategy which is needed to improve police attitudes and practice in relation to child rights and child protection. Other elements may include:

- Training of other actors in the juvenile justice system (lawyers, judges, prosecutors, defenders, social workers, probation officers, detention centre staff, etc.)

- Lobbying to bring national legislation in line with international standards

- Advocacy to ensure child rights and child protection practices are officially incorporated into police – and other professions’ – initial and in-service training curricula to ensure that training is replicable, sustainable and consistent

- Advocacy and awareness raising among police station commanders to ensure sustainability of, and support for, skills learned during training

- Advocacy for monitoring to ensure that standards are being implemented in practice

- Advocacy with local and national governments to allocate adequate resources to the establishment, training and functioning of specialised child protection units in the police

- Lobbying for a better gender balance in police recruitment

- That each child a police officer encounters – either as victim or perpetrator -- is unique and requires an individualised approach;

- That police interventions should take into count the concept of choices, limited choices, and non-choices available to children;

- That the role of the community is essential in police work;

- That there needs to be a better understanding of, and respect for, children’s resiliency and their peer relationships.

- That when an organisation’s staff increase their knowledge and improve their skills and abilities (KSAs) -- human resource development -- changes may need to be made in other parts of the organisation’s subsystems (e.g., management, information technology, etc.) in order to sustain the new KSAs.

- That in order for police to sustain their new knowledge, skills and attitudes, they will need post-training cooperation from local, child rights-focused nongovernmental organisations (NGOs)

- That a transfer of knowledge, skills and abilities in a project such as this is a two-way street, and that expatriate project staff will also be expected to learn from their Ethiopian counterparts.

- That the key principles of child protection in Save the Children’s draft “Training Manual on Child Protection” are similar to those in Keeping Children Safe: A Toolkit for Child Protection, which was developed by 11 international organisations, including Save the Children and the Consortium for Street Children (UK). This means that the manual is firmly grounded in the UN Convention on the Rights of the Child.

Project Monitoring & Evaluation

Monitoring and evaluation are key inputs for the proper implementation of any project. It is, therefore, necessary that the activities of this project be monitored and evaluated at various levels. The following table lays out what will be monitored.

| Areas | Thrust | Methods and Tools | Responsible |
| --- | --- | --- | --- |
| Implementation processes and intermediate outputs and outcomes | Monitoring would focus on answering four basic questions: 1. Are planned project activities being implemented on schedule and within budget? 2. What (if any) is causing delays or unexpected results: 3. Are there any changes happening that would revise/modify original plans? 4. Are the interventions relevant/appropriate to the trainees? | Expenditure tracking Service delivery assessments Feedback surveys | Consortium Administrator in co-operation with: Project Coordinator Project Liaison Officer |
| Outcomes and Impacts | Tracking changes in knowledge, skills, abilities and attitudes of trainees and to make adaptations based on findings. | Participatory Monitoring and Evaluation (PME) Pre and post training surveys | CSC, involving all key stakeholders |

To ensure that the project’s impact is measurable, the following baseline information will be gathered at the beginning of the project:

- Survey of police/street children relationships in each of the 9 regions;

- Annual statistics re children in conflict with the law in each of the 9 regions;

- Annual statistics re child abuse cases successfully prosecuted in each of the 9 regions.

- Annual statistics re number of police officers trained in child rights/protection.

- Annual statistics re number of police officers trained in how to investigate child abuse cases

The information will be gathered again and analysed at the end of Year 2 and Year 3 of the project.

A mid-term evaluation will be carried out in month 18 by an external evaluator. The final evaluation will also be carried out by an external evaluator toward the end of the 36-month project.

Training Monitoring and Evaluation

In addition to the monitoring and evaluation of the entire project, the training itself needs to specifically monitored and evaluated. This will be done as follows:

Monitoring of Training Courses

- Trainers meet together with representatives of the participants at the end of each session/day to discuss and to document how the sessions went, which activities were especially successful or unsuccessful, what changes can be made to materials, presentation style, what needs to be revised, etc.

- Participants draw a large happy face on one side of a piece of paper/card and an unhappy face on the other. At certain times during the session, the facilitator encourages the participants to hold up their pieces of paper to indicate whether or not they are happy with an activity/whether or not they have understood a presentation. This can be adapted in many ways. This would be presented as a fun feedback.

- Brief surveys of participants are carried out at the beginning of each course and repeated at the end to measure knowledge acquired and skills and abilities gained.

Evaluation of Training Course

- (Informal Approach) Trainers facilitate verbal feedback at the end of the training course relating to the specific topics covered, the materials and approaches used, the facilitation style, the balance between presentation of information and practical sessions, etc. The numbers of participants in agreement with specific perspectives can be assessed and recorded.

- (Formal Approach) In addition – or alternately – to the informal evaluation, a training evaluation questionnaire can be completed by all participants individually at the beginning of the course and again at the end of the course. They can remain anonymous to encourage participants to freely express their views.

INITIAL DRAFT WORKPLAN

| Tasks | Responsible | Time-Frame YR MONTH | Methodology | Outputs | M/E |
| --- | --- | --- | --- | --- | --- |
| Project Start-Up | Project Coordinator/ UNICEF Ethiopia | 1 | 1 | Meeting; Sign Contract | Contract signed; team established; | Contract |
| Gather baseline information | Project Liaison Officer | 1 | 1-6 | Surveys; statistical analysis | 27 persons trained; Baseline information gathered | Reports |
| Hold press conference re survey/stats results | EPUC | 1 | 7 | Press conference | Media coverage | News reports |
| Write training manuals | Project Coordinator | 1 | 2-12 | Design/write modules | 9 training manuals written | Written manuals |
| Translate manuals | EPUC | 1 | 3-12 | Translate | 9 training manuals translated | Translat-ed manuals |
| Design training M&E system | Local Consultant | 1 | 2 | Write a document | Written M&E system | Docu-ment |
| Design/write child rights/protection resource materials | Project Liaison Officer | 1 | 2-12 | Design/printing/poster contest | Child rights poster; child protection poster; brochure for police; resource directory; field manual | Printed/published materials |
| Create intelligence gathering model | Child Abuse Investigation Consultant | 1 | 2 | Write a document | Written model | Docu-ment |
| Translate model | EPUC | 1 | 3 | Translate | Written translation | Docu-ment |
| Facilitate intelligence gathering course in 9 regions | Child Abuse Investigation Consultant | 1 | 4-6 | Training workshop | 135 police officers trained | Work-shop evalua-tions |
| Facilitate pilot project #1,2,3,4 workshop 1 | Project Coordinator | 1 | 4-5 | Training workshop | 100 police and community stakeholders trained in participatory learning and action | Work-shop evalua-tions |
| Assess police management practices/structures in 9 regions | Organisation Development Consultant | 1 | 4-6 | Participatory assessments | Written assessment of Federal Police hq; 2 EPUC training centres in Addis and 8 regional training centres | Report |
| Facilitate evidence gathering course in 9 regions | Child Abuse Investigation Consultant | 1 | 10-12 | Training workshop | 135 police officers trained | Work-shop evalua-tions |
| Facilitate pilot project #1,2,3,4 workshop 2 | Project Coordinator | 1 | 8-9 | Training workshop | 100 police and community stakeholders trained in participatory learning and action | Work-shop evalua-tions |
| Facilitate pilot project #1,2,3,4 workshop 3 | Project Coordinator | 3 | 1 | Training workshop | 100 police and community stakeholders trained in participatory learning and action | Work-shop evalua-tions |
| Design OD action plan | Organisation Development Consultant | 1 | 9 | Write plan | Written plan | Docu-ment |
| Facilitate a child abuse investigation course for stakeholders in 9 regions | Child Abuse Investigation Consultant | 2 | 3 | Training workshop | 135 stakeholders trained | Work- shop evalua-tions |
| Provide OD technical assistance | Organisation Development Consultant | 2-3 | 1-12 | On-site support as well as online | Improved procedures/structures | Reports |
| Facilitate a child rights/protection course for stakeholders in 9 regions | Project Coordinator | 2 | 3-4 | Training workshop | 135 stakeholders trained | Work-shop evlua- tions |
| Repeat surveys and gather stats. | Project Liaison Officer | 2 | 2 | Surveys; statistical analysis | Information gathered | Reports |
| Facilitate street children strategy conference | Project Coordinator | 3 | 1 | Large group facilitation (200 participants) | National strategy for street children | Written strategy |
| Provide conference follow-up technical assistance | Project Coordinator | 3 | 1-12 | Review of draft strategy. | Written advice for improving strategy. | Emails; docu-ment |
| Facilitate pilot project 1,2,3,4 workshop 4-5-6 | Project Coordinator | 3 | 5 | Training workshops | 100 stakeholders trained in project cycle | Work- shop evalua-tions |
| Pilot project press conference | Project Liaison Officer | 2 | 5 | Press conference | Media coverage | News reports |
| Monitor and evaluate OD action plan implementation | Organisation Development Consultant | 2-3 | 1-12 | Emails; document reviews; onsite consultation | Improved manage-ment procedures/structures | Reports |
| Implement pilot projects 1,2,3,4 | Project Coordinator | 3 | 5--( | Community based activities | Child rights/protection projects implemented locally | Reports |
| Mid-Term Project Evaluation | External Evaluator | 2 | 6 | Onsite visits/inter-views/review of documents | Written evaluation | Report |
| Repeat surveys and gather stats. | Project Liaison Officer | 3 | 10 | Surveys; statistical analysis | Information gathered | Reports |
| End of project evaluation | External evaluator | 3 | 11 | Onsite visits/inter-views/review of documents | Written evaluation | Report |

PROPOSED TEAM STRUCTURE

| Function | Name | Nationality | UK/Ethiopia | Work Tasks | Full Time (FT)/Part Time (PT) |
| --- | --- | --- | --- | --- | --- |
| Project Coordinator/Lead Trainer | Alexander Dressler | German | UK | Supervise project; write manuals;facilitate workshops; facilitate large group conference | PT |
| Project Liaison Officer | Patrick Shanahan | British | Ethiopia | Liaise with UNICEF, Ethiopia staff and UK staff; supervise surveys; press conferences | PT |
| Local Training Consultant |  | Ethiopian | Ethiopia | Develop training M&E system; support training workshops. | PT |
| Local Police Consultant | TBA | Ethiopian | Ethiopia | Support logistics; training workshops; liaise with police leadership | PT |
| Child Abuse Investigation Consultant | Alison McCausland | British | UK | Write manuals; facilitate workshops; develop intelligence gathering model; support pilot projects |  |
| Organisation Development Consultant | Samir Sharma | British | UK | Assess police management procedures/ Structures re child rights and protection/provide technical assistance. | PT |

Organogram

Pro

BUDGET

PERSONNEL:

Project Coordinator/Lead Trainer

$800/day x 239 days = 								$191,200

Project Liaison Officer

$800/day x 120 days =								  $96,000

Child Abuse Investigation Consultant

$800/day x 162 days = 							            $129,600

Organisation Development Consultant

$800/day x 72 days = 									  $57,600

Local Training Consultant

$200/day x 185 days =								  $37,000

Local Police Consultant

$200/day x 72 days = 									  $14,400

Surveys and Statistical Analysis Consultant

$500/day x 45 days = 									  $22,500

Local Pilot Project Managers

$100/month x 4 managers x 36 months = 						  $14,400

TOTAL PERSONNEL								$371,091

INTERNATIONAL TRAVEL/ACCOMMODATION

20 flights @ $1,000 ea. =								  $20,000

451 days accommodation @ $96/day =                                            		  $43,296

TOTAL INTERNATIONAL TRAVEL/ACCOMMODATION			              $63,296

LOCAL TRANSPORTATION							  $20,600

POLICE/COMMUNITY PILOT PROJECTS

$20,000/ project x 4 projects =							  $80,000

TOTAL POLICE/COMMUNITY PILOT PROJECTS				              $80,000

TRAINING WORKSHOPS							               N/A

NATIONAL STREET CHILDREN CONFERENCE

4-day conference for 200 participants =						   $36,000

TOTAL NATIONAL STREET CHILDREN CONFERENCE			               $36,000

PUBLICATIONS									   $40,000

10,000 child rights/protection posters

10,000 child rights brochures

5,000 child rights/protection field manuals

5,000 child rights/protection resource directories

TOTAL PUBLICATIONS								   $40,000

SUBTOTAL										$610,987

5% Administrative Cost								  $30,549

D

# Footnotes

Responsibilities include overall project coordination, writing training manuals, writing police field manual, writing police resource manual, facilitating training workshops, and facilitating the national street children conference

Includes hotel room @ $75/day and two meals per day

Includes flights within Ethiopia and car/driver charges

It is assumed that UNICEF Ethiopia will pay per diems, accommodation, and transportations costs for workshop participants as was done with similar workshops in 2008-2009. It is also assumed that EPUC will provide the venues in Addis Ababa and in the regions

The figure includes transportation and accommodation and venue costs in Addis Ababa for approximately 200 participants

Ideally, every field officer should have a copy of a field manual and child rights resource directory. But this may not be practical because of costs. Further discussions should be held regarding this.

# Text boxes

EPUC

Ethiopia

Justice Training Centre

Ethiopia

Project Liaison Officer

Ethiopia

Project Coordinator

UK

Training Consultant #1

Ethiopia

Police Consultant #2

Ethiopia

End of Project External Evaluator

Child Abuse Investigation Consultant

UK

Organisation Development Consultant

UK

Mid-Term External Evaluator

UNICEF Ethiopia