2025–2026 ANNUAL REPORT

Scholarship and Nutrition Program for Orphans in Uganda

Prepared by Hands of Empowerment Uganda

Reporting Period: January 2025 – January 2026

Date: January 2026

KEY PROGRAM HIGHLIGHTS (AT A GLANCE)

- 100 orphans & vulnerable children supported

- 3 partner schools receiving daily meals

- 35% increase in school attendance

- 60% reduction in malnutrition

- 2% dropout rate

- USD 300 average cost per child per year

1. EXECUTIVE SUMMARY

During the 2025–2026 reporting period, Hands of Empowerment Uganda made significant progress in expanding access to education and improving nutrition outcomes for orphans and vulnerable children (OVCs) in rural and peri-urban Uganda.

Program Focus:

Education access + daily nutrition + community engagement

A total of 100 OVCs received comprehensive scholarship support, while a daily school feeding program was implemented across three partner schools. These interventions resulted in measurable gains in attendance, academic performance, and child health.

Results Snapshot

Attendance increased by 35%

Dropout rates reduced to 2%

Malnutrition reduced by 60%

Despite funding and logistical challenges, the program demonstrated strong resilience and effectiveness, reinforcing the value of integrated education and nutrition interventions.

2. PROGRAM OVERVIEW

Background

In underserved communities across Uganda, poverty and food insecurity remain major barriers to education—particularly for orphans. Malnutrition contributes to low concentration, frequent absenteeism, and poor academic outcomes.

Hands of Empowerment Uganda addresses these challenges through a holistic, child-centered approach that ensures children are enrolled, nourished, protected, and supported to succeed in school.

Program Objectives (2025–2026)

✔ Provide scholarships to 100 OVCs

✔ Deliver daily nutritious meals in partner schools

✔ Strengthen parental and community participation

Monitor child health and reduce malnutrition

3. PROGRAM ACTIVITIES

🎓 Scholarship Support

Component	Description

Beneficiaries	100 OVCs (gender-balanced)

Support	School fees, uniforms, books, pens

Coverage	Rural communities & Jinja ghetto areas

Outcome: Reduced financial pressure on households and consistent school attendance.

School Nutrition Program

Area	Achievements

Daily Meals	Balanced meals (grains, vegetables, proteins)

Schools Supported	3 partner schools

Health Outcomes	90% achieved healthier BMI levels

Parent Engagement	Nutrition & child-care workshops

Teacher Feedback: Improved energy, focus, and classroom participation.

4. IMPACT AND OUTCOMES

Educational Impact

Indicator	Result

Attendance	⬆️ 35%

Dropout Rate	⬇️ 2%

Improved Grades	65% of learners

Excellence Awards	5 students

Secondary School Referrals	2 students

Nutritional & Health Impact

Indicator	Result

Malnutrition	⬇️ 60%

Immunity	Improved

Absenteeism	Reduced

Classroom Engagement	Increased

Parents reported children were more energetic, confident, and eager to attend school.

5. CHALLENGES FACED & MITIGATION

Challenge	Mitigation Strategy

Funding gaps	Strengthened donor outreach

Poor roads	Improved logistics planning

Low parent participation	Flexible meeting schedules

6. MONITORING, EVALUATION & ACCOUNTABILITY

Data Collection Tools

School attendance registers

Academic performance records

Health screenings (BMI & wellness)

Teacher & parent feedback

Evaluation Frequency: Quarterly

Purpose: Measure progress, improve quality, ensure accountability

7. SAFEGUARDING, GENDER & CHILD PROTECTION

Our Commitment

Gender equity in beneficiary selection

Child protection & zero tolerance for abuse

Safe school environments

All activities uphold the dignity, safety, and best interests of every child.

8. FINANCIAL OVERVIEW & COST EFFICIENCY

Budget Allocation (Approx.)

Category	Percentage

Education Support	55%

School Feeding	35%

Admin & Monitoring	10%

Average Cost per Child: USD 300 per year

Covers full education + daily meals

9. FUTURE PLANS (2026–2027)

Expansion Goals

Increase beneficiaries to 120 OVCs

Support a 4th school

Introduce income-generating activities

Strengthen donor & community partnerships

10. DONOR ENGAGEMENT & SUPPORT OPPORTUNITIES

How Donors Can Help

Sponsor a child’s education & meals

Support school feeding expansion

Invest in long-term sustainability

Every USD 300 transforms one child’s year.

CONCLUSION

The 2025–2026 program year demonstrates that combining education and nutrition creates lasting impact. With improved attendance, health, and academic performance, the Scholarship and Nutrition Program continues to change lives and strengthen communities.

Continued partnership is essential to sustaining and expanding this impact.

Prepared by:

Gizaza   Davis

Director, Hands of Empowerment Uganda

📧 handsofempowermentu@gmail.com

📞 +256 781 401 868 / +256 783 520 269

📄 ANNEX: ONE-PAGE DONOR EXECUTIVE SUMMARY

Beneficiaries: 100 OVCs | Schools: 3

Key Results:

✔ 35% attendance increase

✔ 60% malnutrition reduction

✔ 2% dropout rate

Cost: USD 300 per child/year

Next Target: 120 children, 4 schools

2025–2026 REPORT

Scholarship and Nutrition Program for Orphans in Uganda

Prepared by Hands of Empowerment Uganda

Date: January 2026

1. EXECUTIVE SUMMARY

The 2025–2026 reporting period marked another year of solid progress for the Scholarship and Nutrition Program for orphans in rural Uganda. Building on achievements from previous years, the program expanded its reach, strengthened community partnerships, and deepened its impact on children’s education and nutrition.

A total of 100 orphans and vulnerable children (OVCs) continued to benefit from scholarships, while the school feeding program supported three partner schools, ensuring daily nutritious meals. Improvements were recorded in school attendance, academic performance, and overall child health.

Despite challenges—particularly limited funding and logistical barriers—the program demonstrated resilience and delivered measurable outcomes that continue to transform lives.

2. PROGRAM OVERVIEW

Background

Many children in rural Uganda face barriers to education due to poverty, lack of school materials, and food insecurity. Malnutrition contributes to poor academic performance and developmental delays. Hands of Empowerment Uganda aims to address these challenges through an integrated approach combining scholarships, nutrition support, and community engagement.

Program Objectives (2025–2026)

- Provide scholarships for 100 OVCs, covering tuition, uniforms, and scholastic materials.

- Deliver daily nutritious meals across three schools to improve child health and learning outcomes.

- Strengthen parent and community involvement in child welfare and education.

- Monitor child health indicators and reduce malnutrition rates in targeted areas.

3. PROGRAM ACTIVITIES

Scholarship Distribution

- Beneficiaries: 100 children continued receiving scholarships, maintaining gender balance and inclusive access.

- Support Provided: Fees, uniforms, books, pens, and essential learning materials.

- Geographic Reach: Expanded support to additional vulnerable communities, including Ghetto areas in Jinja.

Nutrition Program

- Daily Meals: Children received balanced meals including grains, vegetables, and proteins.

- Expansion: The feeding program reached an additional school, now totaling three supported schools.

- Health Monitoring: 90% of children recorded healthier BMI levels and improved physical wellbeing.

- Parental Engagement: Workshops were conducted to empower parents to support child nutrition and education.

4. IMPACT AND OUTCOMES

Educational Impact

- Attendance improved significantly, rising by 35%.

- Dropout Rates reduced to 2%.

- Academic Performance: 65% of children recorded improved grades; five recognized for excellence; two recommended for secondary school scholarships.

Nutritional Impact

- 60% reduction in malnutrition cases across partner schools.

- Children showed higher energy levels and improved immunity.

- Teachers and parents reported increased concentration and participation.

5. CHALLENGES FACED

- Funding limitations restricting expansion.

- Logistical barriers caused by poor road infrastructure.

- Low parental participation due to economic constraints.

6. FUTURE PLANS (2026–2027)

- Expand beneficiaries to 120 OVCs.

- Extend nutrition support to a fourth school.

- Introduce income-generating initiatives for program sustainability.

- Strengthen partnerships with donors and increase community outreach.

CONCLUSION

The Scholarship and Nutrition Program continues to make a meaningful impact in the lives of orphans in rural Uganda. Improvements in education, nutrition, and community involvement demonstrate the program’s effectiveness and the transformative power of donor support. Continued investment and partnerships remain crucial to sustaining and expanding this work.

Prepared by:

Gizaza Davis

Director, Hands of Empowerment Uganda

Email: handsofempowermentu@gmail.com

Tel: +256 781 401 868 / +256 755518113