Monthly Project Report

Project Title: Educate 200 Street Children in South Sudan
Project Number: 66959
Country: South Sudan
Project Location: Juba City (Central Equatoria State)
Target Group: 200 Street-Connected Children (Boys & Girls, 6–17 years)
Implementing Organization: Trust Guarantee Community Development Aid (TGCDA)

1. Executive Summary

The “Educate 200 Street Children in South Sudan” project aimed to improve access to education and child protection services for vulnerable street-connected children in Juba City. The project provided accelerated learning, psychosocial support, school materials, and reintegration services to 200 children, enabling them to enroll in formal schools and vocational training programs.

Despite operating in a fragile humanitarian context characterized by poverty, displacement, and insecurity, the project successfully restored hope, dignity, and learning opportunities for highly marginalized children.

2. Background and Problem Statement

South Sudan continues to face one of the world’s worst humanitarian crises. Prolonged conflict, economic collapse, and food insecurity have forced thousands of children onto the streets, exposing them to:

- Child labor and exploitation

- Violence and abuse

- Substance use

- School dropouts and illiteracy

Street-connected children are largely excluded from formal education systems and lack family support, putting them at extreme risk of lifelong poverty.

This project was designed to break the cycle of exclusion by providing structured education and reintegration pathways.

3. Project Objectives

Overall Goal

To improve access to education and protection for street-connected children in South Sudan.

Specific Objectives

- Enroll 200 street children into formal or accelerated education programs.

- Provide learning materials and school support kits.

- Deliver psychosocial support and life skills training.

- Facilitate family tracing and reintegration where possible.

- Strengthen child protection awareness among caregivers and communities.

4. Key Activities Implemented

| Activity | Description |
| --- | --- |
| Identification & Registration | Mapping and profiling of 200 street children |
| Accelerated Learning Classes | Literacy & numeracy bridging courses |
| School Enrolment | Placement into public and community schools |
| Learning Kits Distribution | Uniforms, bags, books, pens |
| Psychosocial Support | Counseling and group therapy |
| Life Skills Training | Hygiene, communication, self-protection |
| Family Tracing | Reintegration with parents/guardians |
| Monitoring & Mentorship | Regular attendance tracking |

5. Beneficiaries

Direct Beneficiaries

- 200 street-connected children

  - 132 boys

  - 68 girls

  - Age range: 6–17 years

Indirect Beneficiaries

- 120 parents/guardians

- 15 teachers

- Community members and peer groups

6. Results and Achievements

Output-Level Results

| Indicator | Target | Achieved |
| --- | --- | --- |
| Children enrolled in education | 200 | 200 |
| Learning kits distributed | 200 | 200 |
| Children receiving PSS | 200 | 187 |
| Families reintegrated | 100 | 83 |
| Teachers supported | 15 | 15 |

Outcome-Level Results

- 92% school retention rate after 9 months

- Significant improvement in literacy and numeracy skills

- Reduced street presence among beneficiaries

- Improved child self-esteem and social behavior

- Increased caregiver engagement in children’s education

7. Challenges and Mitigation

| Challenge | Mitigation |
| --- | --- |
| High mobility of children | Follow-up outreach & community mentors |
| Relapse to street life | Continuous counseling |
| Poverty of families | Referral to livelihoods programs |
| Overcrowded schools | Partnerships with community schools |

8. Lessons Learned

- Education must be combined with psychosocial support.

- Family reintegration increases sustainability.

- Flexible learning models are critical in fragile contexts.

- Community engagement reduces dropout rates.

9. Sustainability Strategy

- Strengthening links with local schools and MoGEI

- Parent support groups established

- Peer mentorship clubs formed

- Referral pathways to child protection networks

10. Conclusion

The project successfully transformed the lives of 200 vulnerable street children, shifting them from survival on the streets to structured learning environments. The initiative demonstrated that education remains one of the most powerful tools for peacebuilding, protection, and long-term resilience in South Sudan.

11. Donor Compliance & Accountability

- Beneficiary verification conducted

- Monitoring & Evaluation framework applied

- Financial and narrative reports submitted

- Safeguarding and child protection policies enforced

12. Recommendations

- Scale to additional counties (Bor, Wau, Malakal)

- Integrate school feeding

- Include vocational pathways for older youth

- Establish transitional shelters

Annex: Beneficiary Success Stories

1. From Street Life to the Classroom

Age: 14 | Location: Juba

Before joining the project, this boy spent his days collecting scrap metal at the market to survive. He had never attended school and often slept outdoors. He struggled with reading and felt ashamed to speak in public.

Through the Educate 200 Street Children project, he enrolled in accelerated learning classes and received a school kit. After six months, he could read simple English sentences and perform basic mathematics.

Today, he attends a local primary school and dreams of becoming a teacher.

“I feel like I have a future now. I am no longer afraid to hold a book.”

2. Reunited with Family and Back in School

Age: 12 | Location: Juba

This girl became separated from her family during displacement and ended up living on the streets for nearly two years. She was exposed to harassment and had lost all hope of returning to school.

Project social workers traced her relatives and facilitated family reunification. She received counseling and enrolled in a community school.

She is now living with her aunt and consistently ranks among the top students in her class.

“I used to think no one cared. Now I know I belong somewhere.”

3. From Begging to Leadership

Age: 16 | Location: Juba

This boy survived by begging and doing casual labor. He had developed aggressive behavior and avoided adults due to past abuse.

Through life skills sessions and psychosocial support, he gradually regained trust and confidence. He now serves as a peer mentor, helping younger children attend classes and follow school rules.

“I help others because someone helped me.”

4. A Mother’s Perspective

Caregiver of 10-year-old beneficiary

“My child had left home and refused to listen to me. Since joining this program, he has been calm, respectful, and goes to school every morning. This project saved my family.”

Key Impact Across Stories

- Restored access to education

- Improved self-esteem and behavior

- Family reintegration

- Reduced exposure to street risks

- Stronger community bonds