## summary program cost
GROWTH STRATEGY
LIST TO DO
DIGITAL SKILLS FOR YOUTH
Project Cost
| Item |  | Cost (USD)
| Program Development |  | 17000
| - Curriculum Design | 5000
| - Training Materials & Resources | 7000
| - Technology and Software Access | 5000
| Training Costs |  | 35000
| - Trainer Fees (for 3 months) | 25000
| - Venue Rental (if applicable) | 5000
| - Equipment (laptops, projectors, etc.) | 5000
| Internship Program |  | 20000
| - Internship Stipends | 15000
| - Mentorship and Support Services | 5000
| Marketing and Outreach |  | 13000
| - Promotional Materials | 5000
| - Community Engagement Activities | 5000
| - Advertising | 3000
| Monitoring and Evaluation |  | 10000
| - Data Collection and Analysis | 5000
| - Reporting Tools and Software | 3000
| - Evaluation Consultant | 2000
| Administrative Costs |  | 15000
| - Staff Salaries | 10000
| - Office Supplies | 3000
| - Miscellaneous Expenses | 2000
|  | Total | 110000

## Breakup of program cost
DIGITAL SKILLS FOR YOUTH
Project Cost - Monthwise
Month | Cost (USD) | Description
Month 1 | 8000 | Program Development (curriculum and materials)
Month 2 | 8000 | Trainer recruitment and training preparation
Month 3 | 8000 | Purchase of technology and equipment, venue setup
Month 4 | 10000 | Start of e-commerce training program (trainer fees, materials)
Month 5 | 10000 | Continued training and outreach activities
Month 6 | 10000 | Ongoing training & community engagement events
Month 7 | 8000 | Mid-program evaluation and adjustments
Month 8 | 10000 | Internship program preparation and recruitment
Month 9 | 10000 | Start of internship program (stipends and support)
Month 10 | 8000 | Continued internship support and mentorship
Month 11 | 8000 | Final evaluation and reporting preparation
Month 12 | 12000 | Program wrap-up, final reports, and dissemination of results
Total | 110000